Department: Financial Services

# Metsimaholo Local Municipality

2019/2020 Schedule C

December 2019

1. Table of Contents

| No. | Section Description | Page No. |
| --- | --- | --- |
| 1 | Table of Contents | 2 |
|  | Part 1 In - Year Report |  |
| 2 | Mayor’s Report | 3 |
| 3 | Resolutions | 4 |
| 4 | Executive Summary | 5 |
| 5 | In-Year budget statement tables | 28 |
|  | Supporting Documentation |  |
| 6 | Debtors’ Analysis | 38 |
| 7 | Creditors’ Analysis | 39 |
| 8 | Investment Portfolio analysis | 40 |
| 9 | Allocation and grant receipts and expenditure | 41 |
| 10 | Councillor allowances and employee benefits | 43 |
| 11 | Material variances to the service delivery and budget implementation plan | 44 |
| 12 | Capital programme performance | 57 |
| 13 | Quality Certificate | 67 |

2.	Report of the Executive Mayor

  - Council approved the 2019/2020 MTREF on 29 May 2019.

  - The information provided to the Executive Mayor is in compliance with Section 71 of the Local Government: Municipal Finance Management Act 56 of 2003. (MFMA).

  - This monthly report is referred to as the Section 71 Report or the Schedule C Report for ease of reference.

  - The report format is a standard template issued by National Treasury to all municipalities for completion and all the necessary information required to be reported on in terms of Section 71 is in included in the report.

  - In terms of Section 71, the Accounting Officer must by no later than 10 working days after the end of each month submit to the mayor and the relevant provincial treasury the monthly Section 71 (Schedule C) report.

  - The Executive Mayor also hereby confirms having received the monthly report timeously from the Accounting Officer.

3.	Resolutions

- That the monthly budget statement and supporting documentation for the month of December 2019 be noted.

# 4.	Executive Summary

The in-year reporting is prepared in accordance with the guidelines as set out in the Government Gazette, 17 April 2009 (Schedule C: in-year reports and mid-year budget and performance assessment of Municipalities) and National Treasury Guidelines, Schedule C. Section 71 Reporting Guideline, July 2013 issued by National Treasury.

Key Indicators for the period under review

- Operating 	Revenue: 	represents 	46% of budgeted revenue.

- Operating 	Expenditure:	represents	44% of budgeted expenditure.

- Capital 	Expenditure:	 represents 	10% of budgeted CAPEX

- Operating Revenue for the period under review

- Revenue for the period is on average 4.0% under budget.

- The property rates on farmland is billed in July 2019 for the full year.

- Waste management the Billing before free services are taken into account, is 48.7% of the budget on waste management.

- Sanitation for the period is 7% below budget before free basic services is taken into account.

- Water (47%) and electricity (48 %) are also below budget however this varies with consumption levels. However, the bulk purchase of water and electricity on the expenditure is already on 50%.

- Included in the revenue of R677 million is R131.5 million from Government Grants, of which R128.9 million was the Equitable Share (70% of the equitable share allocation for the year has already been received) R8.3 million was withheld due to the non-spending of grant funding.

- Operating expenditure for the period under review

- Operating expenditure for the period is 6% below budget.

- Provision was made for vacancies, including filling of posts of directors, for R44m (2018/19 plus 2019/2020)

- Accruals were made for bulk purchases of water and electricity, so that costs and revenues are matched in the same reporting period. Bulk purchase for electricity is 50% and water 49.6%.

- Capital Expenditure

- Capital spending is 9.7% of the budget.

Capital expenditure for the year (6 months) is as follows:

- Grants spending		   16.99%

- Borrowing			   0%

- Donation			   0%

- Own funding			   4.74%

- The approved budgeted Capital Expenditure for the year is R294.5m

- Capital expenditure is to be funded from the following sources:

Current month

(December 2019)

Spending

- Own funds 		  		R  61.3m   	R351k

- Donations				R  26.2m	R0

- Borrowings				R   56.0m	R0

- Grant funds (see below)		R 151.1m   	R9.7m

- Department of Energy			R 10m		R3.0m

- Municipal Infrastructure Grant		R 49.1m	R6.3m

- Department of Water Sanitation	R 15m	 	R332k

- Free State Sports			R 7m		R0

- Regional Bulk Infrastructure		R 70m		R0

Total Capex budget			R 294.5m	R3.2m

- Personnel expenses

- Employee cost for the month totalled R25.3 million

- Employee costs account for: -

  - 20.2% of the current month total expenditure

  - 26.6% of the year to date total expenditure

  - 42.3% of the total personnel budget for the year. Allocation on provision for leave, bonus and other employee benefits still outstanding. Directors not appointed.

- Remuneration of councillors:

- Councillor Allowances in terms of the upper limits for December 2019 amounts to R1.6 million

- Salaries and overtime (excluding Councillors)

Normal salary				R14 220 935

Overtime 					R  2 008 808

Total						R 15 721 078

Overtime %	of normal salary		14.13% 	(Prev. month 12.97 %)

Overtime incurred is to be monitored on an on-going basis by the Technical and Social Services directorates so as to reduce overtime to 5% of normal salaries.

This has not been achieved and is being reported every month.

The schedule below is an analysis of the overtime for the period July 2019 to December 2019 per department.

| Description | YTD Movement | Political Offices | Municipal Manager | Corporate Services | Social Services | Technical Services | Financial Services | LED |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| BASIC SALARIES | 83,991,730 | 5,364,014 | 5,349,387 | 6,078,607 | 28,418,724 | 20,248,891 | 12,378,343 | 83,991,730 |
| OVERTIME | 10,904,693 | 373,448 | 35,102 | 82,299 | 4,774,730 | 5,188,889 | 429,078 | 10,904,693 |
| Overtime as % of salaries | 12.98 | 6.96 | 0.66 | 1.35 | 16.80 | 25.63 | 3.47 | 12.98 |

- Distribution losses

The norms are set by National Treasury as per MFMA Circular 71- Uniform Ratios and Norms (January 2014) paragraph B –Distribution losses

- The electricity distribution loss of 14.95% (Ytd.) is above the acceptable threshold.

The acceptable norm is between 7% and 10%

(The loss for the 2018/2019 financial year was 6%)

- The water distribution loss of 15.5% (Ytd.) is below the acceptable norm.

The acceptable norm is between 15% and 30%.

(The loss for the 2018/2019 financial year was 16%)

|  | Purchased | Sold | (Loss)/ Gain | (Loss)/Gain at cost |
| --- | --- | --- | --- | --- |
|  | kl/kWh | kl/kWh | % | Rand value |
| November (Month) |  |  |  |  |
| Water (Kilolitre) | 1 687 319 | 1 172 000 | (30.54) | (R4 819 181) |
| Electricity (kWh) | 17 541 205 | 14 800 062 | (15.63) | (R1 540 796) |
| Year to date |  |  |  |  |
| Water (Kilolitre) | 10 723 147 | 9 056 654 | (15.5) | (R16 011 478) |
| Electricity (kWh) | 112 055 113 | 95 297 504 | (14.95) | (R13 032 680) |

The electricity losses are indicative of electricity theft and bridging of meters that needs to be investigated by the technical department.

Water losses also arise as a result of unmetered water at informal stands, calculated on average at 20kl per household:

- Themba Kubheka is 	50 000kl per month

- Zamdela is 		60 580kl per month.

Taking this 110 580 kl per month of unmetered water into account, the unaccounted for water loss will reduce further.

F: Current Assets - Debtors

- The debtor’s age analysis has increased to R1.667b (Nov R1.635b)

- The age analysis will continue to grow to the extent of non-payment below 100% and by interest charged every month on the arrears.

- Credit control measures must be applied strictly throughout the municipality, regardless of the customer type, whether it be businesses, schools, hospitals, government departments or private households. This process has been intensified.

- The municipality has in place a detailed Revenue Enhancement Strategy which will be rolled out in this financial year.

  - Presentations have been made to the Senior Management and also to managers and the item also served at MAYCO and is to be discussed at the Strategic Session of the Executive Mayor.

  - A further presentation will be made to the Council in due course.

  - This workshop has been repeatedly postponed and rollout can only be in the 2019/2020 year

Payment Rates

| Average | Excluding prepaid | Including prepaid |
| --- | --- | --- |
| For the month | 52.2% | 59.3% |
| November 2019 levies received in December 2019 |  |  |
| Year to date | 64.5% | 71.1% |
| July to November levies received in August 2019 to December 2019 |  |  |

- Calculation of payment ratio

- The average payment rate is calculated by expressing as a percentage:   Payments received in the month following the month in which levies were raised, and the levies raised for the month

- This calculation does not include prepaid electricity – as the payment rate on this is 100%, by virtue of it being prepaid.

- The average payment rate can exceed 100% which indicates that arrears have also been collected.

Year to Date - Average payment rates:  (excluding prepaid electricity)

|  | LEVIES | PAYMENTS | PAYMENT- |
| --- | --- | --- | --- |
|  | R 000 | R 000 | RATE (%) |
| Sasolburg | 355,674 | 293,739 | 82.6 |
| Zamdela | 92,472 | 10,005 | 10.8 |
| Deneysville | 10,638 | 8,544 | 80.3 |
| Refengkgotso | 20,362 | 184 | 0.9 |
| Oranjeville | 3,805 | 2,513 | 66.0 |
| Metsimaholo | 6,248 | 84 | 1.3 |
| Sundry Debtors | 810 | 937 | 115.7 |
| Metsimaholo | 490,009 | 316,006 | 64.49 |
| Local Municipality |  |  |  |

Monthly payment rate for: December 2019 (excluding prepaid)

|  | LEVIES | PAYMENTS | PAYMENT- |
| --- | --- | --- | --- |
|  | Nov-19 | Dec-19 |  |
|  | R 000 | R 000 | RATE (%) |
| Sasolburg | 53,650 | 35,362 | 65.9 |
| Zamdela | 14,240 | 1,507 | 10.6 |
| Deneysville | 2,513 | 2,161 | 86.0 |
| Refengkgotso | 3,383 | 41 | 1.2 |
| Oranjeville | 623 | 364 | 58.4 |
| Metsimaholo | 1,136 | 18 | 1.6 |
| Sundry Debtors | 194 | 57 | 29.4 |
| Metsimaholo | 75,739 | 39,510 | 52.17 |
| Local Municipality |  |  |  |

- The levies represent all the amounts billed, including indigent accounts, but excluding prepaid electricity sales

- The levied amount is net of the free basic amount.

- The payment amount does not include the indigent subsidy, as the free basic services are deducted from the levies.

- If the free basic services amounts are included in the levies and in the payments, the payment level will be slightly higher

- If prepaid electricity sales are included in the levies and in the payments, the payment level will be slightly higher.

Payment rate per ward – for the month

(Taking into account free basic services to indigents)

| Ward | MOVEMENT(Levies) November 2019 | RECEIPTS December 2019 | PERCENTAGE |
| --- | --- | --- | --- |
| 001 | 1,306,343.13 | -217,366.26 | 16.64 |
| 002 | -610,811.34 | -42,275.67 | -6.92 |
| 003 | 1,470,987.14 | -13,974.63 | 0.95 |
| 004 | 1,289,855.74 | -6,484.75 | 0.50 |
| 005 | 2,024,222.33 | -590,367.66 | 29.17 |
| 006 | 1,960,521.95 | -620,893.09 | 31.67 |
| 007 | 922,597.14 | -140,915.66 | 15.27 |
| 008 | 1,719,538.38 | -67,431.91 | 3.92 |
| 009 | 1,329,243.80 | -60,592.07 | 4.56 |
| 010 | 1,702,061.76 | -285,728.89 | 16.79 |
| 011 | 672,307.78 | -151,188.88 | 22.49 |
| 012 | 440,463.75 | -50,674.86 | 11.50 |
| 013 | 2,080,781.20 | -70,319.68 | 3.38 |
| 014 | 6,829,798.09 | -4,647,038.55 | 68.04 |
| 015 | 1,264,725.40 | -931,986.49 | 73.69 |
| 016 | 6,519,409.46 | -3,726,952.50 | 57.17 |
| 017 | 32,825,008.39 | -20,294,964.30 | 61.83 |
| 018 | 6,106,223.22 | -4,154,736.37 | 68.04 |
| 019 | 2,382,927.81 | -23,397.80 | 0.98 |
| 020 | 2,955,705.04 | -2,172,150.70 | 73.49 |
| 021 | 1 007 352.40 | -32 070.31 | 3.18 |

*Included industrial areas such as NATREF, SASOL, NALEDI

Payment rate per ward - Year to date

(Taking into account free basic services to indigents)

| Ward | MOVEMENT(Levies) | RECEIPTS | PERCENTAGE |
| --- | --- | --- | --- |
| 001 | 10,189,739.46 | -2,500,401.52 | 24.54 |
| 002 | 4,402,039.97 | -266,510.18 | 6.05 |
| 003 | 8,348,728.94 | -97,895.51 | 1.17 |
| 004 | 7,400,178.61 | -30,338.84 | 0.41 |
| 005 | 13,635,860.53 | -3,989,005.70 | 29.25 |
| 006 | 8,313,046.69 | -2,417,541.58 | 29.08 |
| 007 | 6,022,343.79 | -536,284.28 | 8.90 |
| 008 | 12,481,867.74 | -777,114.37 | 6.23 |
| 009 | 7,563,823.85 | -774,159.14 | 10.24 |
| 010 | 11,245,664.63 | -2,415,586.99 | 21.48 |
| 011 | 5,367,442.96 | -1,100,895.96 | 20.51 |
| 012 | 2,715,327.87 | -532,184.62 | 19.60 |
| 013 | 12,436,117.74 | -648,125.25 | 5.21 |
| 014 | 46,537,147.11 | -35,507,047.31 | 76.30 |
| 015 | 8,438,018.90 | -6,896,340.66 | 81.73 |
| 016 | 34,145,984.78 | -28,861,889.31 | 84.52 |
| 017 | 181,574,449.24 | -182,340,548.26 | 100.42 |
| 018 | 72,198,020.67 | -29,217,028.86 | 40.47 |
| 019 | 13,258,680.09 | -279,419.02 | 2.11 |
| 020 | 16,432,438.03 | -8,648,686.87 | 52.63 |
| 021 | 7,322,285.18 | -147,392.76 | 2.01 |

*Included industrial areas such as NATREF, SASOL, NALEDI

- Analysis of Budget, Actual and Collection

(Actual Billing compared to Budgeted Billing) (Including prepaid electricity) Comparison:   (as per General Ledger)

| Budget vs Levy | Budget per Month (19/20) | Actual Levy (December 2019) | Actual Cash Collection (January 2020) |
| --- | --- | --- | --- |
| Cleansing | R2 357 599 |  |  |
| Electricity | R24 852 098 |  |  |
| Sewer | R2 491 001 |  |  |
| Water | R39 848 771 |  |  |
| Assessment Rates | R17 933 680 |  |  |
| Housing/Hostel Interest | R471 268 R3 022 483 |  |  |
| Unallocated |  |  |  |
| Total | R90 976 900 |  |  |

Actual levies are 89.8% of Budgeted levies for the month

| Budget vs Levy | Budget per Month (19/20) | Actual Levy (November 2019) | Actual Cash Collection (December 2019) |
| --- | --- | --- | --- |
| Cleansing | R2 357 599 | R2 881 876 | R1 021 750 |
| Electricity | R24 852 098 | R21 128 260 | R18 741 326 |
| Sewer | R2 491 001 | R2 486 164 | R1 047 972 |
| Water | R39 848 771 | R35 004 940 | R7 568 428 |
| Assessment Rates | R17 933 680 | R15 459 827 | R6 698 282 |
| Housing/Hostel Interest | R471 268 R3 022 483 | R443 763 R4 260 069 | R77 826 R327 452 |
| Unallocated |  |  | R15 452 718 |
| Total | R90 976 900 | R81 664 899 | R50 935 754 |

- Actual levied is 	        	   89.8% 	of budgeted levies for the month.

- Actual cash collection is 	   62.4% 	of budgeted levies for the month

- Actual cash collection is 	   55.9% 	of actual levied-previous month

- Councillors’ balances and arrears outstanding as at 31 December 2019

Councillor Arrears

Councillor balances outstanding		R848.5k 	 (Nov 2019– R819k)

Arrears longer than 3 months 		R778.4k   	 (Nov 2019 – R753k)

The amount has increased from the previous month for the period 3 months and longer

Municipal Systems Act

A Councillor may not be in arrears to the municipality for rates and service charges for a period longer than 3 months

It is the duty of the chairperson of municipal Councils to take necessary action where the Code of Conduct for Councillors has been breached

Councillors balance outstanding as at 31 December 2019

| Account No | Name | Initials | Account Type | Current Ageing | 30 Days Ageing | 60 Days Ageing | 90 Days Ageing | 120+ Days Ageing | Total Ageing | Remarks |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 525381 | DU TOIT | T | Normal | 5,758.62 | 3,982.02 | 3,693.22 | 4,386.89 | 16,154.94 | 33,975.69 | No Arrangement |  |
| 108921 | DYWILI (MY2436) | NN | Normal | 1,052.71 | 787.93 | 881.22 | 943.85 | 26,062.22 | 29,727.93 | No Arrangement |  |
| 536637 | LEOTLELA (MY2403) | PR | Normal | 176.08 | 175.18 | 174.29 | 173.40 | 11,180.65 | 11,879.60 | No Arrangement |  |
| 592959 | LEOTLELA (MY2403) | PR | Handed over | - | - | - | - | 10,944.67 | 10,944.67 | No Arrangement |  |
| 108353 | MAHLAELA (MY2428) | MD | Normal | 494.14 | 447.45 | 223.89 | 219.29 | 8,677.52 | 10,062.29 | No Arrangement |  |
| 595729 | MALINDI (MY2417) | MJ | Handed over | - | - | - | - | 5,129.94 | 5,129.94 | No Arrangement |  |
| 593277 | MATWA (MY2444-R616 PM) | SM | Handed over | - | - | - | - | 11,393.81 | 11,393.81 | No Arrangement |  |
| 872070 | MATWA (MY2444-R616 PM) | SM | Abeyance | - | - | - | - | 6,146.92 | 6,146.92 | No Arrangement |  |
| 553229 | MOISI T J TAATS (MY2405) | ME` | Normal | 440.56 | 194.97 | 378.64 | 1,709.77 | 4,369.34 | 7,093.28 | No Arrangement |  |
| 109049 | MOKOENA M E Maseko (MY2406) | DE | Normal | 448.46 | 332.04 | 310.06 | 309.16 | 38,456.12 | 39,855.84 | No Arrangement |  |
| 590648 | MOKOENA M E Maseko (MY2406) | DE | Handed over | - | - | - | - | 10,839.32 | 10,839.32 | No Arrangement |  |
| 565105 | MOKWENA N Mokoena (MY2439) | MS | Arrangement | - | - | - | - | 26,298.42 | 26,298.42 | Honoured |  |
| 594687 | MOKWENA N Mokoena (MY2439) | MS | Handed over | - | - | - | - | 779.19 | 779.19 | No Arrangement |  |
| 791179 | MOKWENA N Mokoena (MY2439) | MS | Normal | 436.93 | 3,499.51 | - | - | 900.00 | 4,836.44 | No Arrangement |  |
| 594135 | MOKWENA N Mokoena (MY2439) | RE | Handed over | - | - | - | - | 25,181.67 | 25,181.67 | No Arrangement |  |
| 12921 | MOLETA S Motlhale (MY2411) | M | Normal | 600.49 | 594.24 | 593.06 | 587.21 | 17,748.71 | 20,123.71 | No Arrangement |  |
| 553206 | MONYELA P M Mokoena(MY2431) | SD | Normal | 196.00 | 194.94 | 193.96 | 179.83 | 9,625.19 | 10,389.92 | No Arrangement |  |
| 108066 | MOSOKWENI (MY2437) | FD | Normal | 440.50 | 719.54 | 438.44 | 426.67 | 63,680.20 | 65,705.35 | No Arrangement |  |
| 537934 | MOTAUNG (MY2410) | TA | Normal | 329.02 | 321.50 | 319.44 | 317.48 | 13,049.14 | 14,336.58 | No Arrangement |  |
| 106180 | MOTJEANE S M Motjeane(MY2407) | RJ | Normal | 4,408.69 | 4,099.85 | 4,124.79 | 11,667.64 | 84,999.87 | 109,300.84 | No Arrangement |  |
| 103466 | MTSHALI (MY2420) | BP | Normal | 923.89 | 634.27 | 614.87 | 595.51 | 11,081.95 | 13,850.49 | No Arrangement |  |
| 562315 | MTSHALI (MY2420) | BP | Arrangement | - | - | - | - | 29,404.84 | 29,404.84 | Honoured |  |
| 526816 | MZIZI S S Kobo(MY2426) | TJ | Normal | 261.42 | 205.24 | 261.42 | 213.99 | 31,066.53 | 32,008.60 | No Arrangement |  |
| 108037 | NKHELOANE M Nkheloane (MY2433) | NE | Normal | 695.38 | 691.42 | 694.36 | 689.64 | 13,576.31 | 16,347.11 | No Arrangement |  |
| 575013 | NKHELOANE M Nkheloane (MY2433) | NE | Arrangement | - | - | - | - | 6,081.10 | 6,081.10 | Honoured |  |
| 592910 | NKHELOANE M Nkheloane (MY2433) | NE | Handed over | - | - | - | - | 31,356.25 | 31,356.25 | No Arrangement |  |
| 107830 | NYAKU-MAPHEELLE (MY2416) | MM | Normal | 1,926.42 | 1,637.33 | 1,325.40 | 1,637.33 | 7,972.06 | 14,498.54 | No Arrangement |  |
| 830645 | NYAKU-MAPHEELLE (MY2416) | MM | Arrangement | - | - | - | - | 6,002.52 | 6,002.52 | Honoured |  |
| 589204 | POHO(MY2432) | MS | Arrangement | - | - | - | - | 13,940.88 | 13,940.88 | Honoured |  |
| 590215 | SEMELA T S Mokoena(MY2415) | MF | Normal | 736.88 | 731.09 | 730.35 | 725.84 | 53,860.84 | 56,785.00 | No Arrangement |  |
| 512521 | TELANE (MY2429) | P | Normal | 2,076.62 | 5,016.23 | 2,512.98 | 839.47 | 81,677.95 | 92,123.25 | No Arrangement |  |
| 575987 | TSHONGWE (MY2430) | SL | Normal | 1,623.95 | 1,919.16 | 2,008.31 | 3,107.13 | - | 8,658.55 | No Arrangement |  |
| 511192 | TSOTETSI (MY2423) | P | Normal | 469.94 | 468.88 | 467.84 | 466.79 | 71,588.57 | 73,462.02 | No Arrangement |  |
|  |  |  |  | 23,496.70 | 26,652.79 | 19,946.54 | 29,196.89 | 749,227.64 | 848,520.56 |  |  |

- Officials balances and arrears as at December 2019

Those officials who have not made arrangements - Deductions of up to 20% are made from their salaries.

Staff arrears (outstanding greater than 90 days)

Staff (officials) balances outstanding greater than 90 days totalled R1.056m (Nov – R1.2m)

Staffs have been reminded of the requirements of the Municipal Systems Act in that they are not to have arrears for a period longer than 3 months.

- Deductions were effected from the staff salaries as from the month of September 2014 in cases where no arrangements have been made.

- Where arrangements are in place this will be reviewed and the arrangements amounts may be increased. Affordability will be taken into consideration.

- All the officials owing may not be on the list as their residential details is not available. Information is not declared by officials.

Those officials who have not made arrangements - Deductions of up to 20% have been made from their salaries from November 2017. Officials were once again reminded to pay their consumers’ account and to make arrangements.

Officials with arrears will be specifically addressed in the Revenue Enhancement Strategy. The workshop has been postponed and roll out can only happen in 2018/2019 year.

Officials balance outstanding as at 31 December 2019

| Account No | Name | Initials | Account Type | Current Ageing | 30 Days Ageing | 60 Days Ageing | 90 Days Ageing | 120+ Days Ageing | Total Ageing | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 598702 | MPETJEKANA (A48082) | NS | Handed over | 469.78 | 370.88 | - | 17.25 | 7,687.51 | 8,545.42 | Arrangement M & G |
|  |  |  |  | 469.78 | 370.88 | - | 17.25 | 7,687.51 | 8,545.42 |  |
| Account No | Name | Initials | Account Type | Current Ageing | 30 Days Ageing | 60 Days Ageing | 90 Days Ageing | 120+ Days Ageing | Total Ageing | Remarks |
| 589598 | KHUMALO TD032(R550) | MR | Arrangement | - | - | - | - | 16,444.63 | 16,444.63 | Honoured |
| 580348 | KOK (1119)(R1000) | TJ | Arrangement | - | - | - | - | 12,454.82 | 12,454.82 | Honoured |
| 599787 | MABULA(A48085)(R1000.00) | MM | Arrangement | - | - | - | - | 867.74 | 867.74 | Honoured |
| 578762 | MADLALA(A02557) | BT | Arrangement | - | - | - | - | 8,350.18 | 8,350.18 | Honoured |
| 830745 | MALOKA( TD055) | MM | Arrangement | - | - | - | - | 10,918.73 | 10,918.73 | Honoured |
| 581425 | MAROSHA 2541 | PA&MA | Arrangement | - | - | - | 1,227.45 | 3,251.70 | 4,479.15 | Honoured |
| 830780 | MATSEMULA TD035 | MM | Arrangement | - | - | - | - | 4,248.92 | 4,248.92 | Honoured |
| 562772 | MAZIBUKO_(AMPT 00150) | NE | Arrangement | - | - | - | - | 6,289.09 | 6,289.09 | Honoured |
| 830690 | MGXWASHU A19143 | MS | Arrangement | - | - | - | - | 14,504.79 | 14,504.79 | Honoured |
| 830839 | MKHABELA | MG&GN | Arrangement | - | - | - | - | 19,406.89 | 19,406.89 | Honoured |
| 561605 | MNGUNI(A47447) | NB | Arrangement | - | - | - | - | 1,860.39 | 1,860.39 | Honoured |
| 830903 | MOEMISE | MS&DJ | Arrangement | 270.25 | 1,395.55 | 1,273.53 | 1,224.70 | 1,397.84 | 5,561.87 | Honoured |
| 830242 | MOKOENA (A19174)(R600) | MS | Arrangement | - | - | - | - | 5,652.13 | 5,652.13 | Honoured |
| 578911 | MONAHENG A19220 R600 | JC | Arrangement | - | - | - | - | 5,402.48 | 5,402.48 | Honoured |
| 568212 | MONGALE(1724) | M | Arrangement | - | - | - | - | 626.02 | 626.02 | Honoured |
| 576073 | MOTLOUNG_PO3000 | MS | Arrangement | - | - | - | - | 2,949.68 | 2,949.68 | Honoured |
| 830884 | MOTSITSI (1125) | MD&AB | Arrangement | - | - | - | 1,681.68 | 861.62 | 2,543.30 | Honoured |
| 588504 | MOTSITSI A24725(CANCL20191219) | MJ | Arrangement | - | - | - | - | 12,246.33 | 12,246.33 | Honoured |
| 561146 | NDUMO 0127 | LL | Arrangement | - | - | - | - | 286.91 | 286.91 | Honoured |
| 830680 | SELEPE(R400)A24734 | J | Arrangement | - | - | - | - | 4,669.61 | 4,669.61 | Honoured |
| 830112 | SELIANE (BI4738) | RD&CN | Arrangement | - | - | - | - | 9,766.48 | 9,766.48 | Honoured |
| 589284 | SELIANE(BI4738) | RD | Arrangement | - | - | - | - | 1,355.13 | 1,355.13 | Honoured |
| 830387 | SHEBE (5712) | KA | Arrangement | - | - | - | - | 14,859.95 | 14,859.95 | Honoured |
| 830842 | SHEBE (5712) | KA | Arrangement | - | - | - | - | 17,049.37 | 17,049.37 | Honoured |
| 566565 | SIMELANE A24736(R830) | LA | Arrangement | - | - | - | - | 5,413.57 | 5,413.57 | Honoured |
| 830126 | TSHABALALA(3806) | PP | Arrangement | - | - | - | - | 32,660.64 | 32,660.64 | Honoured |
| 562276 | TSHABALALA_A49339 | NS | Arrangement | - | - | - | - | 7,891.96 | 7,891.96 | Honoured |
| 588456 | TSHABANGU 00126 | SM | Arrangement | - | - | - | - | 1,878.03 | 1,878.03 | Honoured |
| 830421 | VAN DER MERWE 0129 | KJH&EA | Arrangement | - | - | - | - | 15,101.89 | 15,101.89 | Honoured |
| 562477 | ZWANE (A02558) | SE&HB | Arrangement | - | - | - | - | 9,655.23 | 9,655.23 | Honoured |
|  |  |  |  | 270.25 | 1,395.55 | 1,273.53 | 4,133.83 | 248,322.75 | 255,395.91 |  |
| Account No | Name | Initials | Account Type | Current Ageing | 30 Days Ageing | 60 Days Ageing | 90 Days Ageing | 120+ Days Ageing | Total Ageing | Remarks |
| 512582 | HLAHANE__(D7212) | J | Normal | 384.25 | 1,063.97 | 1,189.83 | 535.34 | 592.89 | 3,766.28 | No Arrangement |
| 558233 | KASA (1022) | LN | Normal | 482.52 | 475.53 | 476.21 | 389.31 | 12,250.19 | 14,073.76 | No Arrangement |
| 588221 | KHOZA | T | Normal | 1,063.36 | 1,045.46 | 1,000.68 | 1,356.50 | 10,855.97 | 15,321.97 | No Arrangement |
| 792036 | LERATA__4905 | DP | Normal | 161.40 | 160.19 | 158.98 | 157.77 | 891.21 | 1,529.55 | No Arrangement |
| 574530 | LETSHWARA_0123 | DJ | Normal | 589.91 | 742.60 | 608.29 | 633.58 | 1,090.20 | 3,664.58 | No Arrangement |
| 599726 | MABENA(00119) | MS&SV | Normal | 1,774.00 | 1,913.25 | 1,895.51 | 300.69 | - | 5,883.45 | No Arrangement |
| 556399 | MACHAEA | PV | Normal | 1,118.52 | 1,067.58 | 850.62 | 841.50 | 8,469.89 | 12,348.11 | No Arrangement |
| 319590 | MAKHELEDISA (3806) | SJ | Normal | 589.63 | 592.27 | 589.32 | 591.99 | 17,816.97 | 20,180.18 | No Arrangement |
| 791508 | MAKO (A19364) | MK | Normal | 1,835.51 | 1,812.28 | 1,975.97 | 2,118.32 | 61,649.45 | 69,391.53 | No Arrangement |
| 105655 | MALINDI(A19218) | MA | Normal | 742.90 | 738.17 | 741.11 | 737.73 | 3,472.09 | 6,432.00 | No Arrangement |
| 603246 | MASUKU | TL | Normal | 682.65 | 677.48 | 672.30 | 667.14 | 7,851.41 | 10,550.98 | No Arrangement |
| 550463 | MBABALE (1927- R300PM) | JM | Normal | 310.84 | 798.69 | 640.51 | 573.99 | 37,807.33 | 40,131.36 | No Arrangement |
| 538270 | MOFOKENG__00141 | TE | Normal | 401.22 | 359.00 | 1,061.60 | 1,014.12 | - | 2,835.94 | No Arrangement |
| 526623 | MOFOKENG__080313 | DE | Normal | 641.17 | 638.26 | 641.20 | 636.50 | 8,983.05 | 11,540.18 | No Arrangement |
| 511919 | MOFOKENG__D8003 | PJ | Normal | 309.24 | 351.11 | 329.35 | 318.13 | 14,556.63 | 15,864.46 | No Arrangement |
| 568955 | MOHOLI(A10319) | ML&NR | Normal | 1,120.37 | 851.73 | 1,338.29 | 850.64 | 890.59 | 5,051.62 | No Arrangement |
| 107168 | MOKHELE A15891 | SR | Normal | 1,222.27 | 945.93 | 948.47 | 1,278.68 | 23,899.75 | 28,295.10 | No Arrangement |
| 604116 | MOKOENA | SJ&SJ | Normal | 1,021.79 | 1,701.74 | 1,625.11 | 1,032.16 | 2,471.98 | 7,852.78 | No Arrangement |
| 795004 | MOKOENA | TS | Normal | 638.13 | 628.55 | 662.11 | 302.51 | - | 2,231.30 | No Arrangement |
| 604348 | MOKOENA (1101) | SJ&SJ | Normal | 1,262.11 | 1,264.09 | 1,099.86 | 1,129.62 | 1,870.64 | 6,626.32 | No Arrangement |
| 581317 | MOKOENA (A19174)(R600) | MS | Normal | 1,180.94 | 1,010.80 | 1,336.00 | 879.19 | 10,287.48 | 14,694.41 | No Arrangement |
| 1753 | MOKOENA(1101) | SJ | Normal | 723.05 | 801.46 | 754.09 | 810.76 | 2,164.07 | 5,253.43 | No Arrangement |
| 794364 | MOKOENA(1101) | SJ&SJ | Normal | 1,361.81 | 1,433.24 | 1,320.45 | 1,347.45 | 2,454.44 | 7,917.39 | No Arrangement |
| 871950 | MONAHENG A19220 R600 | JC | Abeyance | - | - | - | - | 12,061.37 | 12,061.37 | No Arrangement |
| 100415 | MOTSEI 1006 | ZA | Normal | 792.64 | 521.13 | 1,129.27 | 515.86 | 10,315.90 | 13,274.80 | No Arrangement |
| 109198 | MOTSIE__00119 | JM | Normal | 535.88 | 274.25 | 307.34 | 617.10 | 9,121.12 | 10,855.69 | No Arrangement |
| 108932 | MOTSOENENG 1171 | MJ | Normal | 1,295.07 | 1,013.00 | 1,022.46 | 3,663.23 | 14,470.26 | 21,464.02 | No Arrangement |
| 109232 | NGQUBA(A42517) | T | Normal | 2,175.06 | 1,895.60 | 1,900.49 | 1,974.80 | 42,386.63 | 50,332.58 | No Arrangement |
| 604363 | NKUMANE | SB | Normal | 1,333.82 | 1,010.29 | 999.83 | 1,599.57 | 6,044.90 | 10,988.41 | No Arrangement |
| 605027 | RADEBE(3840) & MASOMBUKA | PM&NB | Normal | 888.76 | 487.54 | 458.72 | 487.45 | 973.61 | 3,296.08 | No Arrangement |
| 794833 | RAMATHE | JS | Normal | 1,888.91 | 2,394.88 | 2,561.60 | 1,792.04 | 89,607.06 | 98,244.49 | No Arrangement |
| 104043 | SEFATSA W07673 | LA | Normal | 956.23 | 10,686.32 | 1,085.50 | 938.04 | 71,550.17 | 85,216.26 | No Arrangement |
| 526983 | SOLANI (080018) | NM | Normal | 791.64 | 2,167.82 | 847.39 | 687.25 | 29,713.95 | 34,208.05 | No Arrangement |
| 795037 | TOM 00140 | NE | Normal | 1,028.33 | 1,031.00 | 1,327.53 | 1,654.04 | 611.64 | 5,652.54 | No Arrangement |
| 599634 | TSOTETSI(00114) | TE | Normal | 1,201.25 | 1,037.88 | 1,332.19 | 2,055.53 | 280.29 | 5,907.14 | No Arrangement |
| 27524 | ZAKWE A024 | OL | Normal | 605.30 | 603.31 | 605.08 | 601.42 | 2,425.08 | 4,840.19 | No Arrangement |
| 592756 | KOK (1119)(R1000) | TJ | Handed over | - | - | - | - | 3,828.31 | 3,828.31 | No Arrangement M & G |
| 597055 | MALINDI(A19218) | MA | Handed over | - | - | - | - | 29,844.65 | 29,844.65 | No Arrangement M & G |
| 582620 | MATSEMULA TD035 | MM | Handed over | 516.93 | - | - | - | 43,175.80 | 43,692.73 | No Arrangement M & G |
| 596744 | MBIKOLO(W10010) | MM | Handed over | - | - | - | - | 9,164.85 | 9,164.85 | No Arrangement M & G |
| 590644 | MOKOENA (A19174)(R600) | MS | Handed over | - | - | - | - | 11,538.32 | 11,538.32 | No Arrangement M & G |
| 593107 | MONAHENG A19220 R600 | JC | Handed over | - | - | - | - | 7,664.79 | 7,664.79 | No Arrangement M & G |
| 598707 | NGQUBA(A42517) | T | Handed over | - | - | - | - | 36,513.50 | 36,513.50 | No Arrangement M & G |
| 588031 | VILAKAZI (4301) | MC | Handed over | - | - | - | - | 21,872.42 | 21,872.42 | No Arrangement M & G |
| 597748 | ZAKWE A024 | OL | Handed over | 40.25 | - | - | 40.25 | 3,203.42 | 3,283.92 | No Arrangement M & G |
|  |  |  |  | 33,667.66 | 44,196.40 | 35,493.26 | 35,130.20 | 686,694.27 | 835,181.79 |  |
| Account No | Name | Initials | Account Type | Current Ageing | 30 Days Ageing | 60 Days Ageing | 90 Days Ageing | 120+ Days Ageing | Total Ageing | Remarks |
| 339440 | KOK (1119)(R1000) | TJ | Normal | 2,130.02 | 1,488.31 | 2,322.94 | 1,745.89 | 15,356.61 | 23,043.77 |  |
| 106694 | MABULA(A48085)(R1000.00) | MM | Normal | 1,247.98 | 1,170.95 | 972.40 | 929.12 | 1,562.97 | 5,883.42 |  |
| 530162 | MADLALA(A02557) | BT | Normal | 933.95 | 1,041.63 | 1,112.27 | 426.58 | 557.00 | 4,071.43 |  |
| 560323 | MKHABELA | MG&GN | Normal | 2,921.37 | 2,300.44 | 2,275.49 | 2,477.03 | 3,350.40 | 13,324.73 |  |
| 604272 | MOTSITSI (1125) | MD&AB | Normal | 5,178.87 | - | - | 58.04 | 1,067.72 | 6,304.63 |  |
| 552905 | SIMELANE A24736(R830) | LA | Normal | 309.61 | 1,370.66 | 7,480.42 | 255.47 | 8,656.54 | 18,072.70 |  |
| 795182 | TSHABALALA(3806) | PP | Normal | 1,804.67 | 1,419.59 | 1,645.33 | 2,026.84 | 11,626.03 | 18,522.46 |  |
| 3931 | TSHABANGU 00126 | SM | Normal | 512.30 | 631.39 | 549.24 | 624.34 | 22,929.90 | 25,247.17 |  |
|  |  |  |  | 15,038.77 | 9,422.97 | 16,358.09 | 8,543.31 | 65,107.17 | 114,470.31 |  |
|  |  |  | TOTAL | 49,446.46 | 55,385.80 | 53,124.88 | 47,824.59 | 1,007,811.70 | 1,213,593.43 |  |

# J Current Liabilities

- The creditor’s age analysis decreased from R152m to R148m

- The payment of creditors affects the cash flow situation.

The top 6 creditors balances are as follows: -

| 1. | Government Garage | June 2019 statement | R16 150 000 |
| --- | --- | --- | --- |
| 2. | Department of Water Affairs | November 2018 statement | R42 697 220 |
| 3. | Eskom | Current account | R 20 850 705 |
| 4. | Rand Water | Current account | R 15 626 640 |
| 5 | Millennium Pumps | October 2019 statement | R1 007 828 |
| 6. | Aqua Transport | July 2018 Statement | R 985 890 |
|  | Total of top 6 | 65.7 % of total creditors | R97 318 283 |
| 7. | Other creditors |  | R50 681 717 |
|  | Total creditors |  | R148 000 000 |

- Government Garage:

No payments were made in December 2019.  No arrangements were made for the payment of outstanding balance.

- Department of Water Affairs:

The monthly account is paid every month.

A formal agreement for payments of the arrear amount is not yet signed.

# There is a dispute on the account and our legal department has been engaging with them to reach a solution

# K: Budget Related Charts

# Chart 1:	Revenue by Major source

Revenue from own sources represents 59.7% of total revenue in December 2019.

The four major sources of own revenue for December 2019 is as follows:

- Water					38.4%

- Electricity	 			29.2%

- Property rates				18.9%

- Interest – outstanding debtors	 5.6%

- Waste Management			 3.5%

# Total				           95.6%

The figures on the chart for December 2019 are cumulative (Year-to-date).

# Chart 2:	Revenue by Minor Source

# The figures on the chart are cumulative (year to date)

- Interest earned on outstanding debtors amounts to R4 384 000 in December 2019.

- Revenue from fines amounts to R98 000 in December 2019.

# Chart 3:	Operating Expenditure by Major Type

# The figures on the chart are cumulative (year to date)

The major expenses for December 2019 are as follows:

- Depreciation				30.9%

- Employee related costs		20.2%

- Bulk Purchases-Electricity		22.2 %

- Bulk purchases – Water		19.5%

- Debt Impairment			10.2%

TOTAL				            79.0%

# Chart 4:	Capital Expenditure Monthly Trend

# Chart 5:	Consumer Debtors Consumers per period

# Consumers per category

COMMENTS ON THE DEBTORS BOOK

Performance of the debtors’ book

- The gross debtors book exceeds R1 billion and the latest amount at end of December 2019 is R1 666 649 000 (June 2019 – R1 484 727 133)

- The concentration of the debtors’ book is mainly in the category of household consumers

- The debtors’ book is an accumulation of debt over many years

- The debtors’ book will continue to grow for as long as the payment level is below 100%, in addition interest is charged on the outstanding balances which also contributes to the growth in the debtors’ book

Impairment of the debtors’ book

- The Impairment on the debtors’ book as at 30 June 2019 is R1 290 138 259 and represents 89.9% of the gross debtor’s book

- Impairment for the six months totalled R72 756 363

- Total impairment as at December 2018 is R1 362 894 622, and represents 81.8% of the gross debtor’s book

Budget implications

- The budget is prepared based on an estimated projection of the payment level and not on the balance of the debtors’ book

Debt collection Control

- Debt collection control measures are to be applied to all household consumers throughout the municipality

- The municipality does not have sufficient capacity in the debt management department to manage all the household debt.

- The debt management department needs to be further capacitated

- No debt collection control measures in all the areas

- The consumption of water and the non-payment for water consumption must be address as a matter of urgency. The payment rate on water for the period July to November 2019 is 20%

5. In -Year	Budget Statement Tables

| FS204 Metsimaholo - Table C1 Monthly Budget Statement Summary - M06 December |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description | 2018/19 | Budget Year 2019/20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Audited Outcome | Original Budget | Adjusted Budget | Monthly actual | YearTD actual |  | YearTD budget |  | YTD variance |  | YTD variance |  | Full Year Forecast |  |
| R thousands |  |  |  |  |  |  |  |  |  |  | % |  |  |  |
| Financial Performance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Property rates | 143 648 | 215 204 | 215 204 | 14 792 | 110 258 |  | 107 602 |  | 2 656 |  | 2% |  | 215 204 |  |
| Service charges | 698 482 | 831 098 | 831 098 | 58 049 | 403 812 |  | 415 549 |  | (11 737) |  | -3% |  | 831 098 |  |
| Investment revenue | 3 784 | 1 500 | 1 500 | 109 | 1 176 |  | 750 |  | 426 |  | 57% |  | 1 500 |  |
| Transfers and subsidies | 168 246 | 189 039 | 189 039 | 52 660 | 131 462 |  | 94 519 |  | 36 943 |  | 39% |  | 189 039 |  |
| Other own revenue | 54 659 | 75 211 | 75 211 | 5 286 | 30 568 |  | 37 605 |  | (7 038) |  | -19% |  | 75 211 |  |
| Total Revenue (excluding capital transfers and contributions) | 1 068 819 | 1 312 052 | 1 312 052 | 130 897 | 677 276 |  | 656 026 |  | 21 250 |  | 3% |  | 1 312 052 |  |
| Employee costs | 288 618 | 359 390 | 358 299 | 25 284 | 151 995 |  | 179 131 |  | (27 137) |  | -15% |  | 358 299 |  |
| Remuneration of Councillors | 17 554 | 19 855 | 19 855 | 1 559 | 9 353 |  | 9 928 |  | (575) |  | -6% |  | 19 855 |  |
| Depreciation & asset impairment | 72 118 | 83 085 | 83 085 | 38 806 | 38 806 |  | 41 543 |  | (2 737) |  | -7% |  | 83 085 |  |
| Finance charges | 8 063 | 6 448 | 6 448 | 199 | 615 |  | 3 224 |  | (2 609) |  | -81% |  | 6 448 |  |
| Materials and bulk purchases | 414 318 | 511 948 | 512 405 | 36 609 | 246 813 |  | 256 001 |  | (9 188) |  | -4% |  | 512 405 |  |
| Transfers and subsidies | 297 | 42 | 42 | – | 44 |  | 21 |  | 23 |  | 108% |  | 42 |  |
| Other expenditure | 365 272 | 329 619 | 330 253 | 22 750 | 124 577 |  | 165 349 |  | (40 772) |  | -25% |  | 330 253 |  |
| Total Expenditure | 1 166 241 | 1 310 388 | 1 310 388 | 125 207 | 572 201 |  | 655 197 |  | (82 996) |  | -13% |  | 1 310 388 |  |
| Surplus/(Deficit) | (97 422) | 1 665 | 1 665 | 5 690 | 105 074 |  | 828 |  | 104 246 |  | 12583% |  | 1 665 |  |
| Transfers and subsidies - capital (monetary allocations) (National / Provincial and District) | 60 980 | 81 069 | 81 069 | – | – |  | 40 535 |  | (40 535) |  | -100% |  | 81 069 |  |
| Contributions & Contributed assets | 65 141 | 96 200 | 96 200 | – | – |  | 48 100 |  | (48 100) |  | -100% |  | 96 200 |  |
| Surplus/(Deficit) after capital transfers & contributions | 28 698 | 178 934 | 178 934 | 5 690 | 105 074 |  | 89 463 |  | 15 611 |  | 17% |  | 178 934 |  |
| Share of surplus/ (deficit) of associate | – | – | – | – | – |  | – |  | – |  |  |  | – |  |
| Surplus/ (Deficit) for the year | 28 698 | 178 934 | 178 934 | 5 690 | 105 074 |  | 89 463 |  | 15 611 |  | 17% |  | 178 934 |  |
| Capital expenditure & funds sources |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Capital expenditure | 117 339 | 294 517 | 294 517 | 10 003 | 28 576 |  | 147 259 |  | (118 683) |  | -81% |  | 294 517 |  |
| Capital transfers recognised | 113 156 | 177 269 | 177 269 | 9 652 | 25 670 |  | 88 635 |  | (62 965) |  | -71% |  | 177 269 |  |
| Borrowing | – | 55 972 | 55 972 | – | – |  | 27 986 |  | (27 986) |  | -100% |  | 55 972 |  |
| Internally generated funds | 4 183 | 61 275 | 61 275 | 351 | 2 906 |  | 30 638 |  | (27 732) |  | -91% |  | 61 275 |  |
| Total sources of capital funds | 117 339 | 294 517 | 294 517 | 10 003 | 28 576 |  | 147 259 |  | (118 683) |  | -81% |  | 294 517 |  |
| Financial position |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total current assets | 838 444 | 344 423 | 344 423 |  | 1 565 190 |  |  |  |  |  |  |  | 344 423 |  |
| Total non-current assets | 1 688 390 | 1 625 784 | 1 625 784 |  | 1 678 161 |  |  |  |  |  |  |  | 1 625 784 |  |
| Total current liabilities | 984 576 | 285 112 | 285 112 |  | 1 599 398 |  |  |  |  |  |  |  | 285 112 |  |
| Total non-current liabilities | 3 828 | 59 570 | 59 570 |  | 3 828 |  |  |  |  |  |  |  | 59 570 |  |
| Community wealth/Equity | 1 606 741 | 1 625 525 | 1 625 525 |  | 1 640 124 |  |  |  |  |  |  |  | 1 625 525 |  |
| Cash flows |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Net cash from (used) operating | 97 785 | 83 249 | 83 249 | 22 822 | 64 652 |  | 41 625 |  | (23 027) |  | -55% |  | 83 249 |  |
| Net cash from (used) investing | (86 656) | (134 237) | (134 237) | 8 298 | (62 907) |  | (67 119) |  | (4 211) |  | 6% |  | (134 237) |  |
| Net cash from (used) financing | (3 312) | (5 924) | (5 924) | 1 494 | (248) |  | (2 962) |  | (2 714) |  | 92% |  | (5 924) |  |
| Cash/cash equivalents at the month/year end | 20 444 | (52 216) | (52 216) | – | 36 915 |  | (28 456) |  | (65 371) |  | 230% |  | (56 912) |  |
| Debtors & creditors analysis | 0-30 Days | 31-60 Days | 61-90 Days | 91-120 Days | 121-150 Dys |  | 151-180 Dys |  | 181 Dys-1 Yr |  | Over 1Yr |  | Total |  |
| Debtors Age Analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total By Income Source | 76 840 | 72 275 | 43 540 | 71 546 | 44 133 |  | 32 937 |  | 185 674 |  | 1 139 705 |  | 1 666 649 |  |
| Creditors Age Analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total Creditors | 42 114 | 4 817 | 2 676 | 1 323 | 97 070 |  | – |  | – |  | – |  | 148 000 |  |

# VIREMENTS:   December 2019

| Account no | Description | Reference | Date | Original | Additional | Reduced |
| --- | --- | --- | --- | --- | --- | --- |
| 33212265170PRMRCZZHO | OS: PRINTING SERVICES | MEMO FROM CORPORATE SERVICES | 20191204 | 0,00 | 870 000,00 | 0,00 |
| 33212323600PRMRCZZHO | INVENTORY - MATERIALS & SUPPLIES | MEMO FROM CORPORATE SERVICES | 20191204 | 889 090,00 | 0,00 | 870 000,00 |
| 33222265170PRMRCZZHO | OS: PRINTING SERVICES | MEMO FROM CORPORATE SERVICES | 20191204 | 0,00 | 55 000,00 | 0,00 |
| 33222323600PRMRCZZHO | INVENTORY - MATERIALS & SUPPLIES | MEMO FROM CORPORATE SERVICES | 20191204 | 68 740,00 | 0,00 | 55 000,00 |
| 33232265170PRMRCZZHO | OS: PRINTING SERVICES | MEMO FROM CORPORATE SERVICES | 20191204 | 0,00 | 10 000,00 | 0,00 |
| 33232323600PRMRCZZHO | INVENTORY - MATERIALS & SUPPLIES | MEMO FROM CORPORATE SERVICES | 20191204 | 35 570,00 | 0,00 | 10 000,00 |
| 3323232360FPRFLTZZWM | INVENTORY - MATERIALS & SUPPLIES FLEET | MEMO FROM CORPORATE SERVICES | 20191204 | 0,00 | 2 000,00 | 0,00 |
| 33232383600PRMRCZZHO | OPR LEASES: MACHINERY & EQUIPMENT | MEMO FROM CORPORATE SERVICES | 20191204 | 945 000,00 | 0,00 | 2 000,00 |
| 33242265170PRMRCZZHO | OS: PRINTING SERVICES | MEMO FROM CORPORATE SERVICES | 20191204 | 0,00 | 7 370,00 | 0,00 |
| 33242323600PRMRCZZHO | INVENTORY - MATERIALS & SUPPLIES | MEMO FROM CORPORATE SERVICES | 20191204 | 9 370,00 | 0,00 | 7 370,00 |
| 34212265170WSMRCZZHO | OS: PRINTING SERVICES | MEMO FROM SOCIAL SERVICES | 20191204 | 0,00 | 100 000,00 | 0,00 |
| 34212323600FGMRCZZHO | INVENTORY - MATERIALS & SUPPLIES | MEMO FROM SOCIAL SERVICES | 20191204 | 116 330,00 | 0,00 | 100 000,00 |
| 34332265170PRMRCZZHO | OS: PRINTING SERVICES | MEMO FROM SOCIAL SERVICES | 20191204 | 0,00 | 10 000,00 | 0,00 |
| 34332323600PRMRCZZHO | INVENTORY - MATERIALS & SUPPLIES | MEMO FROM SOCIAL SERVICES | 20191204 | 250 440,00 | 0,00 | 10 000,00 |
| 34346456020CFD99ZZWM | FIRE ARMS | MEMO FROM SOCIAL SERVICES | 20191204 | 0,00 | 150 000,00 | 0,00 |
| 34346550420CFF84ZZWM | EQUIPMENT | MEMO FROM SOCIAL SERVICES | 20191204 | 348 000,00 | 0,00 | 150 000,00 |
| 35112265170PRMRCZZHO | OS: PRINTING SERVICES | MEMO FROM SOCIAL SERVICES | 20191204 | 0,00 | 5 000,00 | 0,00 |
| 35112323600CPMRCZZHO | INVENTORY - MATERIALS & SUPPLIES | MEMO FROM SOCIAL SERVICES | 20191204 | 6 620,00 | 0,00 | 5 000,00 |
| 36222283610ELQ62ZZHO | CONTR: MAINTENANCE OF EQUIPMENT | MEMO FROM TECHNICAL SERVICES | 20191213 | 4 000 000,00 | 0,00 | 2 000 000,00 |
| 36222323600ELP29ZZHO | INVENTORY - MATERIALS & SUPPLIES | MEMO FROM TECHNICAL SERVICES | 20191220 | 650 000,00 | 1 900 000,00 | 0,00 |
| 36222323600ELQ62ZZHO | INVENTORY - MATERIALS & SUPPLIES | MEMO FROM TECHNICAL SERVICES | 20191213 | 2 500 000,00 | 2 000 000,00 | 0,00 |
| 36222323600ELQ62ZZHO | INVENTORY - MATERIALS & SUPPLIES | MEMO FROM TECHNICAL SERVICES | 20191220 | 2 500 000,00 | 0,00 | 1 900 000,00 |
| 36352283610WWP70ZZWM | CONTR: MAINTENANCE OF EQUIPMENT | MEMO FROM TECHNICAL SERVICES | 20191220 | 0,00 | 200 000,00 | 0,00 |
| 36352323600WWP70ZZWM | INVENTORY - MATERIALS & SUPPLIES | MEMO FROM TECHNICAL SERVICES | 20191220 | 1 622 020,00 | 0,00 | 200 000,00 |
| 37112265170PRMRCZZHO | OS: PRINTING SERVICES | MEMO FROM FINANCIAL SERVICES | 20191204 | 0,00 | 1 280,00 | 0,00 |
| 37112323600PRMRCZZHO | INVENTORY - MATERIALS & SUPPLIES | MEMO FROM FINANCIAL SERVICES | 20191204 | 1 280,00 | 0,00 | 1 280,00 |
| 37212265170PRMRCZZHO | OS: PRINTING SERVICES | MEMO FROM FINANCIAL SERVICES | 20191204 | 0,00 | 640 000,00 | 0,00 |
| 37212323600PRMRCZZHO | INVENTORY - MATERIALS & SUPPLIES | MEMO FROM FINANCIAL SERVICES | 20191204 | 748 410,00 | 0,00 | 640 000,00 |
|  |  |  |  |  | 5 950 650,00 | 5 950 650,00 |

  - Monthly Budget Statement Financial Performance: Standard Classification

| FS204 Metsimaholo - Table C2 Monthly Budget Statement - Financial Performance (functional classification) - M06 December |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description | Ref | 2018/19 | Budget Year 2019/20 |  |  |  |  |  |  |  |
|  |  | Audited Outcome | Original Budget | Adjusted Budget | Monthly actual | YearTD actual | YearTD budget | YTD variance | YTD variance | Full Year Forecast |
| R thousands | 1 |  |  |  |  |  |  |  | % |  |
| Revenue - Functional |  |  |  |  |  |  |  |  |  |  |
| Governance and administration |  | 141 102 | 141 917 | 141 917 | 50 019 | 119 479 | 70 958 | 48 520 | 68% | 141 917 |
| Executive and council |  | – | – | – | – | – | – | – |  | – |
| Finance and administration |  | 141 102 | 141 917 | 141 917 | 50 019 | 119 479 | 70 958 | 48 520 | 68% | 141 917 |
| Internal audit |  | – | – | – | – | – | – | – |  | – |
| Community and public safety |  | 166 928 | 269 616 | 269 616 | 16 519 | 120 734 | 134 808 | (14 074) | -10% | 269 616 |
| Community and social services |  | 470 | 1 950 | 1 950 | 15 | 230 | 975 | (745) | -76% | 1 950 |
| Sport and recreation |  | 2 170 | 17 795 | 17 795 | 19 | 267 | 8 897 | (8 631) | -97% | 17 795 |
| Public safety |  | 4 761 | 17 010 | 17 010 | 96 | 697 | 8 505 | (7 808) | -92% | 17 010 |
| Housing |  | 159 526 | 232 861 | 232 861 | 16 389 | 119 540 | 116 431 | 3 110 | 3% | 232 861 |
| Economic and environmental services |  | 26 891 | 8 716 | 8 716 | 47 | 409 | 4 358 | (3 949) | -91% | 8 716 |
| Planning and development |  | 3 022 | 3 902 | 3 902 | 47 | 408 | 1 951 | (1 543) | -79% | 3 902 |
| Road transport |  | 23 868 | 4 814 | 4 814 | – | 0 | 2 407 | (2 407) | -100% | 4 814 |
| Trading services |  | 860 019 | 1 068 967 | 1 068 967 | 64 312 | 436 654 | 534 484 | (97 829) | -18% | 1 068 967 |
| Energy sources |  | 311 687 | 322 493 | 322 493 | 23 643 | 151 390 | 161 247 | (9 856) | -6% | 322 493 |
| Water management |  | 405 468 | 528 893 | 528 893 | 33 499 | 243 040 | 264 447 | (21 407) | -8% | 528 893 |
| Waste water management |  | 97 014 | 166 325 | 166 325 | 3 172 | 18 486 | 83 163 | (64 677) | -78% | 166 325 |
| Waste management |  | 45 851 | 51 255 | 51 255 | 3 998 | 23 738 | 25 628 | (1 889) | -7% | 51 255 |
| Other | 4 | – | 105 | 105 | – | – | 53 | (53) | -100% | 105 |
| Total Revenue - Functional | 2 | 1 194 939 | 1 489 321 | 1 489 321 | 130 897 | 677 276 | 744 660 | (67 385) | -9% | 1 489 321 |
| Expenditure - Functional |  |  |  |  |  |  |  |  |  |  |
| Governance and administration |  | 257 135 | 314 752 | 314 546 | 25 639 | 122 071 | 157 277 | (35 206) | -22% | 314 546 |
| Executive and council |  | 50 825 | 56 234 | 56 109 | 4 405 | 24 249 | 28 037 | (3 788) | -14% | 56 109 |
| Finance and administration |  | 203 799 | 255 693 | 255 612 | 20 969 | 96 520 | 127 827 | (31 307) | -24% | 255 612 |
| Internal audit |  | 2 511 | 2 826 | 2 826 | 265 | 1 302 | 1 413 | (111) | -8% | 2 826 |
| Community and public safety |  | 84 934 | 103 749 | 103 750 | 8 949 | 43 442 | 51 876 | (8 434) | -16% | 103 750 |
| Community and social services |  | 4 743 | 6 950 | 6 951 | 540 | 2 678 | 3 476 | (798) | -23% | 6 951 |
| Sport and recreation |  | 32 826 | 38 615 | 38 610 | 4 223 | 17 544 | 19 306 | (1 762) | -9% | 38 610 |
| Public safety |  | 41 992 | 52 510 | 52 515 | 3 723 | 20 363 | 26 257 | (5 894) | -22% | 52 515 |
| Housing |  | 5 373 | 5 674 | 5 674 | 463 | 2 857 | 2 837 | 20 | 1% | 5 674 |
| Economic and environmental services |  | 58 502 | 95 508 | 95 613 | 16 621 | 34 112 | 47 841 | (13 729) | -29% | 95 613 |
| Planning and development |  | 14 723 | 22 623 | 22 828 | 1 326 | 7 784 | 11 412 | (3 628) | -32% | 22 828 |
| Road transport |  | 43 779 | 72 885 | 72 785 | 15 295 | 26 327 | 36 428 | (10 101) | -28% | 72 785 |
| Trading services |  | 763 660 | 792 604 | 792 704 | 73 837 | 371 501 | 396 317 | (24 816) | -6% | 792 704 |
| Energy sources |  | 294 022 | 358 161 | 358 161 | 27 802 | 170 425 | 179 081 | (8 656) | -5% | 358 161 |
| Water management |  | 363 085 | 312 802 | 312 802 | 36 474 | 158 274 | 156 401 | 1 873 | 1% | 312 802 |
| Waste water management |  | 46 269 | 60 065 | 60 165 | 5 586 | 20 169 | 30 047 | (9 878) | -33% | 60 165 |
| Waste management |  | 60 284 | 61 577 | 61 577 | 3 975 | 22 634 | 30 788 | (8 155) | -26% | 61 577 |
| Other |  | 2 009 | 3 775 | 3 775 | 161 | 1 076 | 1 887 | (812) | -43% | 3 775 |
| Total Expenditure - Functional | 3 | 1 166 241 | 1 310 388 | 1 310 388 | 125 207 | 572 201 | 655 197 | (82 996) | -13% | 1 310 388 |
| Surplus/ (Deficit) for the year |  | 28 698 | 178 934 | 178 934 | 5 690 | 105 074 | 89 463 | 15 611 | 17% | 178 934 |

# The statement reflects the operating revenue and expenditure per Directorate for the month as well as the year to date figures for the 2019/2020 financial year

# 5.3 Monthly Budget Statement Financial Performance: Municipal vote

| FS204 Metsimaholo - Table C3 Monthly Budget Statement - Financial Performance (revenue and expenditure by municipal vote) - M06 December |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vote Description | Ref | 2018/19 | Budget Year 2019/20 |  |  |  |  |  |  |  |
|  |  | Audited Outcome | Original Budget | Adjusted Budget | Monthly actual | YearTD actual | YearTD budget | YTD variance | YTD variance | Full Year Forecast |
| R thousands |  |  |  |  |  |  |  |  | % |  |
| Revenue by Vote | 1 |  |  |  |  |  |  |  |  |  |
| Vote 01 - Executive & Council |  | – | – | – | – | – | – | – |  | – |
| Vote 02 - Municipal Manager |  | 2 300 | 3 183 | 3 183 | 4 | 45 | 1 591 | (1 546) | -97,2% | 3 183 |
| Vote 03 - Corporate Services |  | 888 | 1 300 | 1 300 | 9 | 624 | 650 | (26) | -4,0% | 1 300 |
| Vote 04 - Social Services |  | 53 253 | 88 010 | 88 010 | 4 128 | 24 932 | 44 005 | (19 073) | -43,3% | 88 010 |
| Vote 05 - Technical Services |  | 838 036 | 1 022 526 | 1 022 526 | 60 314 | 412 916 | 511 263 | (98 347) | -19,2% | 1 022 526 |
| Vote 06 - Financial Services |  | 293 862 | 362 711 | 362 711 | 65 945 | 235 518 | 181 355 | 54 163 | 29,9% | 362 711 |
| Vote 07 - Local Economic Development And Planning |  | 6 601 | 11 593 | 11 593 | 497 | 3 240 | 5 796 | (2 556) | -44,1% | 11 593 |
| Total Revenue by Vote | 2 | 1 194 939 | 1 489 321 | 1 489 321 | 130 897 | 677 276 | 744 660 | (67 385) | -9,0% | 1 489 321 |
| Expenditure by Vote | 1 |  |  |  |  |  |  |  |  |  |
| Vote 01 - Executive & Council |  | 37 009 | 45 943 | 45 943 | 3 351 | 20 594 | 22 972 | (2 378) | -10,4% | 45 943 |
| Vote 02 - Municipal Manager |  | 62 613 | 74 009 | 74 089 | 8 831 | 26 567 | 37 025 | (10 458) | -28,2% | 74 089 |
| Vote 03 - Corporate Services |  | 35 468 | 50 877 | 50 797 | 3 137 | 18 446 | 25 419 | (6 972) | -27,4% | 50 797 |
| Vote 04 - Social Services |  | 140 289 | 160 871 | 160 871 | 12 493 | 63 303 | 80 437 | (17 133) | -21,3% | 160 871 |
| Vote 05 - Technical Services |  | 760 280 | 821 994 | 821 994 | 86 412 | 381 894 | 410 998 | (29 104) | -7,1% | 821 994 |
| Vote 06 - Financial Services |  | 107 122 | 120 909 | 120 909 | 8 240 | 49 454 | 60 455 | (11 001) | -18,2% | 120 909 |
| Vote 07 - Local Economic Development And Planning |  | 23 460 | 35 784 | 35 784 | 2 742 | 11 944 | 17 892 | (5 948) | -33,2% | 35 784 |
| Total Expenditure by Vote | 2 | 1 166 241 | 1 310 388 | 1 310 388 | 125 207 | 572 201 | 655 197 | (82 996) | -12,7% | 1 310 388 |
| Surplus/ (Deficit) for the year | 2 | 28 698 | 178 934 | 178 934 | 5 690 | 105 074 | 89 463 | 15 611 | 17,4% | 178 934 |

# 5.4 Monthly Budget Statement – Financial Performance (Revenue and expenditure)

| FS204 Metsimaholo - Table C4 Monthly Budget Statement - Financial Performance (revenue and expenditure) - M06 December |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description | Ref | 2018/19 | Budget Year 2019/20 |  |  |  |  |  |  |  |
|  |  | Audited Outcome | Original Budget | Adjusted Budget | Monthly actual | YearTD actual | YearTD budget | YTD variance | YTD variance | Full Year Forecast |
| R thousands |  |  |  |  |  |  |  |  | % |  |
| Revenue By Source |  |  |  |  |  |  |  |  |  |  |
| Property rates |  | 143 648 | 215 204 | 215 204 | 14 792 | 110 258 | 107 602 | 2 656 | 2% | 215 204 |
| Service charges - electricity revenue |  | 272 953 | 293 928 | 293 928 | 22 860 | 147 102 | 146 964 | 138 | 0% | 293 928 |
| Service charges - water revenue |  | 365 987 | 478 442 | 478 442 | 30 007 | 224 918 | 239 221 | (14 303) | -6% | 478 442 |
| Service charges - sanitation revenue |  | 27 518 | 29 892 | 29 892 | 2 451 | 14 794 | 14 946 | (152) | -1% | 29 892 |
| Service charges - refuse revenue |  | 32 024 | 28 836 | 28 836 | 2 732 | 16 998 | 14 418 | 2 580 | 18% | 28 836 |
| Rental of facilities and equipment |  | 5 852 | 6 567 | 6 567 | 446 | 2 754 | 3 283 | (529) | -16% | 6 567 |
| Interest earned - external investments |  | 3 784 | 1 500 | 1 500 | 109 | 1 176 | 750 | 426 | 57% | 1 500 |
| Interest earned - outstanding debtors |  | 37 327 | 36 270 | 36 270 | 4 384 | 23 618 | 18 135 | 5 483 | 30% | 36 270 |
| Dividends received |  | 115 | – | – | – | – | – | – |  | – |
| Fines, penalties and forfeits |  | 4 055 | 16 920 | 16 920 | 98 | 454 | 8 460 | (8 006) | -95% | 16 920 |
| Licences and permits |  | 106 | 211 | 211 | – | – | 105 | (105) | -100% | 211 |
| Agency services |  |  |  |  |  |  |  | – |  |  |
| Transfers and subsidies |  | 168 246 | 189 039 | 189 039 | 52 660 | 131 462 | 94 519 | 36 943 | 39% | 189 039 |
| Other revenue |  | 7 204 | 15 243 | 15 243 | 358 | 3 741 | 7 622 | (3 881) | -51% | 15 243 |
| Gains on disposal of PPE |  | – | – | – | – | – | – | – |  | – |
| Total Revenue (excluding capital transfers and contributions) |  | 1 068 819 | 1 312 052 | 1 312 052 | 130 897 | 677 276 | 656 026 | 21 250 | 3% | 1 312 052 |
| Expenditure By Type |  |  |  |  |  |  |  |  |  |  |
| Employee related costs |  | 288 618 | 359 390 | 358 299 | 25 284 | 151 995 | 179 131 | (27 137) | -15% | 358 299 |
| Remuneration of councillors |  | 17 554 | 19 855 | 19 855 | 1 559 | 9 353 | 9 928 | (575) | -6% | 19 855 |
| Debt impairment |  | 234 586 | 152 751 | 152 751 | 12 729 | 76 375 | 76 376 | (0) | 0% | 152 751 |
| Depreciation & asset impairment |  | 72 118 | 83 085 | 83 085 | 38 806 | 38 806 | 41 543 | (2 737) | -7% | 83 085 |
| Finance charges |  | 8 063 | 6 448 | 6 448 | 199 | 615 | 3 224 | (2 609) | -81% | 6 448 |
| Bulk purchases |  | 397 280 | 479 007 | 479 007 | 34 474 | 238 889 | 239 503 | (614) | 0% | 479 007 |
| Other materials |  | 17 039 | 32 941 | 33 398 | 2 135 | 7 924 | 16 498 | (8 574) | -52% | 33 398 |
| Contracted services |  | 82 250 | 110 421 | 111 749 | 7 826 | 31 280 | 55 936 | (24 656) | -44% | 111 749 |
| Transfers and subsidies |  | 297 | 42 | 42 | – | 44 | 21 | 23 | 108% | 42 |
| Other expenditure |  | 49 950 | 66 448 | 65 754 | 2 195 | 16 921 | 33 038 | (16 116) | -49% | 65 754 |
| Loss on disposal of PPE |  | (1 514) | – | – | – | – | – | – |  | – |
| Total Expenditure |  | 1 166 241 | 1 310 388 | 1 310 388 | 125 207 | 572 201 | 655 197 | (82 996) | -13% | 1 310 388 |
| Surplus/(Deficit) |  | (97 422) | 1 665 | 1 665 | 5 690 | 105 074 | 828 | 104 246 | 0 | 1 665 |
| Transfers and subsidies - capital (monetary allocations) (National / Provincial and District) |  | 60 980 | 81 069 | 81 069 | – | – | 40 535 | (40 535) | (0) | 81 069 |
| Transfers and subsidies - capital (monetary allocations) (National / Provincial Departmental Agencies, Households, Non-profit Institutions, Private Enterprises, Public Corporatons, Higher Educational Institutions) |  | 1 611 | – | – | – | – | – | – |  | – |
| Transfers and subsidies - capital (in-kind - all) |  | 63 529 | 96 200 | 96 200 | – | – | 48 100 | (48 100) | (0) | 96 200 |
| Surplus/(Deficit) after capital transfers & contributions |  | 28 698 | 178 934 | 178 934 | 5 690 | 105 074 | 89 463 |  |  | 178 934 |
| Taxation |  |  |  |  |  |  |  | – |  |  |
| Surplus/(Deficit) after taxation |  | 28 698 | 178 934 | 178 934 | 5 690 | 105 074 | 89 463 |  |  | 178 934 |
| Attributable to minorities |  |  |  |  |  |  |  |  |  |  |
| Surplus/(Deficit) attributable to municipality |  | 28 698 | 178 934 | 178 934 | 5 690 | 105 074 | 89 463 |  |  | 178 934 |
| Share of surplus/ (deficit) of associate |  |  |  |  |  |  |  |  |  |  |
| Surplus/ (Deficit) for the year |  | 28 698 | 178 934 | 178 934 | 5 690 | 105 074 | 89 463 |  |  | 178 934 |

5.5 Monthly Budget Statement - Capital Expenditure: (municipal vote, standard classification and funding)

| FS204 Metsimaholo - Table C5 Monthly Budget Statement - Capital Expenditure (municipal vote, functional classification and funding) - M06 December |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vote Description | Ref | 2018/19 | Budget Year 2019/20 |  |  |  |  |  |  |  |
|  |  | Audited Outcome | Original Budget | Adjusted Budget | Monthly actual | YearTD actual | YearTD budget | YTD variance | YTD variance | Full Year Forecast |
| R thousands | 1 |  |  |  |  |  |  |  | % |  |
| Multi-Year expenditure appropriation | 2 |  |  |  |  |  |  |  |  |  |
| Vote 01 - Executive & Council |  | – | – | – | – | – | – | – |  | – |
| Vote 02 - Municipal Manager |  | 526 | 2 980 | 2 980 | – | 75 | 1 490 | (1 415) | -95% | 2 980 |
| Vote 03 - Corporate Services |  | – | 5 600 | 5 600 | 3 | 3 | 2 800 | (2 797) | -100% | 5 600 |
| Vote 04 - Social Services |  | 168 | 1 504 | 1 654 | – | – | 790 | (790) | -100% | 1 654 |
| Vote 05 - Technical Services |  | 79 753 | 167 510 | 170 295 | 8 055 | 20 071 | 84 882 | (64 811) | -76% | 170 295 |
| Vote 06 - Financial Services |  | – | – | – | – | – | – | – |  | – |
| Vote 07 - Local Economic Development And Planning |  | – | 1 000 | 1 000 | – | – | 500 | (500) | -100% | 1 000 |
| Total Capital Multi-year expenditure | 4,7 | 80 447 | 178 594 | 181 529 | 8 059 | 20 148 | 90 461 | (70 313) | -78% | 181 529 |
| Single Year expenditure appropriation | 2 |  |  |  |  |  |  |  |  |  |
| Vote 01 - Executive & Council |  | – | 80 | 80 | – | – | 40 | (40) | -100% | 80 |
| Vote 02 - Municipal Manager |  | 28 | 1 735 | 1 735 | – | 332 | 868 | (535) | -62% | 1 735 |
| Vote 03 - Corporate Services |  | 104 | 653 | 653 | – | 8 | 326 | (318) | -98% | 653 |
| Vote 04 - Social Services |  | 7 324 | 34 632 | 34 482 | 1 264 | 1 264 | 17 278 | (16 014) | -93% | 34 482 |
| Vote 05 - Technical Services |  | 29 219 | 77 777 | 74 992 | 680 | 6 811 | 37 762 | (30 951) | -82% | 74 992 |
| Vote 06 - Financial Services |  | 156 | 747 | 747 | – | 13 | 374 | (361) | -97% | 747 |
| Vote 07 - Local Economic Development And Planning |  | 60 | 300 | 300 | – | – | 150 | (150) | -100% | 300 |
| Total Capital single-year expenditure | 4 | 36 892 | 115 923 | 112 988 | 1 945 | 8 428 | 56 797 | (48 370) | -85% | 112 988 |
| Total Capital Expenditure |  | 117 339 | 294 517 | 294 517 | 10 003 | 28 576 | 147 259 | (118 683) | -81% | 294 517 |
| Capital Expenditure - Functional Classification |  |  |  |  |  |  |  |  |  |  |
| Governance and administration |  | 908 | 14 141 | 14 141 | 3 | 628 | 7 070 | (6 442) | -91% | 14 141 |
| Executive and council |  | – | 80 | 80 | – | – | 40 | (40) | -100% | 80 |
| Finance and administration |  | 908 | 14 061 | 14 061 | 3 | 628 | 7 030 | (6 402) | -91% | 14 061 |
| Internal audit |  |  |  |  |  |  |  | – |  |  |
| Community and public safety |  | 2 451 | 30 186 | 30 186 | 1 264 | 1 264 | 15 093 | (13 828) | -92% | 30 186 |
| Community and social services |  | 6 | 2 281 | 2 281 | – | – | 1 140 | (1 140) | -100% | 2 281 |
| Sport and recreation |  | 832 | 20 953 | 20 953 | 1 264 | 1 264 | 10 477 | (9 212) | -88% | 20 953 |
| Public safety |  | 1 613 | 6 951 | 6 951 | – | – | 3 476 | (3 476) | -100% | 6 951 |
| Housing |  |  |  |  |  |  |  | – |  |  |
| Health |  |  |  |  |  |  |  | – |  |  |
| Economic and environmental services |  | 23 450 | 49 468 | 49 468 | – | 1 503 | 24 734 | (23 231) | -94% | 49 468 |
| Planning and development |  | 60 | 1 200 | 1 200 | – | – | 600 | (600) | -100% | 1 200 |
| Road transport |  | 23 390 | 48 268 | 48 268 | – | 1 503 | 24 134 | (22 631) | -94% | 48 268 |
| Environmental protection |  |  |  |  |  |  |  | – |  |  |
| Trading services |  | 90 530 | 200 723 | 200 723 | 8 736 | 25 180 | 100 362 | (75 182) | -75% | 200 723 |
| Energy sources |  | 21 218 | 37 269 | 37 269 | 2 975 | 3 647 | 18 634 | (14 987) | -80% | 37 269 |
| Water management |  | 8 696 | 23 784 | 23 734 | 332 | 4 680 | 11 885 | (7 205) | -61% | 23 734 |
| Waste water management |  | 55 575 | 133 720 | 133 770 | 5 428 | 16 853 | 66 867 | (50 014) | -75% | 133 770 |
| Waste management |  | 5 041 | 5 950 | 5 950 | – | – | 2 975 | (2 975) | -100% | 5 950 |
| Other |  |  |  |  |  |  |  | – |  |  |
| Total Capital Expenditure - Functional Classification | 3 | 117 339 | 294 517 | 294 517 | 10 003 | 28 576 | 147 259 | (118 683) | -81% | 294 517 |
| Funded by: |  |  |  |  |  |  |  |  |  |  |
| National Government |  | 87 466 | 151 069 | 151 069 | 9 652 | 25 670 | 75 535 | (49 865) | -66% | 151 069 |
| Provincial Government |  | – | – | – | – | – | – | – |  | – |
| District Municipality |  |  |  |  |  |  |  | – |  |  |
| Other transfers and grants |  | 25 690 | 26 200 | 26 200 | – | – | 13 100 | (13 100) | -100% | 26 200 |
| Transfers recognised - capital |  | 113 156 | 177 269 | 177 269 | 9 652 | 25 670 | 88 635 | (62 965) | -71% | 177 269 |
| Borrowing | 6 | – | 55 972 | 55 972 | – | – | 27 986 | (27 986) | -100% | 55 972 |
| Internally generated funds |  | 4 183 | 61 275 | 61 275 | 351 | 2 906 | 30 638 | (27 732) | -91% | 61 275 |
| Total Capital Funding |  | 117 339 | 294 517 | 294 517 | 10 003 | 28 576 | 147 259 | (118 683) | -81% | 294 517 |

  - Monthly Budget Statement – Financial Position

| FS204 Metsimaholo - Table C6 Monthly Budget Statement - Financial Position - M06 December |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Description | Ref | 2018/19 | Budget Year 2019/20 |  |  |  |
|  |  | Audited Outcome | Original Budget | Adjusted Budget | YearTD actual | Full Year Forecast |
| R thousands | 1 |  |  |  |  |  |
| ASSETS |  |  |  |  |  |  |
| Current assets |  |  |  |  |  |  |
| Cash |  | 8 851 | 26 465 | 26 465 | (25 230) | 26 465 |
| Call investment deposits |  | 8 667 | 7 715 | 7 715 | 597 536 | 7 715 |
| Consumer debtors |  | 192 945 | 274 599 | 274 599 | 325 646 | 274 599 |
| Other debtors |  | 626 514 | 16 968 | 16 968 | 665 861 | 16 968 |
| Current portion of long-term receivables |  | – | – | – | – | – |
| Inventory |  | 1 467 | 18 676 | 18 676 | 1 376 | 18 676 |
| Total current assets |  | 838 444 | 344 423 | 344 423 | 1 565 190 | 344 423 |
| Non-current assets |  |  |  |  |  |  |
| Long-term receivables |  | – | – | – | – | – |
| Investments |  | – | – | – | – | – |
| Investment property |  | 445 937 | 86 659 | 86 659 | 445 400 | 86 659 |
| Investments in Associate |  |  |  |  |  |  |
| Property, plant and equipment |  | 1 233 970 | 1 533 977 | 1 533 977 | 1 225 197 | 1 533 977 |
| Biological |  |  |  |  |  |  |
| Intangible |  | 4 189 | 4 588 | 4 588 | 3 269 | 4 588 |
| Other non-current assets |  | 4 294 | 561 | 561 | 4 294 | 561 |
| Total non-current assets |  | 1 688 390 | 1 625 784 | 1 625 784 | 1 678 161 | 1 625 784 |
| TOTAL ASSETS |  | 2 526 834 | 1 970 207 | 1 970 207 | 3 243 350 | 1 970 207 |
| LIABILITIES |  |  |  |  |  |  |
| Current liabilities |  |  |  |  |  |  |
| Bank overdraft |  | – | – | – | – | – |
| Borrowing |  | 4 983 | 4 364 | 4 364 | 2 257 | 4 364 |
| Consumer deposits |  | 24 101 | 26 294 | 26 294 | 25 204 | 26 294 |
| Trade and other payables |  | 825 591 | 170 246 | 170 246 | 1 442 036 | 170 246 |
| Provisions |  | 129 901 | 84 208 | 84 208 | 129 901 | 84 208 |
| Total current liabilities |  | 984 576 | 285 112 | 285 112 | 1 599 398 | 285 112 |
| Non-current liabilities |  |  |  |  |  |  |
| Borrowing |  | 3 828 | 59 570 | 59 570 | 3 828 | 59 570 |
| Provisions |  | – | – | – | – | – |
| Total non-current liabilities |  | 3 828 | 59 570 | 59 570 | 3 828 | 59 570 |
| TOTAL LIABILITIES |  | 988 404 | 344 682 | 344 682 | 1 603 226 | 344 682 |
| NET ASSETS | 2 | 1 538 431 | 1 625 525 | 1 625 525 | 1 640 124 | 1 625 525 |
| COMMUNITY WEALTH/EQUITY |  |  |  |  |  |  |
| Accumulated Surplus/(Deficit) |  | 1 606 741 | 1 625 525 | 1 625 525 | 1 640 124 | 1 625 525 |
| Reserves |  | – | – | – | – | – |
| TOTAL COMMUNITY WEALTH/EQUITY | 2 | 1 606 741 | 1 625 525 | 1 625 525 | 1 640 124 | 1 625 525 |

# The year to date does not take into account the opening balances, but only reflects the net movement for the month/period.

  - Monthly Budget Statement – Cash Flow

| FS204 Metsimaholo - Table C7 Monthly Budget Statement - Cash Flow - M06 December |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description | Ref | 2018/19 | Budget Year 2019/20 |  |  |  |  |  |  |  |
|  |  | Audited Outcome | Original Budget | Adjusted Budget | Monthly actual | YearTD actual | YearTD budget | YTD variance | YTD variance | Full Year Forecast |
| R thousands | 1 |  |  |  |  |  |  |  | % |  |
| CASH FLOW FROM OPERATING ACTIVITIES |  |  |  |  |  |  |  |  |  |  |
| Receipts |  |  |  |  |  |  |  |  |  |  |
| Property rates |  | 100 875 | 124 373 | 124 373 | 9 634 | 75 500 | 62 187 | 13 313 | 21% | 124 373 |
| Service charges |  | 479 389 | 667 215 | 667 215 | 39 422 | 303 568 | 333 608 | (30 039) | -9% | 667 215 |
| Other revenue |  | 20 637 | 22 181 | 22 181 | 7 936 | 103 418 | 11 091 | 92 328 | 832% | 22 181 |
| Government - operating |  | 150 551 | 186 715 | 186 715 | 52 660 | 131 462 | 93 358 | 38 105 | 41% | 186 715 |
| Government - capital |  | 94 002 | – | – | 12 585 | 41 078 | – | 41 078 | #DIV/0! | – |
| Interest |  | 36 490 | 28 326 | 28 326 | 437 | 3 151 | 14 163 | (11 012) | -78% | 28 326 |
| Dividends |  | 107 | – | – | – | – | – | – |  | – |
| Payments |  |  |  |  |  |  |  |  |  |  |
| Suppliers and employees |  | (780 232) | (943 431) | (943 431) | (99 654) | (592 911) | (471 716) | 121 196 | -26% | (943 431) |
| Finance charges |  | (4 024) | (2 130) | (2 130) | (199) | (615) | (1 065) | (450) | 42% | (2 130) |
| Transfers and Grants |  | (9) | – | – | – | – | – | – |  | – |
| NET CASH FROM/(USED) OPERATING ACTIVITIES |  | 97 785 | 83 249 | 83 249 | 22 822 | 64 652 | 41 625 | (23 027) | -55% | 83 249 |
| CASH FLOWS FROM INVESTING ACTIVITIES |  |  |  |  |  |  |  |  |  |  |
| Receipts |  |  |  |  |  |  |  |  |  |  |
| Proceeds on disposal of PPE |  | – | – | – | – | – | – | – |  | – |
| Decrease (Increase) in non-current debtors |  | – | 300 | 300 | (1 705) | (52 904) | 150 | (53 054) | -35369% | 300 |
| Decrease (increase) other non-current receivables |  | – | – | – | – | – | – | – |  | – |
| Decrease (increase) in non-current investments |  |  |  |  |  |  |  | – |  |  |
| Payments |  |  |  |  |  |  |  |  |  |  |
| Capital assets |  | (86 656) | (134 537) | (134 537) | 10 003 | (10 003) | (67 269) | (57 265) | 85% | (134 537) |
| NET CASH FROM/(USED) INVESTING ACTIVITIES |  | (86 656) | (134 237) | (134 237) | 8 298 | (62 907) | (67 119) | (4 211) | 6% | (134 237) |
| CASH FLOWS FROM FINANCING ACTIVITIES |  |  |  |  |  |  |  |  |  |  |
| Receipts |  |  |  |  |  |  |  |  |  |  |
| Short term loans |  | – | – | – | – | – | – | – |  | – |
| Borrowing long term/refinancing |  | – | – | – | – | – | – | – |  | – |
| Increase (decrease) in consumer deposits |  | – | – | – | 142 | 1 103 | – | 1 103 | #DIV/0! | – |
| Payments |  |  |  |  |  |  |  |  |  |  |
| Repayment of borrowing |  | (3 312) | (5 924) | (5 924) | 1 352 | (1 352) | (2 962) | (1 610) | 54% | (5 924) |
| NET CASH FROM/(USED) FINANCING ACTIVITIES |  | (3 312) | (5 924) | (5 924) | 1 494 | (248) | (2 962) | (2 714) | 92% | (5 924) |
| NET INCREASE/ (DECREASE) IN CASH HELD |  | 7 817 | (56 912) | (56 912) | 32 614 | 1 496 | (28 456) |  |  | (56 912) |
| Cash/cash equivalents at beginning: |  | 12 628 | 4 696 | 4 696 |  | 35 419 |  |  |  |  |
| Cash/cash equivalents at month/year end: |  | 20 444 | (52 216) | (52 216) |  | 36 915 | (28 456) |  |  | (56 912) |

# Supporting Documentation

- Debtors’ analysis

| FS204 Metsimaholo - Supporting Table SC3 Monthly Budget Statement - aged debtors –M06 December |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description |  | Budget Year 2019/20 |  |  |  |  |  |  |  |  |  |  |  |  |
| R thousands | NT Code | 0-30 Days | 31-60 Days | 61-90 Days | 91-120 Days | 121-150 Dys | 151-180 Dys | 181 Dys-1 Yr | Over 1Yr | Total | Total over 90 days | Actual Bad Debts Written Off against Debtors | Impairment - Bad Debts i.t.o Council Policy |  |
| Debtors Age Analysis By Income Source |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Trade and Other Receivables from Exchange Transactions - Water | 1200 | 39,555 | 40,100 | 26,681 | 56,161 | 25,977 | 15,660 | 124,559 | 683,562 | 1,012,255 | 905,919 | 1,131 | 40,682 |  |
| Trade and Other Receivables from Exchange Transactions - Electricity | 1300 | 11,287 | 10,671 | 2,496 | 1,927 | 1,989 | 2,003 | 10,050 | 47,137 | 87,560 | 63,106 | 91 | 8,574 |  |
| Receivables from Non-exchange Transactions - Property Rates | 1400 | 13,759 | 10,907 | 5,605 | 5,083 | 3,469 | 8,650 | 12,282 | 79,556 | 139,311 | 109,040 | 304 | 20,457 |  |
| Receivables from Exchange Transactions - Waste Water Management | 1500 | 2,584 | 1,910 | 1,212 | 1,078 | 1,029 | 1,008 | 5,141 | 36,187 | 50,149 | 44,444 | 41 | 2,121 |  |
| Receivables from Exchange Transactions - Waste Management | 1600 | 2,976 | 2,293 | 1,607 | 1,426 | 1,369 | 1,336 | 6,943 | 54,126 | 72,075 | 65,200 | 51 | 2,542 |  |
| Receivables from Exchange Transactions - Property Rental Debtors | 1700 | – | – | – | – | – | – | – | – | – | – | – | – |  |
| Interest on Arrear Debtor Accounts | 1810 | 4,383 | 4,245 | 3,865 | 3,645 | 3,560 | 3,594 | 19,938 | 154,034 | 197,264 | 184,770 | – | – |  |
| Other | 1900 | 2,295 | 2,149 | 2,074 | 2,226 | 6,740 | 686 | 6,761 | 85,104 | 108,034 | 101,517 | – | – |  |
| Total By Income Source | 2000 | 76,840 | 72,275 | 43,540 | 71,546 | 44,133 | 32,937 | 185,674 | 1,139,705 | 1,666,649 | 1,473,995 | 1,619 | 74,375 |  |
| 2018/19 - totals only |  |  |  |  |  |  |  |  |  | – | – |  |  |  |
| Debtors Age Analysis By Customer Group |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Organs of State | 2200 | 3,676 | 5,285 | 1,194 | 2,006 | 1,181 | 534 | 4,583 | 18,425 | 36,884 | 26,729 | – | – |  |
| Commercial | 2300 | 31,250 | 23,058 | 5,949 | 37,540 | 3,944 | 5,762 | 19,511 | 72,393 | 199,407 | 139,149 | – | – |  |
| Households | 2400 | 41,913 | 43,932 | 36,397 | 32,000 | 39,008 | 26,641 | 161,580 | 1,048,887 | 1,430,358 | 1,308,116 | 1,619 | 74,375 |  |
| Other | 2500 | – | – | – | – | – | – | – | – | – | – | – | – |  |
| Total By Customer Group | 2600 | 76,840 | 72,275 | 43,540 | 71,546 | 44,133 | 32,937 | 185,674 | 1,139,705 | 1,666,649 | 1,473,995 | 1,619 | 74,375 |  |

No Consumer debts were written off in terms of the Credit Control and Debt Collection Policy during December 2019

- Creditors’ analysis

| FS204 Metsimaholo - Supporting Table SC4 Monthly Budget Statement - aged creditors - Mid-year M06 December |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description | NT Code | Budget Year 2019/20 |  |  |  |  |  |  |  |  |
|  |  | 0 - 30 Days | 31 - 60 Days | 61 - 90 Days | 91 - 120 Days | 121 - 150 Days | 151 - 180 Days | 181 Days - 1 Year | Over 1 Year | Total |
| R thousands |  |  |  |  |  |  |  |  |  |  |
| Creditors Age Analysis By Customer Type |  |  |  |  |  |  |  |  |  |  |
| Bulk Electricity | 0100 | 20,851 | – | – | – | – | – | – | – | 20,851 |
| Bulk Water | 0200 | 16,676 | 920 | 1,134 | 995 | 38,575 | – | – | – | 58,300 |
| PAYE deductions | 0300 | – | – | – | – | – | – | – | – | – |
| VAT (output less input) | 0400 | – | – | – | – | – | – | – | – | – |
| Pensions / Retirement deductions | 0500 | – | – | – | – | – | – | – | – | – |
| Loan repayments | 0600 | – | – | – | – | – | – | – | – | – |
| Trade Creditors | 0700 | 3,588 | 1,844 | 566 | 329 | 58,495 | – | – | – | 64,821 |
| Auditor General | 0800 | 1,000 | 2,053 | 976 | – | – | – | – | – | 4,029 |
| Other | 0900 | – | – | – | – | – | – | – | – | – |
| Total By Customer Type | 1000 | 42,114 | 4,817 | 2,676 | 1,323 | 97,070 | – | – | – | 148,000 |

Trade creditors include outstanding orders, as a commitment is already made.

The amount becomes payable when the work is completed or when the service is delivered.

- Investment portfolio analyses

FS204 Metsimaholo - Supporting Table SC5 Monthly Budget Statement - investment portfolio –M06 December 2019

| Investments by maturity Name of institution & investment ID | Ref | Period of Investment | Type of Investment | Capital Guarantee (Yes/ No) | Variable or Fixed interest rate | Opening balance | Interest to be realised | Partial / Premature Withdrawal (4) | Investment Top Up | Closing Balance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R thousands |  | Yrs/Months |  |  |  |  |  |  |  |  |
| Municipality |  |  |  |  |  |  |  |  |  |  |
| ABSA BANK |  |  | Call |  | 6.30% | 955 |  | – | – | 955 |
| NEDBANK |  |  | Call |  | 6.25% | 1,461 |  | (10,000) | 10,000 | 1,461 |
| FNB |  |  | Call |  | 6.10% | 375 |  | – | 36 | 411 |
| STANDARD BANK |  |  | Call |  | 6.30% | 412 |  | (62,000) | 71,245 | 9,657 |
| INVESTEC |  |  | Call |  | 6.35% | 165 |  | – | 5,000 | 5,165 |
| FIXED |  |  | 32 days |  | 7.20% | 20,055 |  | – | 15,000 | 35,055 |
| TOTAL INVESTMENTS AND INTEREST | 2 |  |  |  |  | 23,423 |  | – | – | 52,704 |

# 9.Allocation and grant receipts and expenditure

| FS204 Metsimaholo - Supporting Table SC6 Monthly Budget Statement - transfers and grant receipts - M06 December |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description |  | Ref |  | 2018/19 |  | Budget Year 2019/20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Audited Outcome |  | Original Budget |  | Adjusted Budget |  | Monthly actual |  | YearTD actual |  | YearTD budget |  | YTD variance |  | YTD variance |  | Full Year Forecast |  |
| R thousands |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | % |  |  |  |
| RECEIPTS: |  | 1,2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Operating Transfers and Grants |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| National Government: |  |  |  | 171 101 |  | 192 431 |  | 192 431 |  | 52 660 |  | 131 462 |  | 131 462 |  | – |  | 0,0% |  | 192 431 |  |
| Equitable Share |  |  |  | 163 296 |  | 183 064 |  | 183 064 |  | 52 660 |  | 128 937 |  | 128 937 |  | – |  | 0,0% |  | 183 064 |  |
| Expanded Public Works Programme Integrated Grant |  |  |  | 2 170 |  | 2 314 |  | 2 314 |  | – |  | 290 |  | 290 |  | – |  | 0,0% |  | 2 314 |  |
| Local Government Financial Management Grant |  |  |  | 3 540 |  | 4 470 |  | 4 470 |  | – |  | 2 235 |  | 2 235 |  | – |  | 0,0% |  | 4 470 |  |
| Municipal Infrastructure Grant |  |  |  | 2 095 |  | 2 583 |  | 2 583 |  | – |  | – |  | – |  | – |  |  |  | 2 583 |  |
| Municipal Systems Improvement Grant |  |  |  | – |  | – |  | – |  | – |  | – |  | – |  | – |  |  |  | – |  |
| Operation Clean Audit |  | 3 |  | – |  | – |  | – |  | – |  | – |  | – |  | – |  |  |  | – |  |
| Other transfers and grants [insert description] |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | – |  |  |  |  |  |
| Provincial Government: |  |  |  | – |  | – |  | – |  | – |  | – |  | – |  | – |  |  |  | – |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | – |  |  |  |  |  |
| Other transfers and grants [insert description] |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | – |  |  |  |  |  |
| District Municipality: |  |  |  | – |  | – |  | – |  | – |  | – |  | – |  | – |  |  |  | – |  |
| [insert description] |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | – |  |  |  |  |  |
| Other grant providers: |  |  |  | – |  | – |  | – |  | – |  | – |  | – |  | – |  |  |  | – |  |
| Auditor-General |  |  |  | – |  | – |  | – |  | – |  | – |  | – |  | – |  |  |  | – |  |
| Government Motor Transport |  |  |  | – |  | – |  | – |  | – |  | – |  | – |  | – |  |  |  | – |  |
| Unspecified |  |  |  | – |  | – |  | – |  | – |  | – |  | – |  | – |  |  |  | – |  |
| Total Operating Transfers and Grants |  | 5 |  | 171 101 |  | 192 431 |  | 192 431 |  | 52 660 |  | 131 462 |  | 131 462 |  | – |  |  |  | 192 431 |  |
| Capital Transfers and Grants |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| National Government: |  |  |  | 60 980 |  | 74 069 |  | 74 069 |  | 12 585 |  | 53 748 |  | 53 748 |  | – |  | 0,0% |  | 74 069 |  |
| Integrated National Electrification Programme |  |  |  | – |  | – |  | – |  | – |  | – |  | – |  | – |  |  |  | – |  |
| Integrated National Electrification Programme Grant |  |  |  | 3 289 |  | 10 000 |  | 10 000 |  | – |  | 3 000 |  | 3 000 |  | – |  | 0,0% |  | 10 000 |  |
| Municipal Infrastructure Grant |  |  |  | 47 691 |  | 49 069 |  | 49 069 |  | 12 585 |  | 33 246 |  | 33 246 |  | – |  | 0,0% |  | 49 069 |  |
| Municipal Water Infrastructure Grant |  |  |  | – |  | – |  | – |  | – |  | – |  | – |  | – |  |  |  | – |  |
| Regional Bulk Infrastructure Grant |  |  |  | – |  | – |  | – |  | – |  | 4 952 |  | 4 952 |  | – |  | 0,0% |  | – |  |
| Water Services Infrastructure Grant |  |  |  | 10 000 |  | 15 000 |  | 15 000 |  | – |  | 12 550 |  | 12 550 |  | – |  | 0,0% |  | 15 000 |  |
| Provincial Government: |  |  |  | – |  | 33 200 |  | 33 200 |  | – |  | – |  | – |  | – |  |  |  | 33 200 |  |
| Specify (Add grant description) |  |  |  | – |  | 33 200 |  | 33 200 |  | – |  | – |  | – |  | – |  |  |  | 33 200 |  |
| Sports and Recreation |  |  |  | – |  | – |  | – |  | – |  | – |  | – |  | – |  |  |  | – |  |
| District Municipality: |  |  |  | – |  | – |  | – |  | – |  | – |  | – |  | – |  |  |  | – |  |
| [insert description] |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | – |  |  |  |  |  |
| Other grant providers: |  |  |  | 65 141 |  | 70 000 |  | 70 000 |  | – |  | – |  | – |  | – |  |  |  | 70 000 |  |
| Government Motor Transport |  |  |  | 1 611 |  | – |  | – |  | – |  | – |  | – |  | – |  |  |  | – |  |
| Production |  |  |  | 39 450 |  | 70 000 |  | 70 000 |  | – |  | – |  | – |  | – |  |  |  | 70 000 |  |
| Unspecified |  |  |  | 24 079 |  | – |  | – |  | – |  | – |  | – |  | – |  |  |  | – |  |
| Total Capital Transfers and Grants |  | 5 |  | 126 120 |  | 177 269 |  | 177 269 |  | 12 585 |  | 53 748 |  | 53 748 |  | – |  |  |  | 177 269 |  |
| TOTAL RECEIPTS OF TRANSFERS & GRANTS |  | 5 |  | 297 221 |  | 369 700 |  | 369 700 |  | 65 245 |  | 185 210 |  | 185 210 |  | – |  |  |  | 369 700 |  |
| FS204 Metsimaholo - Supporting Table SC7(1) Monthly Budget Statement - transfers and grant expenditure - M06 December |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Description |  | Ref |  | 2018/19 |  | Budget Year 2019/20 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Audited Outcome |  | Original Budget |  | Adjusted Budget |  | Monthly actual |  | YearTD actual |  | YearTD budget |  | YTD variance |  | YTD variance |  | Full Year Forecast |  |  |
| R thousands |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | % |  |  |  |  |
| EXPENDITURE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Operating expenditure of Transfers and Grants |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| National Government: |  |  |  | 20 445 |  | 28 368 |  | 25 373 |  | 6 175 |  | 38 911 |  | 38 911 |  | – |  |  |  | 25 373 |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | – |  |  |  |  |  |  |
| Department of Environmental Affairs |  |  |  | – |  | – |  | – |  | – |  | – |  | – |  | – |  |  |  | – |  |  |
| Equitable Share |  |  |  | 16 907 |  | 19 156 |  | 19 156 |  | 5 845 |  | 36 590 |  | 36 590 |  | – |  |  |  | 19 156 |  |  |
| Expanded Public Works Programme Integrated Grant |  |  |  | – |  | – |  | – |  | 127 |  | 669 |  | 669 |  | – |  |  |  | – |  |  |
| Local Government Financial Management Grant |  |  |  | 1 339 |  | 6 470 |  | 3 470 |  | 43 |  | 593 |  | 593 |  | – |  |  |  | 3 470 |  |  |
| Municipal Infrastructure Grant |  |  |  | 2 199 |  | 2 741 |  | 2 746 |  | 159 |  | 1 059 |  | 1 059 |  | – |  |  |  | 2 746 |  |  |
| Provincial Government: |  |  |  | – |  | – |  | – |  | – |  | – |  | – |  | – |  |  |  | – |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | – |  |  |  |  |  |  |
| District Municipality: |  |  |  | – |  | – |  | – |  | – |  | – |  | – |  | – |  |  |  | – |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | – |  |  |  |  |  |  |
| Other grant providers: |  |  |  | 311 |  | – |  | – |  | – |  | – |  | – |  | – |  |  |  | – |  |  |
| Unspecified |  |  |  | 311 |  | – |  | – |  | – |  | – |  | – |  | – |  |  |  | – |  |  |
| Total operating expenditure of Transfers and Grants: |  |  |  | 20 756 |  | 28 368 |  | 25 373 |  | 6 175 |  | 38 911 |  | 38 911 |  | – |  |  |  | 25 373 |  |  |
| Capital expenditure of Transfers and Grants |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| National Government: |  |  |  | 87 466 |  | 151 069 |  | 151 069 |  | 11 100 |  | 29 507 |  | 29 507 |  | – |  |  |  | 151 069 |  |  |
| Integrated National Electrification Programme Grant |  |  |  | 2 907 |  | 10 000 |  | 10 000 |  | 3 421 |  | 3 897 |  | 3 897 |  | – |  |  |  | 10 000 |  |  |
| Municipal Infrastructure Grant |  |  |  | 41 107 |  | 56 069 |  | 56 069 |  | 7 296 |  | 20 447 |  | 20 447 |  | – |  |  |  | 56 069 |  |  |
| Regional Bulk Infrastructure Grant |  |  |  | 34 756 |  | 80 000 |  | 80 000 |  | – |  | – |  | – |  | – |  |  |  | 80 000 |  |  |
| Water Services Infrastructure Grant |  |  |  | 8 696 |  | 5 000 |  | 5 000 |  | 382 |  | 5 163 |  | 5 163 |  | – |  |  |  | 5 000 |  |  |
| Provincial Government: |  |  |  | – |  | – |  | – |  | – |  | – |  | – |  | – |  |  |  | – |  |  |
| Housing |  |  |  | – |  | – |  | – |  | – |  | – |  | – |  | – |  |  |  | – |  |  |
| Water Supply Infrastructure |  |  |  | – |  | – |  | – |  | – |  | – |  | – |  | – |  |  |  | – |  |  |
| District Municipality: |  |  |  | – |  | – |  | – |  | – |  | – |  | – |  | – |  |  |  | – |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | – |  |  |  |  |  |  |
| Other grant providers: |  |  |  | 25 690 |  | 26 200 |  | 26 200 |  | – |  | – |  | 6 550 |  | (6 550) |  | -100,0% |  | 26 200 |  |  |
| Buildings and Construction |  |  |  | – |  | – |  | – |  | – |  | – |  | – |  | – |  |  |  | – |  |  |
| Government Motor Transport |  |  |  | 1 611 |  | – |  | – |  | – |  | – |  | – |  | – |  |  |  | – |  |  |
| Households |  |  |  | – |  | – |  | – |  | – |  | – |  | – |  | – |  |  |  | – |  |  |
| Human Settlement Re-development Programme |  |  |  | – |  | 26 200 |  | 26 200 |  | – |  | – |  | 6 550 |  | (6 550) |  | -100,0% |  | 26 200 |  |  |
| South Africa Sport Commission |  |  |  | – |  | – |  | – |  | – |  | – |  | – |  | – |  |  |  | – |  |  |
| Unspecified |  |  |  | 24 079 |  | – |  | – |  | – |  | – |  | – |  | – |  |  |  | – |  |  |
| Total capital expenditure of Transfers and Grants |  |  |  | 113 156 |  | 177 269 |  | 177 269 |  | 11 100 |  | 29 507 |  | 36 057 |  | (6 550) |  | -18,2% |  | 177 269 |  |  |
| TOTAL EXPENDITURE OF TRANSFERS AND GRANTS |  |  |  | 133 912 |  | 205 637 |  | 202 642 |  | 17 275 |  | 68 419 |  | 74 969 |  | (6 550) |  | -8,7% |  | 202 642 |  |  |

10. Councillor allowance and employee benefit

| FS204 Metsimaholo - Supporting Table SC8 Monthly Budget Statement - councillor and staff benefits - M06 December |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Summary of Employee and Councillor remuneration | Ref | 2018/19 | Budget Year 2019/20 |  |  |  |  |  |  |  |
|  |  | Audited Outcome | Original Budget | Adjusted Budget | Monthly actual | YearTD actual | YearTD budget | YTD variance | YTD variance | Full Year Forecast |
| R thousands |  |  |  |  |  |  |  |  | % |  |
| Councillors (Political Office Bearers plus Other) |  |  |  |  |  |  |  |  |  |  |
| Basic Salaries and Wages |  | 12 576 | 14 457 | 14 457 | 1 130 | 6 787 | 7 229 | (442) | -6% | 14 457 |
| Pension and UIF Contributions |  | – | – | – | – | – | – | – |  | – |
| Medical Aid Contributions |  |  |  |  |  |  |  | – |  |  |
| Motor Vehicle Allowance |  |  |  |  |  |  |  | – |  |  |
| Cell phone Allowance |  | 1 706 | 2 004 | 2 004 | 143 | 857 | 1 002 | (145) | -14% | 2 004 |
| Housing Allowances |  | – | – | – | – | – | – | – |  | – |
| Other benefits and allowances |  | 3 271 | 3 394 | 3 394 | 286 | 1 709 | 1 697 | 12 | 1% | 3 394 |
| Sub Total - Councillors |  | 17 554 | 19 855 | 19 855 | 1 559 | 9 353 | 9 928 | (575) | -6% | 19 855 |
| % increase | 4 |  | 13,1% | 13,1% |  |  |  |  |  | 13,1% |
| Senior Managers of the Municipality | 3 |  |  |  |  |  |  |  |  |  |
| Basic Salaries and Wages |  | 1 830 | 8 086 | 8 086 | 124 | 744 | 4 043 | (3 298) | -82% | 8 086 |
| Pension and UIF Contributions |  | 2 | 19 | 19 | 0 | 1 | 9 | (8) | -90% | 19 |
| Medical Aid Contributions |  | – | – | – | – | – | – | – |  | – |
| Overtime |  | – | – | – | – | – | – | – |  | – |
| Performance Bonus |  | – | 815 | 815 | – | – | 408 | (408) | -100% | 815 |
| Motor Vehicle Allowance |  | 244 | 258 | 258 | 101 | 201 | 129 | 72 | 55% | 258 |
| Cellphone Allowance |  | 41 | 167 | 167 | 8 | 23 | 84 | (60) | -72% | 167 |
| Housing Allowances |  | – | – | – | – | – | – | – |  | – |
| Other benefits and allowances |  | 3 444 | 1 829 | 1 909 | 338 | 2 094 | 934 | 1 160 | 124% | 1 909 |
| Payments in lieu of leave |  | 367 | 108 | 108 | – | – | 54 | (54) | -100% | 108 |
| Long service awards |  | – | – | – | – | – | – | – |  | – |
| Post-retirement benefit obligations | 2 | (2 733) | – | – | – | – | – | – |  | – |
| Sub Total - Senior Managers of Municipality |  | 3 195 | 11 280 | 11 360 | 571 | 3 063 | 5 660 | (2 597) | -46% | 11 360 |
| % increase | 4 |  | 253,0% | 255,5% |  |  |  |  |  | 255,5% |
| Other Municipal Staff |  |  |  |  |  |  |  |  |  |  |
| Basic Salaries and Wages |  | 157 896 | 213 171 | 211 634 | 14 221 | 83 992 | 105 874 | (21 882) | -21% | 211 634 |
| Pension and UIF Contributions |  | 27 360 | 29 921 | 29 921 | 2 486 | 14 584 | 14 961 | (377) | -3% | 29 921 |
| Medical Aid Contributions |  | 17 227 | 19 355 | 19 355 | 1 506 | 8 847 | 9 678 | (831) | -9% | 19 355 |
| Overtime |  | 23 196 | 24 101 | 24 101 | 2 009 | 10 905 | 12 051 | (1 146) | -10% | 24 101 |
| Performance Bonus |  | 12 932 | 15 149 | 15 149 | 891 | 6 854 | 7 575 | (720) | -10% | 15 149 |
| Motor Vehicle Allowance |  | 18 534 | 21 581 | 21 581 | 1 542 | 9 785 | 10 791 | (1 005) | -9% | 21 581 |
| Cell phone Allowance |  | 1 224 | 1 511 | 1 511 | 109 | 672 | 756 | (84) | -11% | 1 511 |
| Housing Allowances |  | 2 433 | 2 180 | 2 180 | 208 | 1 262 | 1 090 | 172 | 16% | 2 180 |
| Other benefits and allowances |  | 10 393 | 10 880 | 11 247 | 1 353 | 8 266 | 5 567 | 2 699 | 48% | 11 247 |
| Payments in lieu of leave |  | 838 | 1 517 | 1 517 | 64 | 1 457 | 759 | 698 | 92% | 1 517 |
| Long service awards |  | 1 139 | 744 | 744 | 150 | 1 254 | 372 | 882 | 237% | 744 |
| Post-retirement benefit obligations | 2 | 12 252 | 7 998 | 7 998 | 174 | 1 054 | 3 999 | (2 945) | -74% | 7 998 |
| Sub Total - Other Municipal Staff |  | 285 423 | 348 109 | 346 939 | 24 713 | 148 932 | 173 471 | (24 540) | -14% | 346 939 |
| % increase | 4 |  | 22,0% | 21,6% |  |  |  |  |  | 21,6% |
| Total Parent Municipality |  | 306 172 | 379 245 | 378 155 | 26 843 | 161 348 | 189 059 | (27 711) | -15% | 378 155 |
|  |  |  | 23,9% | 23,5% |  |  |  |  |  | 23,5% |
| TOTAL SALARY, ALLOWANCES & BENEFITS |  | 306 172 | 379 245 | 378 155 | 26 843 | 161 348 | 189 059 | (27 711) | -15% | 378 155 |
| % increase | 4 |  | 23,9% | 23,5% |  |  |  |  |  | 23,5% |
| TOTAL MANAGERS AND STAFF |  | 288 618 | 359 390 | 358 299 | 25 284 | 151 995 | 179 131 | (27 137) | -15% | 358 299 |

# 11. Material variances to the Service Delivery and Budget Implementation Plan

# 11.1   Actual revenue must be at least at 50% of the budget and expenditure cannot exceed 50% of the budget. All the transactions for the year, especially on expenditure have not been processed.

# If there is no budget amount on revenue, it means that revenue was received that was not anticipated.

|  | Revenue less than 50% by end of December 2019 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Vote number | Description | Budget | Curr Mth Exp | YTD Movement | Unspent Bud | Perc | Remarks |
|  | MUNICIPAL MANAGER |  |  |  |  |  |  |
| 12001040530000000000 | PENALTIES: TENDER WITHDRAWAL | -600,000.00 | -3,500.00 | -45,247.25 | -554,752.75 | 7.54 |  |
| 12001178970000000000 | TS_O_M_NG_MIG GRANT | -2,582,600.00 | 0.00 | 0.00 | -2,582,600.00 | 0.00 | Journal must be done to allocate the funds |
|  | CORPORATE SERVICES |  |  |  |  |  |  |
| 13001385170000000000 | STAFF RECOVERIES | -250,000.00 | 0.00 | 0.00 | -250,000.00 | 0.00 |  |
|  | SOCIAL SERVICES |  |  |  |  |  |  |
| 14001040080000000000 | FINES: TRAFFIC - COURT FINES | -3,320,100.00 | -94,990.00 | -409,047.59 | -2,911,052.41 | 12.32 |  |
| 14001040100000000000 | FINES: TRAFFIC - MUNICIPAL | -13,000,000.00 | 0.00 | 0.00 | -13,000,000.00 | 0.00 |  |
| 14001060110000000000 | TRADING | -210,930.00 | 0.00 | 0.00 | -210,930.00 | 0.00 |  |
| 14001178910000000000 | TS_O_M_NG_EPWP GRANT | -1,157,000.00 | 0.00 | -290,000.00 | -867,000.00 | 25.06 |  |
| 14001179100000000000 | TS_O_M_NRF_EQUITABLE SHARE | -19,029,940.00 | -1,030,637.85 | -5,113,147.80 | -13,916,792.20 | 26.86 |  |
| 14001322010000000000 | WASTE MANGEMENT: DISPOSAL FACILITIES | -544,430.00 | -69,621.56 | -141,222.88 | -403,207.12 | 25.93 | The Division normally to road blocks to stop the defaulters to dispose at the site. Income Section gives discounts to people to continue using Landfill site. The road to Landfill site was closed for ±3 Weeks in December. Users at the site used alternative |
| 14001420080000000000 | ADVERTISEMENTS | -30,490.00 | 0.00 | 0.00 | -30,490.00 | 0.00 |  |
| 15001258940000000000 | TS_C_M_NG_MIG GRANT | -10,242,760.00 | 0.00 | 0.00 | -10,242,760.00 | 0.00 | Allocation to revenue be done when assets are capitalised |
| 15001259400000000000 | SUPPLY DESC | -7,000,000.00 | 0.00 | 0.00 | -7,000,000.00 | 0.00 |  |
| 15001400880000000000 | N-M-R PPE: S/LINE-COMMUNITY ASSETS | -319,400.00 | -510.00 | -8,938.71 | -310,461.29 | 2.79 |  |
| 15001401090000000000 | N-M-R PPE: AD HOC-COMMUNITY ASSETS | 0.00 | -500.00 | -3,000.00 | 3,000.00 | 0.00 |  |
| 15001401100000000000 | N-M-R PPE: AD HOC-OTHER ASSETS | -587,300.00 | 0.00 | -29,635.66 | -557,664.34 | 5.04 |  |
| 15001420610000000000 | CEMETERY & BURIAL | -495,000.00 | -14,916.53 | -220,739.18 | -274,260.82 | 44.59 |  |
| 15001421210000000000 | ENTRANCE FEES | -1,100,000.00 | -18,312.96 | -233,955.46 | -866,044.54 | 21.26 |  |
|  | TECHNICAL SERVICES |  |  |  |  |  |  |
| 16001179100000000000 | TS_O_M_NRF_EQUITABLE SHARE | -34,593,890.00 | -1,916,646.47 | -9,713,422.08 | -24,880,467.92 | 28.07 |  |
| 16001219400000000000 | PRIV ENT: SUBS N-FIN ENTPR - PRODUCTION | -70,000,000.00 | 0.00 | 0.00 | -70,000,000.00 | 0.00 | Allocation to revenue be done when assets are capitalised |
| 16001219420000000000 | TS_C_IK_PG_FS_INFR_SPEC | -26,200,000.00 | 0.00 | 0.00 | -26,200,000.00 | 0.00 | Allocation to revenue be done when assets are capitalised |
| 16001258910000000000 | TS_C_M_NG_INEP GRANT | -10,000,000.00 | 0.00 | 0.00 | -10,000,000.00 | 0.00 | Allocation to revenue be done when assets are capitalised |
| 16001258940000000000 | TS_C_M_NG_MIG GRANT | -38,826,640.00 | 0.00 | 0.00 | -38,826,640.00 | 0.00 | Allocation to revenue be done when assets are capitalised |
| 16001259030000000000 | TS_C_M_NG_WSIG GRANT | -15,000,000.00 | 0.00 | 0.00 | -15,000,000.00 | 0.00 | Allocation to revenue be done when assets are capitalised |
| 16001321080000000000 | ELEC: METER READING FEES | 0.00 | -1,025.00 | -15,295.00 | 15,295.00 | 0.00 |  |
| 16001321120000000000 | ELEC SALES: COMMERC CONVEN SINGLE PHASE | -49,952,640.00 | -3,003,971.12 | -19,361,603.65 | -30,591,036.35 | 38.75 |  |
| 16001321130000000000 | ELEC SALES: COMMERCIAL CONVEN 3-PHASE | 0.00 | -19,289.09 | -19,289.09 | 19,289.09 | 0.00 |  |
| 16001321160000000000 | ELEC SALES: DOMESTI LOW HOME LIGHT 1 60A | -27,345,670.00 | -1,669,373.43 | -12,293,100.82 | -15,052,569.18 | 44.95 |  |
| 16001321270000000000 | ELEC SALES: INDUSTR 11 000 VOLTS (HIGH) | -1,611,060.00 | -95,807.50 | -324,520.66 | -1,286,539.34 | 20.14 |  |
| 16001321310000000000 | ELEC SALES: SPORT/CHURCH/HOLIDAY/OLD-AGE | -8,799,420.00 | -378,475.97 | -974,001.30 | -7,825,418.70 | 11.06 |  |
| 16001321330000000000 | ELEC SALES: WATER PUMPS | -1,848,770.00 | -8,851.90 | -245,089.19 | -1,603,680.81 | 13.25 |  |
| 16001321380000000000 | ELEC: AVAILABILITY CHARGES | -12,766,790.00 | -950,104.40 | -5,689,485.20 | -7,077,304.80 | 44.56 |  |
| 16001323020000000000 | WASTE WATER MANG: SANITATION CHARGES | -23,051,080.00 | -1,748,256.71 | -10,660,408.84 | -12,390,671.16 | 46.24 |  |
| 16001323060000000000 | WASTE WATER MANG: AVAILABILITY CHARGES | -5,172,950.00 | -304,589.95 | -1,749,584.35 | -3,423,365.65 | 33.82 |  |
| 16001323070000000000 | WASTE WATER MANG: CONNECTION/RECONNECTIO | 0.00 | 0.00 | -16,367.54 | 16,367.54 | 0.00 |  |
| 16001324000000000000 | WATER: CONNECTION/RECONNECTION | -257,070.00 | -2,373.60 | -94,509.60 | -162,560.40 | 36.76 |  |
| 16001324010000000000 | WATER: METER READING FEES | 0.00 | -1,230.00 | -59,795.00 | 59,795.00 | 0.00 |  |
| 16001324060000000000 | WATER: INDUSTRIAL WATER | -287,972,080.00 | -14,608,776.53 | -121,434,438.62 | -166,537,641.38 | 42.16 |  |
| 16001424540000000000 | PLAN & DEV: BUILDING PLAN APPROVAL | -5,840.00 | 0.00 | -305.61 | -5,534.39 | 5.23 |  |
| 16001424570000000000 | PLAN & DEV: DRAINAGE FEES | 0.00 | -500.02 | -4,543.66 | 4,543.66 | 0.00 |  |
|  | FINANCIAL SERVICES |  |  |  |  |  |  |
| 17001021500000000000 | FARM PROPERTIES: AGRICULTURAL PURPOSES | -3,135,770.00 | 0.00 | -546,238.38 | -2,589,531.62 | 17.41 |  |
| 17001025100000000000 | RESIDENTIAL PROPERTIES: DEVELOPED | -89,071,610.00 | -6,700,406.18 | -40,728,607.67 | -48,343,002.33 | 45.72 |  |
| 17001025110000000000 | RESIDENTIAL PROPERTIES: VACANT LAND | -9,765,300.00 | -181,270.46 | -1,092,804.00 | -8,672,496.00 | 11.19 |  |
| 17001025460000000000 | STATE-OWNED PROPERTIES | -15,688,960.00 | 0.00 | -1,877,490.26 | -13,811,469.74 | 11.96 |  |
| 17001380010000000000 | ADMINISTRATIVE HANDLING FEES | 0.00 | -4,619.72 | -14,194.45 | 14,194.45 | 0.00 |  |
| 17001423310000000000 | LEGAL FEES | -5,300,000.00 | -237,717.61 | -1,630,211.72 | -3,669,788.28 | 30.75 |  |
| 17001425520000000000 | SALE OF: VALUATION ROLLS | -260,000.00 | 0.00 | 0.00 | -260,000.00 | 0.00 |  |
|  | LED |  |  |  |  |  |  |
| 18001382420000000000 | INSPECTION FEES: AGRICULTURAL ACTIVITIES | -105,260.00 | 0.00 | 0.00 | -105,260.00 | 0.00 |  |
| 18001401100000000000 | N-M-R PPE: AD HOC-OTHER ASSETS | -5,655,210.00 | -441,949.48 | -2,688,130.90 | -2,967,079.10 | 47.53 |  |
| 18001424550000000000 | PLAN & DEV: BUILDING PLAN CLAUSE LEVY | -300,000.00 | -5,739.30 | -83,916.43 | -216,083.57 | 27.97 |  |
| 18001425430000000000 | SALE OF: AGRIC PROD - ASSET < CAP THRESH | -5,107,260.00 | -8,960.00 | -163,947.00 | -4,943,313.00 | 3.21 |  |

|  | Expenditure more than 50% by end of December 2019 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Vote number | Description | Budget | Curr Mth Exp | YTD Movement | Unspent Bud | Perc | Remarks |
|  | COUNCIL |  |  |  |  |  |  |
| 11002110220000000000 | MS: ALL - CELLULAR & TELEPHONE | 128,380.00 | 13,109.21 | 75,967.51 | 52,412.49 | 59.17 |  |
| 11002110320000000000 | MS: ALL - LEAVE PAY | 93,750.00 | 38,865.98 | 987,329.74 | -893,579.74 | 999.99 |  |
| 11002110380000000000 | MS: OVERTIME - STRUCTURED | 543,460.00 | 32,513.98 | 373,448.53 | 170,011.47 | 68.71 |  |
| 11002110440000000000 | MS: SRB - ACTING ALLOWANCE | 115,000.00 | 12,597.98 | 77,508.17 | 37,491.83 | 67.39 |  |
| 11002110460000000000 | MS: SRB - ANNUAL BONUS | 904,010.00 | 20,034.34 | 568,106.34 | 335,903.66 | 62.84 |  |
| 11002110500000000000 | MS: SRB - LONG SERVICE AWARD | 89,550.00 | 0.00 | 52,301.65 | 37,248.35 | 58.40 |  |
| 11002110560000000000 | MS: SRB - STANDBY ALLOWANCE | 10,000.00 | 7,772.84 | 110,037.04 | -100,037.04 | 999.99 |  |
| 11002130200000000000 | MS: SOC CONTR - MEDICAL | 263,240.00 | 58,857.00 | 184,497.00 | 78,743.00 | 70.08 |  |
| 11002130300000000000 | MS: SOC CONTR - PENSION | 342,070.00 | 144,159.82 | 498,332.87 | -156,262.87 | 145.68 |  |
| 11002210310000000000 | WHIP: OFFICE-BEARER ALLOWANCE | 513,680.00 | 54,016.92 | 324,101.52 | 189,578.48 | 63.09 |  |
| 11002210650000000000 | EXEC MAYOR: TRAVELLING ALLOWANCE | 212,000.00 | 17,905.65 | 107,433.90 | 104,566.10 | 50.67 |  |
| 11002211250000000000 | EXCO: TRAVELLING ALLOWANCE | 710,200.00 | 64,460.30 | 386,761.80 | 323,438.20 | 54.45 |  |
| 11002211550000000000 | OTH COUNCIL: TRAVELLING ALLOWANCE | 1,060,000.00 | 91,796.60 | 545,113.14 | 514,886.86 | 51.42 |  |
| 11002285430000000000 | CONTR: STAGE & SOUND CREW | 152,330.00 | 28,700.00 | 110,720.00 | 41,610.00 | 72.68 |  |
| 11002301600000000000 | OC: ENTERTAINMENT - EXEC MAYOR | 6,000.00 | 0.00 | 7,569.00 | -1,569.00 | 126.15 |  |
| 1100232061F000000000 | INV - CONSUMABL STORES -ZERO RATED FLEET | 108,000.00 | 25,890.60 | 66,906.09 | 41,093.91 | 61.95 |  |
| 11002362540000000000 | INT PAID: FINANCE LEASES | 37,510.00 | 6,257.97 | 23,349.97 | 14,160.03 | 62.24 |  |
| 11002721500000000000 | DEPRECIATION FURNITURE & OFFICE EQUIPM | 33,760.00 | 19,871.47 | 19,871.47 | 13,888.53 | 58.86 | Re-allocation between depreciation votes will be done with adjustment budget. Total depreciation is in line with the budget |
| 11002725700000000000 | DEPRECIATION TRANSPORT ASSETS | 69,110.00 | 88,151.13 | 88,151.13 | -19,041.13 | 127.55 | Re-allocation between depreciation votes will be done with adjustment budget. Total depreciation is in line with the budget |
|  | MUNICIPAL MANAGER |  |  |  |  |  |  |
| 12002030070000000000 | SM MM: ALLOW - CELLULAR & TELEPHONE | 38,700.00 | 8,290.78 | 23,290.78 | 15,409.22 | 60.18 |  |
| 12002030090000000000 | SM MM: ALLOW - TRAVEL OR MOTOR VEHICLE | 258,000.00 | 100,506.56 | 200,506.56 | 57,493.44 | 77.71 |  |
| 12002030160000000000 | SM MM: SRB - ENTERTAINMENT | 86,000.00 | 0.00 | 81,475.00 | 4,525.00 | 94.73 |  |
| 12002030180000000000 | SM MM: SRB - ACTING & POST RELATED ALLOW | 300,000.00 | 109,193.93 | 584,736.71 | -284,736.71 | 194.91 |  |
| 12002110260000000000 | MS: HB & INC: HOUSING BENEFITS | 182,420.00 | 16,589.86 | 98,631.39 | 83,788.61 | 54.06 |  |
| 12002110460000000000 | MS: SRB - ANNUAL BONUS | 882,470.00 | 196,422.80 | 595,872.98 | 286,597.02 | 67.52 |  |
| 12002110560000000000 | MS: SRB - STANDBY ALLOWANCE | 66,400.00 | 2,890.20 | 37,183.34 | 29,216.66 | 55.99 |  |
| 12002130300000000000 | MS: SOC CONTR - PENSION | 1,818,370.00 | 156,185.03 | 918,088.51 | 900,281.49 | 50.48 |  |
| 12002140080000000000 | MS: PRB - MED: PAST SERVICE COST | 108,830.00 | 8,984.70 | 54,456.56 | 54,373.44 | 50.03 |  |
| 12002265170000000000 | OS: PRINTING SERVICES | 403,500.00 | 11,603.00 | 232,964.02 | 170,535.98 | 57.73 |  |
| 12002305810000000000 | OC: T&S DOM TRP - W/OUT OPR OWN TRANSPRT | 5,000.00 | 1,686.24 | 4,799.61 | 200.39 | 95.99 |  |
| 12002320600000000000 | INV - CONSUMABLE STORES - STANDARD RATED | 453,550.00 | 159,089.56 | 256,249.80 | 197,300.20 | 56.49 |  |
| 12002323600000000000 | INVENTORY - MATERIALS & SUPPLIES | 566,040.00 | 90,590.00 | 297,203.56 | 268,836.44 | 52.50 |  |
| 12002362540000000000 | INT PAID: FINANCE LEASES | 27,870.00 | 4,613.82 | 21,233.83 | 6,636.17 | 76.18 | Allocations of interest be corrected |
| 12002720040000000000 | AMORTISATION INTANG COMPUTER SOFTWARE | 1,648,070.00 | 870,837.85 | 870,837.85 | 777,232.15 | 52.83 |  |
| 12002723600000000000 | DEPRECIATION MACHINERY & EQUIPMENT | 456,940.00 | 267,635.90 | 267,635.90 | 189,304.10 | 58.57 | Re-allocation between depreciation votes will be done with adjustment budget. Total depreciation is in line with the budget |
| 12002729200000000000 | DEPRECIATION OP BUILDING MUNIC OFFICES | 1,120.00 | 99,484.17 | 99,484.17 | -98,364.17 | 999.99 | Re-allocation between depreciation votes will be done with adjustment budget. Total depreciation is in line with the budget |
|  | CORPORATE SERVICES |  |  |  |  |  |  |
| 13002030980000000000 | SM D01: SRB - ACTING & POST RELATE ALLOW | 222,500.00 | 52,137.89 | 303,135.30 | -80,635.30 | 136.24 |  |
| 13002110220000000000 | MS: ALL - CELLULAR & TELEPHONE | 113,200.00 | 4,932.63 | 58,141.87 | 55,058.13 | 51.36 |  |
| 13002110380000000000 | MS: OVERTIME - STRUCTURED | 159,250.00 | 16,385.98 | 82,299.92 | 76,950.08 | 51.67 |  |
| 13002110440000000000 | MS: SRB - ACTING ALLOWANCE | 139,250.00 | -25,950.98 | 146,714.92 | -7,464.92 | 105.36 |  |
| 13002110560000000000 | MS: SRB - STANDBY ALLOWANCE | 12,600.00 | 964.32 | 7,375.68 | 5,224.32 | 58.53 |  |
| 13002130010000000000 | MS: SOC CONTR - BARGAINING COUNCIL | 3,870.00 | 326.20 | 2,014.43 | 1,855.57 | 52.05 |  |
| 13002260620000000000 | OS: CLEANING SERVICES | 1,735,000.00 | 242,250.72 | 1,453,504.32 | 281,495.68 | 83.77 |  |
| 13002303330000000000 | OC: LIC - VEHICLE LIC & REGISTRATIONS | 2,630.00 | 0.00 | 1,345.00 | 1,285.00 | 51.14 |  |
| 13002304520000000000 | OC: PROFESSIONAL BODIES M/SHIP & SUBS | 3,212,610.00 | 0.00 | 3,178,072.00 | 34,538.00 | 98.92 |  |
| 13002728800000000000 | DEPRECIATION COMMUNITY HALLS | 120,000.00 | 69,508.43 | 69,508.43 | 50,491.57 | 57.92 | Re-allocation between depreciation votes will be done with adjustment budget. Total depreciation is in line with the budget |
| 13002729230000000000 | DEPRECIATION OP BUILDING WORKSHOPS | 1,320.00 | 768.23 | 768.23 | 551.77 | 58.19 | Re-allocation between depreciation votes will be done with adjustment budget. Total depreciation is in line with the budget |
|  | SOCIAL SERVICES |  |  |  |  |  |  |
| 14002031360000000000 | SM D02: SRB - ENTERTAINMENT | 2,000.00 | 0.00 | 1,833.91 | 166.09 | 91.69 |  |
| 14002031380000000000 | SM D02: SRB - ACTING & POST RELATE ALLOW | 215,000.00 | 52,137.89 | 303,135.30 | -88,135.30 | 140.99 |  |
| 14002110260000000000 | MS: HB & INC: HOUSING BENEFITS | 335,570.00 | 56,381.69 | 355,764.17 | -20,194.17 | 106.01 |  |
| 14002110320000000000 | MS: ALL - LEAVE PAY | 162,250.00 | 541.45 | 121,618.73 | 40,631.27 | 74.95 |  |
| 14002110400000000000 | MS: PAYMENTS - SHIFT ADD REMUNERATION | 1,401,120.00 | 301,604.24 | 1,796,039.96 | -394,919.96 | 128.18 |  |
| 14002110440000000000 | MS: SRB - ACTING ALLOWANCE | 225,970.00 | 44,093.55 | 248,736.73 | -22,766.73 | 110.07 | Waste Management: The vote is over spent due to none appointment of Staff. |
| 14002110500000000000 | MS: SRB - LONG SERVICE AWARD | 215,000.00 | 272.64 | 273,047.55 | -58,047.55 | 126.99 |  |
| 14002130100000000000 | MS: SOC CONTR - GROUP LIFE INSURANCE | 52,100.00 | 4,441.83 | 26,708.64 | 25,391.36 | 51.26 |  |
| 14002303330000000000 | OC: LIC - VEHICLE LIC & REGISTRATIONS | 324,710.00 | 0.00 | 179,644.50 | 145,065.50 | 55.32 |  |
| 14002305110000000000 | OC: REG FEES NATIONAL | 15,500.00 | 0.00 | 15,700.00 | -200.00 | 101.29 |  |
| 1400232061F000000000 | INV - CONSUMABL STORES -ZERO RATED FLEET | 1,692,360.00 | 127,805.50 | 968,084.99 | 724,275.01 | 57.20 |  |
| 1400232360F000000000 | INVENTORY - MATERIALS & SUPPLIES FLEET | 1,307,500.00 | 2,773.81 | 745,791.97 | 561,708.03 | 57.03 |  |
| 14002362420000000000 | INT PAID BOR: ANNUITY LOANS | 34,040.00 | 22,144.21 | 22,144.21 | 11,895.79 | 65.05 |  |
| 14002599400000000000 | HH SSP SOC ASS: SOCIAL RELIEF | 31,000.00 | 0.00 | 43,625.40 | -12,625.40 | 140.72 |  |
| 14002721000000000000 | DEPRECIATION SOLID WASTE LANDFILL SITES | 2,540.00 | 1,819.39 | 1,819.39 | 720.61 | 71.62 | Re-allocation between depreciation votes will be done with adjustment budget. Total depreciation is in line with the budget |
| 14002721500000000000 | DEPRECIATION FURNITURE & OFFICE EQUIPM | 9,790.00 | 12,866.71 | 12,866.71 | -3,076.71 | 131.42 | Re-allocation between depreciation votes will be done with adjustment budget. Total depreciation is in line with the budget |
| 14002723600000000000 | DEPRECIATION MACHINERY & EQUIPMENT | 353,350.00 | 595,582.95 | 595,582.95 | -242,232.95 | 168.55 | Re-allocation between depreciation votes will be done with adjustment budget. Total depreciation is in line with the budget |
| 15002110380000000000 | MS: OVERTIME - STRUCTURED | 1,940,880.00 | 198,499.80 | 1,043,687.90 | 897,192.10 | 53.77 |  |
| 15002110440000000000 | MS: SRB - ACTING ALLOWANCE | 256,290.00 | 21,652.88 | 185,625.31 | 70,664.69 | 72.42 |  |
| 15002110460000000000 | MS: SRB - ANNUAL BONUS | 1,551,630.00 | 10,049.76 | 791,283.37 | 760,346.63 | 50.99 |  |
| 15002110500000000000 | MS: SRB - LONG SERVICE AWARD | 21,500.00 | 17,274.05 | 245,102.34 | -223,602.34 | 999.99 |  |
| 15002110560000000000 | MS: SRB - STANDBY ALLOWANCE | 67,500.00 | 6,550.23 | 41,216.10 | 26,283.90 | 61.06 |  |
| 15002110600000000000 | MS: SRB - UNIFORM/SPEC/PROTEC CLOTHING | 715,000.00 | 0.00 | 554,446.97 | 160,553.03 | 77.54 |  |
| 15002130300000000000 | MS: SOC CONTR - PENSION | 3,304,360.00 | 277,229.38 | 1,663,179.16 | 1,641,180.84 | 50.33 |  |
| 15002140080000000000 | MS: PRB - MED: PAST SERVICE COST | 103,470.00 | 12,511.95 | 75,345.88 | 28,124.12 | 72.81 |  |
| 15002303330000000000 | OC: LIC - VEHICLE LIC & REGISTRATIONS | 23,020.00 | 0.00 | 20,693.50 | 2,326.50 | 89.89 |  |
| 15002721500000000000 | DEPRECIATION FURNITURE & OFFICE EQUIPM | 114,240.00 | 109,009.57 | 109,009.57 | 5,230.43 | 95.42 | Re-allocation between depreciation votes will be done with adjustment budget. Total depreciation is in line with the budget |
| 15002723600000000000 | DEPRECIATION MACHINERY & EQUIPMENT | 136,370.00 | 378,097.89 | 378,097.89 | -241,727.89 | 277.25 | Re-allocation between depreciation votes will be done with adjustment budget. Total depreciation is in line with the budget |
| 15002728800000000000 | DEPRECIATION COMMUNITY HALLS | 3,810.00 | 809,177.94 | 809,177.94 | -805,367.94 | 999.99 | Re-allocation between depreciation votes will be done with adjustment budget. Total depreciation is in line with the budget |
|  | TECHNICAL SERVICES |  |  |  |  |  |  |
| 16002031780000000000 | SM D03: SRB - ACTING & POST RELATE ALLOW | 322,500.00 | 0.00 | 223,400.59 | 99,099.41 | 69.27 |  |
| 16002110220000000000 | MS: ALL - CELLULAR & TELEPHONE | 307,850.00 | 25,776.53 | 156,533.31 | 151,316.69 | 50.84 |  |
| 16002110380000000000 | MS: OVERTIME - STRUCTURED | 7,992,470.00 | 1,036,003.73 | 5,188,889.63 | 2,803,580.37 | 64.92 |  |
| 16002110440000000000 | MS: SRB - ACTING ALLOWANCE | 874,140.00 | 78,122.74 | 606,225.83 | 267,914.17 | 69.35 |  |
| 16002110500000000000 | MS: SRB - LONG SERVICE AWARD | 129,000.00 | 86,816.92 | 250,465.96 | -121,465.96 | 194.15 |  |
| 16002110560000000000 | MS: SRB - STANDBY ALLOWANCE | 1,926,830.00 | 302,486.64 | 1,791,790.64 | 135,039.36 | 92.99 |  |
| 16002110600000000000 | MS: SRB - UNIFORM/SPEC/PROTEC CLOTHING | 1,070,640.00 | 78,520.20 | 820,640.37 | 249,999.63 | 76.64 |  |
| 16002303330000000000 | OC: LIC - VEHICLE LIC & REGISTRATIONS | 222,160.00 | 147.00 | 125,860.50 | 96,299.50 | 56.65 |  |
| 16002305760000000000 | OC: T&S DOM - ACCOMMODATION | 50,980.00 | 0.00 | 27,049.14 | 23,930.86 | 53.05 |  |
| 1600232061F000000000 | INV - CONSUMABL STORES -ZERO RATED FLEET | 2,007,340.00 | 281,746.45 | 1,177,597.45 | 829,742.55 | 58.66 |  |
| 16002326600000000000 | INVENTORY - WATER | 600,000.00 | 228,000.00 | 396,000.00 | 204,000.00 | 66.00 |  |
| 16002340010000000000 | ESKOM | 287,044,840.00 | 18,159,726.84 | 143,690,542.72 | 143,354,297.28 | 50.05 |  |
| 16002383600000000000 | OPR LEASES: MACHINERY & EQUIPMENT | 3,217,090.00 | 479,680.59 | 1,692,773.07 | 1,524,316.93 | 52.61 |  |
| 16002721220000000000 | DEPRECIATION WATER SUPPLY RESERVOIRS | 378,220.00 | 189,462.08 | 189,462.08 | 188,757.92 | 50.09 | Re-allocation between depreciation votes will be done with adjustment budget. Total depreciation is in line with the budget |
| 16002721260000000000 | DEPRECIATION WATER SUPPLY DISTRIBUTION | 7,995,150.00 | 10,973,147.78 | 10,973,147.78 | -2,977,997.78 | 137.24 | Re-allocation between depreciation votes will be done with adjustment budget. Total depreciation is in line with the budget |
| 16002721500000000000 | DEPRECIATION FURNITURE & OFFICE EQUIPM | 71,990.00 | 68,616.30 | 68,616.30 | 3,373.70 | 95.31 | Re-allocation between depreciation votes will be done with adjustment budget. Total depreciation is in line with the budget |
| 16002722430000000000 | DEPRECIATION ELEC HV SUBSTATIONS | 41,600.00 | 447,819.37 | 447,819.37 | -406,219.37 | 999.99 | Re-allocation between depreciation votes will be done with adjustment budget. Total depreciation is in line with the budget |
| 16002722460000000000 | DEPRECIATION ELEC MV SUBSTATIONS | 119,750.00 | 397,349.52 | 397,349.52 | -277,599.52 | 331.81 | Re-allocation between depreciation votes will be done with adjustment budget. Total depreciation is in line with the budget |
| 16002722470000000000 | DEPRECIATION ELEC MV SWITCHING STATIONS | 40,880.00 | 28,037.04 | 28,037.04 | 12,842.96 | 68.58 | Re-allocation between depreciation votes will be done with adjustment budget. Total depreciation is in line with the budget |
| 16002722480000000000 | DEPRECIATION ELEC MV NETWORKS | 7,742,970.00 | 3,917,402.47 | 3,917,402.47 | 3,825,567.53 | 50.59 | Re-allocation between depreciation votes will be done with adjustment budget. Total depreciation is in line with the budget |
| 16002722490000000000 | DEPRECIATION ELEC LV NETWORKS | 124,920.00 | 292,826.32 | 292,826.32 | -167,906.32 | 234.41 | Re-allocation between depreciation votes will be done with adjustment budget. Total depreciation is in line with the budget |
| 16002723600000000000 | DEPRECIATION MACHINERY & EQUIPMENT | 1,650,470.00 | 1,000,844.42 | 1,000,844.42 | 649,625.58 | 60.63 | Re-allocation between depreciation votes will be done with adjustment budget. Total depreciation is in line with the budget |
| 16002728010000000000 | DEPRECIATION ROADS STRUCTURES | 5,477,030.00 | 3,500,916.77 | 3,500,916.77 | 1,976,113.23 | 63.91 | Re-allocation between depreciation votes will be done with adjustment budget. Total depreciation is in line with the budget |
| 16002729200000000000 | DEPRECIATION OP BUILDING MUNIC OFFICES | 206,980.00 | 165,170.31 | 165,170.31 | 41,809.69 | 79.80 | Re-allocation between depreciation votes will be done with adjustment budget. Total depreciation is in line with the budget |
|  | FINANCIAL SERVICES |  |  |  |  |  |  |
| 17002030580000000000 | SM CFO: SRB - ACTING & POST RELATE ALLOW | 430,000.00 | 71,999.94 | 295,687.03 | 134,312.97 | 68.76 | Post of CFO not filled. Transfer of funds from salary vote – CFO to acting vote |
| 17002110220000000000 | MS: ALL - CELLULAR & TELEPHONE | 121,510.00 | 10,404.80 | 60,839.59 | 60,670.41 | 50.06 |  |
| 17002110260000000000 | MS: HB & INC: HOUSING BENEFITS | 256,720.00 | 21,470.94 | 129,733.41 | 126,986.59 | 50.53 |  |
| 17002110440000000000 | MS: SRB - ACTING ALLOWANCE | 320,000.00 | 27,386.11 | 243,332.20 | 76,667.80 | 76.04 | Staff not appointed and therefor acting longer than anticipated. |
| 17002110460000000000 | MS: SRB - ANNUAL BONUS | 2,005,460.00 | 35,887.09 | 1,004,537.45 | 1,000,922.55 | 50.09 |  |
| 17002110500000000000 | MS: SRB - LONG SERVICE AWARD | 161,250.00 | 23,478.61 | 335,268.87 | -174,018.87 | 207.91 | Adjust with adjustment budget |
| 17002110600000000000 | MS: SRB - UNIFORM/SPEC/PROTEC CLOTHING | 102,000.00 | 0.00 | 68,907.01 | 33,092.99 | 67.55 |  |
| 17002130010000000000 | MS: SOC CONTR - BARGAINING COUNCIL | 10,170.00 | 894.72 | 5,329.27 | 4,840.73 | 52.40 |  |
| 17002130100000000000 | MS: SOC CONTR - GROUP LIFE INSURANCE | 63,630.00 | 5,696.41 | 32,967.21 | 30,662.79 | 51.81 |  |
| 17002265110000000000 | OS: CONNECT/DIS-CONNECTION: ELECTICITY | 350,000.00 | 81,973.45 | 248,657.54 | 101,342.46 | 71.04 |  |
| 17002300400000000000 | OC: BC/FAC/C FEES - BANK ACCOUNTS | 700,000.00 | 37,192.71 | 367,701.95 | 332,298.05 | 52.52 | Bank cost depends on number of transactions |
| 17002301120000000000 | OC: COMM - POSTAGE/STAMPS/FRANKING MACH | 1,580,000.00 | 123,256.03 | 815,744.77 | 764,255.23 | 51.62 | Email of accounts not 100% effective |
| 17002303330000000000 | OC: LIC - VEHICLE LIC & REGISTRATIONS | 3,200.00 | 0.00 | 2,397.50 | 802.50 | 74.92 | Pay one once ayear |
| 17002723600000000000 | DEPRECIATION MACHINERY & EQUIPMENT | 39,450.00 | 35,767.65 | 35,767.65 | 3,682.35 | 90.66 | Re-allocation between depreciation votes will be done with adjustment budget. Total depreciation is in line with the budget |
|  | LED |  |  |  |  |  |  |
| 18002032580000000000 | SM D05: SRB - ACTING & POST RELATE ALLOW | 322,500.00 | 52,137.89 | 300,652.55 | 21,847.45 | 93.22 |  |
| 18002110260000000000 | MS: HB & INC: HOUSING BENEFITS | 83,450.00 | 8,012.16 | 44,441.88 | 39,008.12 | 53.25 |  |
| 18002110320000000000 | MS: ALL - LEAVE PAY | 43,000.00 | 0.00 | 92,252.04 | -49,252.04 | 214.53 |  |
| 18002110440000000000 | MS: SRB - ACTING ALLOWANCE | 117,100.00 | 17,944.36 | 95,392.80 | 21,707.20 | 81.46 |  |
| 18002110460000000000 | MS: SRB - ANNUAL BONUS | 1,156,430.00 | 52,337.32 | 692,442.71 | 463,987.29 | 59.87 |  |
| 18002110500000000000 | MS: SRB - LONG SERVICE AWARD | 10,750.00 | 22,301.66 | 80,628.26 | -69,878.26 | 750.03 |  |
| 18002130100000000000 | MS: SOC CONTR - GROUP LIFE INSURANCE | 4,830.00 | 1,761.23 | 6,170.20 | -1,340.20 | 127.74 |  |
| 18002140080000000000 | MS: PRB - MED: PAST SERVICE COST | 54,400.00 | 9,018.00 | 57,786.60 | -3,386.60 | 106.22 |  |
| 18002303330000000000 | OC: LIC - VEHICLE LIC & REGISTRATIONS | 1,200.00 | 0.00 | 654.00 | 546.00 | 54.50 |  |
| 1800230572F000000000 | OC: TOLL GATE FEES FLEET | 3,000.00 | 708.50 | 2,020.50 | 979.50 | 67.35 |  |
| 18002305760000000000 | OC: T&S DOM - ACCOMMODATION | 70,000.00 | 5,287.65 | 46,925.75 | 23,074.25 | 67.03 |  |
| 18002305770000000000 | OC: T&S DOM - DAILY ALLOWANCE | 8,000.00 | 268.00 | 5,226.00 | 2,774.00 | 65.32 |  |
| 18002305810000000000 | OC: T&S DOM TRP - W/OUT OPR OWN TRANSPRT | 22,000.00 | 2,651.53 | 17,654.73 | 4,345.27 | 80.24 |  |
| 1800232061F000000000 | INV - CONSUMABL STORES -ZERO RATED FLEET | 15,000.00 | 5,778.41 | 15,382.56 | -382.56 | 102.55 |  |
| 18002721260000000000 | DEPRECIATION WATER SUPPLY DISTRIBUTION | 50.00 | 30.16 | 30.16 | 19.84 | 60.32 | Re-allocation between depreciation votes will be done with adjustment budget. Total depreciation is in line with the budget |
| 18002721500000000000 | DEPRECIATION FURNITURE & OFFICE EQUIPM | 24,130.00 | 13,453.17 | 13,453.17 | 10,676.83 | 55.75 | Re-allocation between depreciation votes will be done with adjustment budget. Total depreciation is in line with the budget |
| 18002722480000000000 | DEPRECIATION ELEC MV NETWORKS | 207,900.00 | 106,530.11 | 106,530.11 | 101,369.89 | 51.24 | Re-allocation between depreciation votes will be done with adjustment budget. Total depreciation is in line with the budget |
| 18002728800000000000 | DEPRECIATION COMMUNITY HALLS | 1,600.00 | 128,006.56 | 128,006.56 | -126,406.56 | 999.99 | Re-allocation between depreciation votes will be done with adjustment budget. Total depreciation is in line with the budget |
| 18002729230000000000 | DEPRECIATION OP BUILDING WORKSHOPS | 19,200.00 | 16,055.30 | 16,055.30 | 3,144.70 | 83.62 | Re-allocation between depreciation votes will be done with adjustment budget. Total depreciation is in line with the budget |

Variance to monthly target of Cash flow for December 2019 as per SDBIP

| Detail | Actual July | Actual Aug | Actual Sept | Actual Oct | Actual Nov | Month 6 Dec | Actual Dec | Var | Var % | Month 7 Jan | Month 8 Feb | Month 9 Mar | Month 10 Apr | Month 11 May | Month 12 June |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cash Receipts by Source |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Property rates | 10,453,021 | 14,024 | 10,447,978 | 18,990,234 | 11,950,222 | 13,542,000 | 9,634,298 | 3,907,702 | 29 | 10,542,000 | 14,542,000 | 14,542,000 | 14,542,000 | 14,542,000 | 174,290,240 |
| Service charges - electricity revenue | 29,097,420 | 37,588 | 16,391,349 | 29,506,235 | 22,678,382 | 19,097,420 | 18,812,270 | 285,150 | 1 | 18,097,420 | 17,097,420 | 24,097,420 | 25,097,420 | 26,097,420 | 276,779,470 |
| Service charges - water revenue | 21,177,190 | 29,027 | 15,987,182 | 39,234,833 | 18,290,691 | 35,427,830 | 17,303,640 | 18,124,190 | 51 | 35,427,830 | 36,427,830 | 34,427,830 | 32,427,830 | 32,427,830 | 397,078,610 |
| Service charges - sanitation revenue | 1,804,240 | 2,015 | 1,509,830 | 2,887,005 | 1,736,902 | 1,999,000 | 1,511,554 | 487,446 | 24 | 1,800,000 | 2,137,000 | 2,137,000 | 2,237,000 | 2,137,000 | 25,650,560 |
| Service charges - refuse | 2,361,608 | 2,601 | 1,969,898 | 3,966,191 | 2,135,892 | 1,400,000 | 1,794,385 | -394,385 | -28 | 1,979,000 | 1,979,000 | 2,479,000 | 1,979,000 | 1,979,000 | 23,752,330 |
| Rental of facilities and equipment | 452,806 | 910 | 49,899 | 446,505 | 449,451 | 547,250 | 82,412 | 464,838 | 85 | 547,250 | 547,250 | 547,250 | 547,250 | 547,250 | 6,566,910 |
| Interest earned - external investments | 0 | 439 | 33,596 | 468,407 | 125,980 | 250,000 | 109,315 | 140,685 | 56 | 150,000 | 75,000 | 200,000 | 150,000 | 90,000 | 1,500,000 |
| Interest earned - outstanding debtors | 279,640 | 405 | 334,701 | 246,529 | 381,408 | 2,508,000 | 327,452 | 2,180,548 | 87 | 2,508,000 | 2,608,000 | 2,558,000 | 2,570,000 | 2,508,000 | 30,104,100 |
| Dividends received | 0 | – | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Fines, penalties and forfeits | 18,908 | 83 | 126,285 | 54,382 | 73,560 | 276,000 | 98,490 | 177,510 | 64 | 276,000 | 276,000 | 276,000 | 276,000 | 276,000 | 3,320,100 |
| Licences and permits | 0 | – | 0 | 0 | 0 | 17,580 | 0 | 17,580 | 100 | 17,580 | 17,580 | 17,580 | 17,580 | 17,580 | 210,930 |
| Agency services |  |  |  |  |  |  | 0 | 0 | 0 |  |  |  |  |  |  |
| Transfer receipts - operating | 76,277,000 | 2,525 | 0 | 0 | 0 | 54,919,200 | 52,660,000 | 2,259,200 | 4 | 196,020 | 196,020 | 36,612,800 | 196,020 | 196,020 | 189,039,000 |
| Other revenue | 697,828 | 13,486 | 6,493,089 | 5,020,945 | 49,301,282 | 1,020,250 | 7,755,560 | -6,735,310 | -660 | 1,020,250 | 1,020,250 | 1,020,250 | 1,020,250 | 1,020,250 | 12,163,450 |
| Cash Receipts by Source | 142,619,661 | 103,101,552 | 53,343,807 | 100,821,266 | 107,123,770 | 131,004,530 | 110,089,376 | 20,915,154 |  | 72,561,350 | 76,923,350 | 118,915,130 | 81,060,350 | 81,838,350 | 1,140,455,700 |
| Other Cash Flows by Source |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Transfer receipts - capital | 25,813,370 | 2,680 | 0 |  | 0 |  | 12,585,000 | -12,585,000 | 100 |  | 35,000,000 | 19,700,000 | 0 | 0 | 177,269,000 |
| Contributions & Contributed assets |  |  |  |  | 0 |  |  | 0 | 0 |  |  |  |  |  |  |
| Proceeds on disposal of PPE | 0 | – | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Short term loans | 0 | – | 0 |  | 0 | 15,692,000 |  | 15,692,000 | 100 | 0 | 0 | 0 | 0 | 0 | 21,692,450 |
| Borrowing long term/refinancing | 0 | – | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 16,000,000 | 0 | 0 | 37,709,000 |
| Increase in consumer deposits | 172,797 | 240 | 202,103 | 137,844 | 207,988 | -33,000 | 142,284 | -175,284 | 531 | -30,000 | -30,000 | -33,000 | -33,000 | -33,000 | -400,000 |
| Receipt of non-current debtors | 0 | – | 0 |  | 0 | 200,000 |  | 200,000 | 100 | 250,000 | 200,000 | 500,000 | 200,000 | 300,000 | 8,050,000 |
| Receipt of non-current receivables | 0 | – | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Change in non-current investments |  |  |  |  | 0 |  |  | 0 | 0 |  |  |  |  |  |  |
| Total Cash Receipts by Source | 168,605,828 | 106,021,580 | 53,545,910 | 100,959,110 | 107,331,758 | 146,863,530 | 122,816,660 | 24,046,870 |  | 72,781,350 | 112,093,350 | 155,082,130 | 81,227,350 | 82,105,350 | 1,384,776,150 |
| Cash Payments by Type |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Employee related costs | 24,119,406 | 23,984 | 25,411,384 | 24,991,016 | 28,204,766 | 28,992,000 | 25,283,995 | 3,708,005 | 13 | 28,992,000 | 30,992,000 | 30,992,000 | 30,992,000 | 31,992,000 | 350,931,390 |
| Remuneration of councillors | 1,558,839 | 1,559 | 1,558,839 | 1,558,839 | 1,558,839 | 1,591,920 | 1,558,839 | 33,081 | 2 | 1,591,920 | 1,591,920 | 1,591,920 | 1,591,920 | 1,591,920 | 19,855,440 |
| Interest paid | 0 | 41 | 57,238 | 207,846 | 109,959 | 1,500,000 | 198,870 | 1,301,130 | 87 | 200,000 | 200,000 | 20,000 | 200,000 | 200,000 | 6,448,030 |
| Bulk purchases - Electricity | 30,792,980 | 40,165 | 34,608,720 | 21,525,160 | 21,311,100 | 19,000,000 | 20,596,280 | -1,596,280 | -8 | 19,000,000 | 20,004,330 | 20,004,330 | 20,004,330 | 20,004,330 | 287,044,840 |
| Bulk purchases - Water & Sewer | 16,288,950 | 17,739 | 17,698,278 | 16,275,760 | 19,230,260 | 20,289,000 | 30,454,753 | -10,165,753 | -50 | 17,289,000 | 16,589,000 | 15,889,000 | 15,789,000 | 14,999,000 | 191,961,780 |
| Other materials | 223,087 | 1,042 | 1,213,379 | 2,171,180 | 1,139,702 | 2,348,500 | 2,134,735 | 213,765 | 9 | 2,348,500 | 2,348,500 | 2,348,500 | 2,348,500 | 2,348,500 | 32,941,245 |
| Contracted services | 1,971,769 | 6,059 | 3,150,560 | 8,076,127 | 4,196,669 | 9,558,420 | 785,703 | 8,772,717 | 92 | 9,558,420 | 9,558,420 | 9,558,420 | 9,558,420 | 9,558,420 | 110,421,000 |
| Grants and subsidies paid - other municipalities | 0 | – | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Grants and subsidies paid - other | 0 | – | 0 | 0 | 0 | 10,000 |  | 10,000 | 100 | 0 | 0 | 10,000 | 0 | 0 | 42,020 |
| General expenses | 13,512,339 | 17,243 | 25,261,980 | 14,253,002 | 23,602,635 | 5,537,000 | 18,839,391 | -13,302,391 | -240 | 5,537,000 | 6,037,000 | 6,537,000 | 7,237,000 | 7,007,000 | 66,447,520 |
| Cash Payments by Type | 88,467,370 | 107,832,630 | 108,960,378 | 89,058,930 | 99,353,930 | 88,826,840 | 99,852,566 | -11,025,726 |  | 84,516,840 | 87,321,170 | 86,951,170 | 87,721,170 | 87,701,170 | 1,066,093,265 |
| Other Cash Flows/Payments by Type |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Capital assets | 0 |  | 0 | 0 | 0 | 30,600,000 | 10,003,272 | 0 | 0 | 24,000,000 | 24,000,000 | 40,000,000 | 27,000,000 | 29,500,000 | 294,517,100 |
| Repayment of borrowing | 0 |  | 0 | 0 | 0 | 942,000 | 1,351,562 | 0 | 0 | 541,898 | 541,898 | 541,898 | 541,898 | 541,898 | 8,642,396 |
| Other Cash Flows/Payments | 64,793,571 | 3,478 | 1,404,611 | -17,452,894 | -1,024,557 | 0 | 1,705,346 | -17,452,894 | 0 | 3,000,000 | 0 | 0 | 0 | 0 | 16,762,000 |
| Total Cash Payments by Type | 153,260,941 | 111,310,453 | 110,364,989 | 71,606,036 | 98,329,373 | 120,368,840 | 112,912,746 | -28,478,620 | -24 | 112,058,738 | 111,863,068 | 127,493,068 | 115,263,068 | 117,743,068 | 1,386,014,761 |
| NET INCREASE/(DECREASE) IN CASH HELD | 15,344,887 | -5,288,873 | -56,819,079 | 29,353,074 | 9,002,385 | 26,494,690 | 9,903,914 | 52,525,490 | 246 | -39,277,388 | 230,282 | 27,589,062 | -34,035,718 | -35,637,718 | -1,238,611 |
| Cash/cash equivalents at the month/year beginning: | 35,419,000 | 50,763,887 | 45,475,014 | -11,344,065 | 18,009,009 | 124,196,300 | 27,011,394 | 121,161,437 | 98 | 150,690,990 | 111,413,602 | 111,643,884 | 139,232,946 | 105,197,228 | 35,419,000 |
| Cash/cash equivalents at the month/year end: | 50,763,887 | 45,475,014 | -11,344,065 | 18,009,009 | 27,011,394 | 150,690,990 | 36,915,308 | 173,686,927 | 124 | 111,413,602 | 111,643,884 | 139,232,946 | 105,197,228 | 69,559,510 | 34,180,389 |

- Capital programme performance

| FS204 Metsimaholo - Supporting Table SC13a Monthly Budget Statement - capital expenditure on new assets by asset class - M06 December |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description | Ref | 2018/19 | Budget Year 2019/20 |  |  |  |  |  |  |  |
|  |  | Audited Outcome | Original Budget | Adjusted Budget | Monthly actual | YearTD actual | YearTD budget | YTD variance | YTD variance | Full Year Forecast |
| R thousands | 1 |  |  |  |  |  |  |  | % |  |
| Capital expenditure on new assets by Asset Class/Sub-class |  |  |  |  |  |  |  |  |  |  |
| Infrastructure |  | 97 638 | 181 686 | 181 686 | 8 736 | 26 493 | 90 843 | 64 350 | 70,8% | 181 686 |
| Roads Infrastructure |  | 20 101 | 9 501 | 9 501 | – | 1 761 | 4 750 | 2 989 | 62,9% | 9 501 |
| Roads |  | 20 101 | 4 808 | 4 808 | – | 1 503 | 2 404 | 901 | 37,5% | 4 808 |
| Road Structures |  | – | – | – | – | – | – | – |  | – |
| Road Furniture |  | – | 4 693 | 4 693 | – | 258 | 2 346 | 2 088 | 89,0% | 4 693 |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Storm water Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Drainage Collection |  |  |  |  |  |  |  | – |  |  |
| Storm water Conveyance |  |  |  |  |  |  |  | – |  |  |
| Attenuation |  |  |  |  |  |  |  | – |  |  |
| Electrical Infrastructure |  | 13 692 | 18 216 | 18 216 | 2 975 | 3 389 | 9 108 | 5 719 | 62,8% | 18 216 |
| Power Plants |  |  |  |  |  |  |  | – |  |  |
| HV Substations |  | – | – | – | – | – | – | – |  | – |
| HV Switching Station |  |  |  |  |  |  |  | – |  |  |
| HV Transmission Conductors |  |  |  |  |  |  |  | – |  |  |
| MV Substations |  | – | 150 | 150 | – | – | 75 | 75 | 100,0% | 150 |
| MV Switching Stations |  | – | – | – | – | – | – | – |  | – |
| MV Networks |  | 10 759 | 1 650 | 1 650 | – | – | 825 | 825 | 100,0% | 1 650 |
| LV Networks |  | 2 907 | 15 916 | 15 916 | 2 975 | 3 389 | 7 958 | 4 569 | 57,4% | 15 916 |
| Capital Spares |  | 26 | 500 | 500 | – | – | 250 | 250 | 100,0% | 500 |
| Water Supply Infrastructure |  | 8 696 | 9 593 | 9 593 | 332 | 4 489 | 4 797 | 307 | 6,4% | 9 593 |
| Dams and Weirs |  |  |  |  |  |  |  | – |  |  |
| Boreholes |  |  |  |  |  |  |  | – |  |  |
| Reservoirs |  |  |  |  |  |  |  | – |  |  |
| Pump Stations |  |  |  |  |  |  |  | – |  |  |
| Water Treatment Works |  | 8 696 | 9 593 | 9 593 | 332 | 4 489 | 4 797 | 307 | 6,4% | 9 593 |
| Bulk Mains |  |  |  |  |  |  |  | – |  |  |
| Distribution |  | – | – | – | – | – | – | – |  | – |
| Distribution Points |  |  |  |  |  |  |  | – |  |  |
| PRV Stations |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Sanitation Infrastructure |  | 55 149 | 144 126 | 144 126 | 5 428 | 16 853 | 72 063 | 55 210 | 76,6% | 144 126 |
| Pump Station |  |  |  |  |  |  |  | – |  |  |
| Reticulation |  | 11 057 | 31 876 | 31 876 | 2 064 | 6 741 | 15 938 | 9 197 | 57,7% | 31 876 |
| Waste Water Treatment Works |  | 34 756 | 80 000 | 80 000 | – | – | 40 000 | 40 000 | 100,0% | 80 000 |
| Outfall Sewers |  |  |  |  |  |  |  | – |  |  |
| Toilet Facilities |  | 9 336 | 32 250 | 32 250 | 3 364 | 10 112 | 16 125 | 6 013 | 37,3% | 32 250 |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Solid Waste Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Landfill Sites |  | – | – | – | – | – | – | – |  | – |
| Waste Transfer Stations |  |  |  |  |  |  |  | – |  |  |
| Waste Processing Facilities |  |  |  |  |  |  |  | – |  |  |
| Waste Drop-off Points |  |  |  |  |  |  |  | – |  |  |
| Waste Separation Facilities |  | – | – | – | – | – | – | – |  | – |
| Electricity Generation Facilities |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Rail Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Rail Lines |  |  |  |  |  |  |  | – |  |  |
| Rail Structures |  |  |  |  |  |  |  | – |  |  |
| Rail Furniture |  |  |  |  |  |  |  | – |  |  |
| Drainage Collection |  |  |  |  |  |  |  | – |  |  |
| Storm water Conveyance |  |  |  |  |  |  |  | – |  |  |
| Attenuation |  |  |  |  |  |  |  | – |  |  |
| MV Substations |  |  |  |  |  |  |  | – |  |  |
| LV Networks |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Coastal Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Sand Pumps |  |  |  |  |  |  |  | – |  |  |
| Piers |  |  |  |  |  |  |  | – |  |  |
| Revetments |  |  |  |  |  |  |  | – |  |  |
| Promenades |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Information and Communication Infrastructure |  | – | 250 | 250 | – | – | 125 | 125 | 100,0% | 250 |
| Data Centres |  |  |  |  |  |  |  | – |  |  |
| Core Layers |  |  |  |  |  |  |  | – |  |  |
| Distribution Layers |  | – | 250 | 250 | – | – | 125 | 125 | 100,0% | 250 |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Community Assets |  | 625 | 17 049 | 17 049 | 1 264 | 1 264 | 8 524 | 7 260 | 85,2% | 17 049 |
| Community Facilities |  | 621 | 17 005 | 17 005 | 1 264 | 1 264 | 8 503 | 7 238 | 85,1% | 17 005 |
| Halls |  | – | – | – | – | – | – | – |  | – |
| Centres |  |  |  |  |  |  |  | – |  |  |
| Crèches |  |  |  |  |  |  |  | – |  |  |
| Clinics/Care Centres |  |  |  |  |  |  |  | – |  |  |
| Fire/Ambulance Stations |  | – | – | – | – | – | – | – |  | – |
| Testing Stations |  |  |  |  |  |  |  | – |  |  |
| Museums |  |  |  |  |  |  |  | – |  |  |
| Galleries |  |  |  |  |  |  |  | – |  |  |
| Theatres |  |  |  |  |  |  |  | – |  |  |
| Libraries |  |  |  |  |  |  |  | – |  |  |
| Cemeteries/Crematoria |  | – | 470 | 470 | – | – | 235 | 235 | 100,0% | 470 |
| Police |  |  |  |  |  |  |  | – |  |  |
| Purls |  | – | – | – | – | – | – | – |  | – |
| Public Open Space |  | 621 | 16 535 | 16 535 | 1 264 | 1 264 | 8 268 | 7 003 | 84,7% | 16 535 |
| Nature Reserves |  |  |  |  |  |  |  | – |  |  |
| Public Ablution Facilities |  |  |  |  |  |  |  | – |  |  |
| Markets |  |  |  |  |  |  |  | – |  |  |
| Stalls |  | – | – | – | – | – | – | – |  | – |
| Abattoirs |  |  |  |  |  |  |  | – |  |  |
| Airports |  |  |  |  |  |  |  | – |  |  |
| Taxi Ranks/Bus Terminals |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Sport and Recreation Facilities |  | 4 | 44 | 44 | – | – | 22 | 22 | 100,0% | 44 |
| Indoor Facilities |  |  |  |  |  |  |  | – |  |  |
| Outdoor Facilities |  | 4 | 44 | 44 | – | – | 22 | 22 | 100,0% | 44 |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Heritage assets |  | – | – | – | – | – | – | – |  | – |
| Monuments |  |  |  |  |  |  |  | – |  |  |
| Historic Buildings |  |  |  |  |  |  |  | – |  |  |
| Works of Art |  |  |  |  |  |  |  | – |  |  |
| Conservation Areas |  |  |  |  |  |  |  | – |  |  |
| Other Heritage |  |  |  |  |  |  |  | – |  |  |
|  |  |  |  |  |  |  |  | – |  |  |
| Investment properties |  | – | – | – | – | – | – | – |  | – |
| Revenue Generating |  | – | – | – | – | – | – | – |  | – |
| Improved Property |  |  |  |  |  |  |  | – |  |  |
| Unimproved Property |  |  |  |  |  |  |  | – |  |  |
| Non-revenue Generating |  | – | – | – | – | – | – | – |  | – |
| Improved Property |  |  |  |  |  |  |  | – |  |  |
| Unimproved Property |  |  |  |  |  |  |  | – |  |  |
| Other assets |  | – | 3 800 | 3 800 | – | – | 1 900 | 1 900 | 100,0% | 3 800 |
| Operational Buildings |  | – | 3 800 | 3 800 | – | – | 1 900 | 1 900 | 100,0% | 3 800 |
| Municipal Offices |  | – | 300 | 300 | – | – | 150 | 150 | 100,0% | 300 |
| Pay/Enquiry Points |  |  |  |  |  |  |  | – |  |  |
| Building Plan Offices |  |  |  |  |  |  |  | – |  |  |
| Workshops |  |  |  |  |  |  |  | – |  |  |
| Yards |  |  |  |  |  |  |  | – |  |  |
| Stores |  |  |  |  |  |  |  | – |  |  |
| Laboratories |  |  |  |  |  |  |  | – |  |  |
| Training Centres |  |  |  |  |  |  |  | – |  |  |
| Manufacturing Plant |  |  |  |  |  |  |  | – |  |  |
| Depots |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  | – | 3 500 | 3 500 | – | – | 1 750 | 1 750 | 100,0% | 3 500 |
| Housing |  | – | – | – | – | – | – | – |  | – |
| Staff Housing |  |  |  |  |  |  |  | – |  |  |
| Social Housing |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Biological or Cultivated Assets |  | – | – | – | – | – | – | – |  | – |
| Biological or Cultivated Assets |  |  |  |  |  |  |  | – |  |  |
| Intangible Assets |  | – | 1 400 | 1 400 | – | – | 700 | 700 | 100,0% | 1 400 |
| Servitudes |  |  |  |  |  |  |  | – |  |  |
| Licences and Rights |  | – | 1 400 | 1 400 | – | – | 700 | 700 | 100,0% | 1 400 |
| Water Rights |  |  |  |  |  |  |  | – |  |  |
| Effluent Licenses |  |  |  |  |  |  |  | – |  |  |
| Solid Waste Licenses |  |  |  |  |  |  |  | – |  |  |
| Computer Software and Applications |  | – | 1 400 | 1 400 | – | – | 700 | 700 | 100,0% | 1 400 |
| Load Settlement Software Applications |  |  |  |  |  |  |  | – |  |  |
| Unspecified |  |  |  |  |  |  |  | – |  |  |
| Computer Equipment |  | 310 | 1 330 | 1 330 | – | 75 | 665 | 590 | 88,8% | 1 330 |
| Computer Equipment |  | 310 | 1 330 | 1 330 | – | 75 | 665 | 590 | 88,8% | 1 330 |
| Furniture and Office Equipment |  | 164 | 2 636 | 2 636 | 3 | 11 | 1 318 | 1 307 | 99,2% | 2 636 |
| Furniture and Office Equipment |  | 164 | 2 636 | 2 636 | 3 | 11 | 1 318 | 1 307 | 99,2% | 2 636 |
| Machinery and Equipment |  | 2 449 | 1 479 | 1 479 | – | 211 | 740 | 529 | 71,5% | 1 479 |
| Machinery and Equipment |  | 2 449 | 1 479 | 1 479 | – | 211 | 740 | 529 | 71,5% | 1 479 |
| Transport Assets |  | 8 606 | 17 548 | 17 548 | – | – | 8 774 | 8 774 | 100,0% | 17 548 |
| Transport Assets |  | 8 606 | 17 548 | 17 548 | – | – | 8 774 | 8 774 | 100,0% | 17 548 |
| Land |  | – | – | – | – | – | – | – |  | – |
| Land |  |  |  |  |  |  |  | – |  |  |
| Zoo's, Marine and Non-biological Animals |  | – | – | – | – | – | – | – |  | – |
| Zoo's, Marine and Non-biological Animals |  |  |  |  |  |  |  | – |  |  |
| Total Capital Expenditure on new assets | 1 | 109 792 | 226 928 | 226 928 | 10 003 | 28 053 | 113 464 | 85 411 | 75,3% | 226 928 |

| FS204 Metsimaholo - Supporting Table SC13b Monthly Budget Statement - capital expenditure on renewal of existing assets by asset class - M06 December |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description | Ref | 2018/19 | Budget Year 2019/20 |  |  |  |  |  |  |  |
|  |  | Audited Outcome | Original Budget | Adjusted Budget | Monthly actual | YearTD actual | YearTD budget | YTD variance | YTD variance | Full Year Forecast |
| R thousands | 1 |  |  |  |  |  |  |  | % |  |
| Capital expenditure on renewal of existing assets by Asset Class/Sub-class |  |  |  |  |  |  |  |  |  |  |
| Infrastructure |  | 7 461 | 58 604 | 58 604 | – | 190 | 29 302 | 29 112 | 99,3% | 58 604 |
| Roads Infrastructure |  | – | 42 000 | 42 000 | – | – | 21 000 | 21 000 | 100,0% | 42 000 |
| Roads |  | – | 42 000 | 42 000 | – | – | 21 000 | 21 000 | 100,0% | 42 000 |
| Road Structures |  |  |  |  |  |  |  | – |  |  |
| Road Furniture |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Storm water Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Drainage Collection |  |  |  |  |  |  |  | – |  |  |
| Storm water Conveyance |  |  |  |  |  |  |  | – |  |  |
| Attenuation |  |  |  |  |  |  |  | – |  |  |
| Electrical Infrastructure |  | 7 461 | 13 600 | 13 600 | – | – | 6 800 | 6 800 | 100,0% | 13 600 |
| Power Plants |  |  |  |  |  |  |  | – |  |  |
| HV Substations |  |  |  |  |  |  |  | – |  |  |
| HV Switching Station |  |  |  |  |  |  |  | – |  |  |
| HV Transmission Conductors |  |  |  |  |  |  |  | – |  |  |
| MV Substations |  |  |  |  |  |  |  | – |  |  |
| MV Switching Stations |  |  |  |  |  |  |  | – |  |  |
| MV Networks |  | 7 461 | – | – | – | – | – | – |  | – |
| LV Networks |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  | – | 13 600 | 13 600 | – | – | 6 800 | 6 800 | 100,0% | 13 600 |
| Water Supply Infrastructure |  | – | 3 000 | 2 950 | – | 190 | 1 493 | 1 302 | 87,2% | 2 950 |
| Dams and Weirs |  |  |  |  |  |  |  | – |  |  |
| Boreholes |  |  |  |  |  |  |  | – |  |  |
| Reservoirs |  | – | – | – | – | – | – | – |  | – |
| Pump Stations |  |  |  |  |  |  |  | – |  |  |
| Water Treatment Works |  | – | 1 300 | 1 250 | – | 49 | 643 | 594 | 92,3% | 1 250 |
| Bulk Mains |  |  |  |  |  |  |  | – |  |  |
| Distribution |  |  |  |  |  |  |  | – |  |  |
| Distribution Points |  |  |  |  |  |  |  | – |  |  |
| PRV Stations |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  | – | 1 700 | 1 700 | – | 141 | 850 | 709 | 83,4% | 1 700 |
| Sanitation Infrastructure |  | – | 4 | 54 | – | – | 9 | 9 | 100,0% | 54 |
| Pump Station |  | – | 4 | 4 | – | – | 2 | 2 | 100,0% | 4 |
| Reticulation |  |  |  |  |  |  |  | – |  |  |
| Waste Water Treatment Works |  | – | – | – | – | – | – | – |  | – |
| Outfall Sewers |  |  |  |  |  |  |  | – |  |  |
| Toilet Facilities |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  | – | – | 50 | – | – | 7 | 7 | 100,0% | 50 |
| Solid Waste Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Landfill Sites |  |  |  |  |  |  |  | – |  |  |
| Waste Transfer Stations |  |  |  |  |  |  |  | – |  |  |
| Waste Processing Facilities |  |  |  |  |  |  |  | – |  |  |
| Waste Drop-off Points |  |  |  |  |  |  |  | – |  |  |
| Waste Separation Facilities |  |  |  |  |  |  |  | – |  |  |
| Electricity Generation Facilities |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Rail Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Rail Lines |  |  |  |  |  |  |  | – |  |  |
| Rail Structures |  |  |  |  |  |  |  | – |  |  |
| Rail Furniture |  |  |  |  |  |  |  | – |  |  |
| Drainage Collection |  |  |  |  |  |  |  | – |  |  |
| Storm water Conveyance |  |  |  |  |  |  |  | – |  |  |
| Attenuation |  |  |  |  |  |  |  | – |  |  |
| MV Substations |  |  |  |  |  |  |  | – |  |  |
| LV Networks |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Coastal Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Sand Pumps |  |  |  |  |  |  |  | – |  |  |
| Piers |  |  |  |  |  |  |  | – |  |  |
| Revetments |  |  |  |  |  |  |  | – |  |  |
| Promenades |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Information and Communication Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Data Centres |  |  |  |  |  |  |  | – |  |  |
| Core Layers |  |  |  |  |  |  |  | – |  |  |
| Distribution Layers |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Community Assets |  | – | 2 983 | 2 983 | – | – | 1 492 | 1 492 | 100,0% | 2 983 |
| Community Facilities |  | – | 2 983 | 2 983 | – | – | 1 492 | 1 492 | 100,0% | 2 983 |
| Halls |  |  |  |  |  |  |  | – |  |  |
| Centres |  |  |  |  |  |  |  | – |  |  |
| Crèches |  |  |  |  |  |  |  | – |  |  |
| Clinics/Care Centres |  |  |  |  |  |  |  | – |  |  |
| Fire/Ambulance Stations |  | – | – | – | – | – | – | – |  | – |
| Testing Stations |  |  |  |  |  |  |  | – |  |  |
| Museums |  |  |  |  |  |  |  | – |  |  |
| Galleries |  |  |  |  |  |  |  | – |  |  |
| Theatres |  |  |  |  |  |  |  | – |  |  |
| Libraries |  |  |  |  |  |  |  | – |  |  |
| Cemeteries/Crematoria |  | – | 1 233 | 1 233 | – | – | 617 | 617 | 100,0% | 1 233 |
| Police |  |  |  |  |  |  |  | – |  |  |
| Purls |  |  |  |  |  |  |  | – |  |  |
| Public Open Space |  | – | 1 750 | 1 750 | – | – | 875 | 875 | 100,0% | 1 750 |
| Nature Reserves |  |  |  |  |  |  |  | – |  |  |
| Public Ablution Facilities |  | – | – | – | – | – | – | – |  | – |
| Markets |  |  |  |  |  |  |  | – |  |  |
| Stalls |  |  |  |  |  |  |  | – |  |  |
| Abattoirs |  |  |  |  |  |  |  | – |  |  |
| Airports |  |  |  |  |  |  |  | – |  |  |
| Taxi Ranks/Bus Terminals |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Sport and Recreation Facilities |  | – | – | – | – | – | – | – |  | – |
| Indoor Facilities |  |  |  |  |  |  |  | – |  |  |
| Outdoor Facilities |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Heritage assets |  | – | – | – | – | – | – | – |  | – |
| Monuments |  |  |  |  |  |  |  | – |  |  |
| Historic Buildings |  |  |  |  |  |  |  | – |  |  |
| Works of Art |  |  |  |  |  |  |  | – |  |  |
| Conservation Areas |  |  |  |  |  |  |  | – |  |  |
| Other Heritage |  |  |  |  |  |  |  | – |  |  |
|  |  |  |  |  |  |  |  | – |  |  |
| Investment properties |  | – | – | – | – | – | – | – |  | – |
| Revenue Generating |  | – | – | – | – | – | – | – |  | – |
| Improved Property |  |  |  |  |  |  |  | – |  |  |
| Unimproved Property |  |  |  |  |  |  |  | – |  |  |
| Non-revenue Generating |  | – | – | – | – | – | – | – |  | – |
| Improved Property |  |  |  |  |  |  |  | – |  |  |
| Unimproved Property |  |  |  |  |  |  |  | – |  |  |
| Other assets |  | – | 200 | 100 | – | – | 50 | 50 | 100,0% | 100 |
| Operational Buildings |  | – | 200 | 100 | – | – | 50 | 50 | 100,0% | 100 |
| Municipal Offices |  | – | 200 | 100 | – | – | 50 | 50 | 100,0% | 100 |
| Pay/Enquiry Points |  |  |  |  |  |  |  | – |  |  |
| Building Plan Offices |  |  |  |  |  |  |  | – |  |  |
| Workshops |  |  |  |  |  |  |  | – |  |  |
| Yards |  |  |  |  |  |  |  | – |  |  |
| Stores |  |  |  |  |  |  |  | – |  |  |
| Laboratories |  |  |  |  |  |  |  | – |  |  |
| Training Centres |  |  |  |  |  |  |  | – |  |  |
| Manufacturing Plant |  |  |  |  |  |  |  | – |  |  |
| Depots |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Housing |  | – | – | – | – | – | – | – |  | – |
| Staff Housing |  |  |  |  |  |  |  | – |  |  |
| Social Housing |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Biological or Cultivated Assets |  | – | – | – | – | – | – | – |  | – |
| Biological or Cultivated Assets |  |  |  |  |  |  |  | – |  |  |
| Intangible Assets |  | – | 1 200 | 1 200 | – | 332 | 600 | 268 | 44,6% | 1 200 |
| Servitudes |  |  |  |  |  |  |  | – |  |  |
| Licences and Rights |  | – | 1 200 | 1 200 | – | 332 | 600 | 268 | 44,6% | 1 200 |
| Water Rights |  |  |  |  |  |  |  | – |  |  |
| Effluent Licenses |  |  |  |  |  |  |  | – |  |  |
| Solid Waste Licenses |  |  |  |  |  |  |  | – |  |  |
| Computer Software and Applications |  | – | 1 200 | 1 200 | – | 332 | 600 | 268 | 44,6% | 1 200 |
| Load Settlement Software Applications |  |  |  |  |  |  |  | – |  |  |
| Unspecified |  |  |  |  |  |  |  | – |  |  |
| Computer Equipment |  | 85 | 200 | 200 | – | – | 100 | 100 | 100,0% | 200 |
| Computer Equipment |  | 85 | 200 | 200 | – | – | 100 | 100 | 100,0% | 200 |
| Furniture and Office Equipment |  | – | 966 | 816 | – | – | 446 | 446 | 100,0% | 816 |
| Furniture and Office Equipment |  | – | 966 | 816 | – | – | 446 | 446 | 100,0% | 816 |
| Machinery and Equipment |  | – | 521 | 771 | – | – | 348 | 348 | 100,0% | 771 |
| Machinery and Equipment |  | – | 521 | 771 | – | – | 348 | 348 | 100,0% | 771 |
| Transport Assets |  | – | 715 | 715 | – | – | 358 | 358 | 100,0% | 715 |
| Transport Assets |  | – | 715 | 715 | – | – | 358 | 358 | 100,0% | 715 |
| Land |  | – | – | – | – | – | – | – |  | – |
| Land |  |  |  |  |  |  |  | – |  |  |
|  |  |  |  |  |  |  |  |  | . |  |
| Zoo's, Marine and Non-biological Animals |  | – | – | – | – | – | – | – |  | – |
| Zoo's, Marine and Non-biological Animals |  |  |  |  |  |  |  | – |  |  |
| Total Capital Expenditure on renewal of existing assets | 1 | 7 546 | 65 389 | 65 389 | – | 523 | 32 695 | 32 172 | 98,4% | 65 389 |

| FS204 Metsimaholo - Supporting Table SC13e Monthly Budget Statement - capital expenditure on upgrading of existing assets by asset class - M06 December |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description | Ref | 2018/19 | Budget Year 2019/20 |  |  |  |  |  |  |  |
|  |  | Audited Outcome | Original Budget | Adjusted Budget | Monthly actual | YearTD actual | YearTD budget | YTD variance | YTD variance | Full Year Forecast |
| R thousands | 1 |  |  |  |  |  |  |  | % |  |
| Capital expenditure on upgrading of existing assets by Asset Class/Sub-class |  |  |  |  |  |  |  |  |  |  |
| Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Roads Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Roads |  |  |  |  |  |  |  | – |  |  |
| Road Structures |  |  |  |  |  |  |  | – |  |  |
| Road Furniture |  | – | – | – | – | – | – | – |  | – |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Storm water Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Drainage Collection |  |  |  |  |  |  |  | – |  |  |
| Storm water Conveyance |  |  |  |  |  |  |  | – |  |  |
| Attenuation |  |  |  |  |  |  |  | – |  |  |
| Electrical Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Power Plants |  |  |  |  |  |  |  | – |  |  |
| HV Substations |  | – | – | – | – | – | – | – |  | – |
| HV Switching Station |  |  |  |  |  |  |  | – |  |  |
| HV Transmission Conductors |  |  |  |  |  |  |  | – |  |  |
| MV Substations |  |  |  |  |  |  |  | – |  |  |
| MV Switching Stations |  |  |  |  |  |  |  | – |  |  |
| MV Networks |  |  |  |  |  |  |  | – |  |  |
| LV Networks |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Water Supply Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Dams and Weirs |  |  |  |  |  |  |  | – |  |  |
| Boreholes |  |  |  |  |  |  |  | – |  |  |
| Reservoirs |  |  |  |  |  |  |  | – |  |  |
| Pump Stations |  |  |  |  |  |  |  | – |  |  |
| Water Treatment Works |  |  |  |  |  |  |  | – |  |  |
| Bulk Mains |  |  |  |  |  |  |  | – |  |  |
| Distribution |  |  |  |  |  |  |  | – |  |  |
| Distribution Points |  |  |  |  |  |  |  | – |  |  |
| PRV Stations |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Sanitation Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Pump Station |  |  |  |  |  |  |  | – |  |  |
| Reticulation |  |  |  |  |  |  |  | – |  |  |
| Waste Water Treatment Works |  |  |  |  |  |  |  | – |  |  |
| Outfall Sewers |  |  |  |  |  |  |  | – |  |  |
| Toilet Facilities |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Solid Waste Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Landfill Sites |  |  |  |  |  |  |  | – |  |  |
| Waste Transfer Stations |  |  |  |  |  |  |  | – |  |  |
| Waste Processing Facilities |  |  |  |  |  |  |  | – |  |  |
| Waste Drop-off Points |  |  |  |  |  |  |  | – |  |  |
| Waste Separation Facilities |  |  |  |  |  |  |  | – |  |  |
| Electricity Generation Facilities |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Rail Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Rail Lines |  |  |  |  |  |  |  | – |  |  |
| Rail Structures |  |  |  |  |  |  |  | – |  |  |
| Rail Furniture |  |  |  |  |  |  |  | – |  |  |
| Drainage Collection |  |  |  |  |  |  |  | – |  |  |
| Storm water Conveyance |  |  |  |  |  |  |  | – |  |  |
| Attenuation |  |  |  |  |  |  |  | – |  |  |
| MV Substations |  |  |  |  |  |  |  | – |  |  |
| LV Networks |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Coastal Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Sand Pumps |  |  |  |  |  |  |  | – |  |  |
| Piers |  |  |  |  |  |  |  | – |  |  |
| Revetments |  |  |  |  |  |  |  | – |  |  |
| Promenades |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Information and Communication Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Data Centres |  |  |  |  |  |  |  | – |  |  |
| Core Layers |  |  |  |  |  |  |  | – |  |  |
| Distribution Layers |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Community Assets |  | – | 2 200 | 2 200 | – | – | 1 100 | 1 100 | 100,0% | 2 200 |
| Community Facilities |  | – | 2 200 | 2 200 | – | – | 1 100 | 1 100 | 100,0% | 2 200 |
| Halls |  | – | 200 | 200 | – | – | 100 | 100 | 100,0% | 200 |
| Centres |  |  |  |  |  |  |  | – |  |  |
| Crèches |  |  |  |  |  |  |  | – |  |  |
| Clinics/Care Centres |  |  |  |  |  |  |  | – |  |  |
| Fire/Ambulance Stations |  |  |  |  |  |  |  | – |  |  |
| Testing Stations |  |  |  |  |  |  |  | – |  |  |
| Museums |  |  |  |  |  |  |  | – |  |  |
| Galleries |  |  |  |  |  |  |  | – |  |  |
| Theatres |  |  |  |  |  |  |  | – |  |  |
| Libraries |  |  |  |  |  |  |  | – |  |  |
| Cemeteries/Crematoria |  |  |  |  |  |  |  | – |  |  |
| Police |  |  |  |  |  |  |  | – |  |  |
| Purls |  |  |  |  |  |  |  | – |  |  |
| Public Open Space |  | – | – | – | – | – | – | – |  | – |
| Nature Reserves |  | – | 2 000 | 2 000 | – | – | 1 000 | 1 000 | 100,0% | 2 000 |
| Public Ablution Facilities |  |  |  |  |  |  |  | – |  |  |
| Markets |  |  |  |  |  |  |  | – |  |  |
| Stalls |  |  |  |  |  |  |  | – |  |  |
| Abattoirs |  |  |  |  |  |  |  | – |  |  |
| Airports |  |  |  |  |  |  |  | – |  |  |
| Taxi Ranks/Bus Terminals |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Sport and Recreation Facilities |  | – | – | – | – | – | – | – |  | – |
| Indoor Facilities |  |  |  |  |  |  |  | – |  |  |
| Outdoor Facilities |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Heritage assets |  | – | – | – | – | – | – | – |  | – |
| Monuments |  |  |  |  |  |  |  | – |  |  |
| Historic Buildings |  |  |  |  |  |  |  | – |  |  |
| Works of Art |  |  |  |  |  |  |  | – |  |  |
| Conservation Areas |  |  |  |  |  |  |  | – |  |  |
| Other Heritage |  |  |  |  |  |  |  | – |  |  |
|  |  |  |  |  |  |  |  | – |  |  |
| Investment properties |  | – | – | – | – | – | – | – |  | – |
| Revenue Generating |  | – | – | – | – | – | – | – |  | – |
| Improved Property |  |  |  |  |  |  |  | – |  |  |
| Unimproved Property |  |  |  |  |  |  |  | – |  |  |
| Non-revenue Generating |  | – | – | – | – | – | – | – |  | – |
| Improved Property |  |  |  |  |  |  |  | – |  |  |
| Unimproved Property |  |  |  |  |  |  |  | – |  |  |
| Other assets |  | – | – | – | – | – | – | – |  | – |
| Operational Buildings |  | – | – | – | – | – | – | – |  | – |
| Municipal Offices |  |  |  |  |  |  |  | – |  |  |
| Pay/Enquiry Points |  |  |  |  |  |  |  | – |  |  |
| Building Plan Offices |  |  |  |  |  |  |  | – |  |  |
| Workshops |  |  |  |  |  |  |  | – |  |  |
| Yards |  |  |  |  |  |  |  | – |  |  |
| Stores |  |  |  |  |  |  |  | – |  |  |
| Laboratories |  |  |  |  |  |  |  | – |  |  |
| Training Centres |  |  |  |  |  |  |  | – |  |  |
| Manufacturing Plant |  |  |  |  |  |  |  | – |  |  |
| Depots |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Housing |  | – | – | – | – | – | – | – |  | – |
| Staff Housing |  |  |  |  |  |  |  | – |  |  |
| Social Housing |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Biological or Cultivated Assets |  | – | – | – | – | – | – | – |  | – |
| Biological or Cultivated Assets |  |  |  |  |  |  |  | – |  |  |
| Intangible Assets |  | – | – | – | – | – | – | – |  | – |
| Servitudes |  |  |  |  |  |  |  | – |  |  |
| Licences and Rights |  | – | – | – | – | – | – | – |  | – |
| Water Rights |  |  |  |  |  |  |  | – |  |  |
| Effluent Licenses |  |  |  |  |  |  |  | – |  |  |
| Solid Waste Licenses |  |  |  |  |  |  |  | – |  |  |
| Computer Software and Applications |  | – | – | – | – | – | – | – |  | – |
| Load Settlement Software Applications |  |  |  |  |  |  |  | – |  |  |
| Unspecified |  |  |  |  |  |  |  | – |  |  |
| Computer Equipment |  | – | – | – | – | – | – | – |  | – |
| Computer Equipment |  |  |  |  |  |  |  | – |  |  |
| Furniture and Office Equipment |  | – | – | – | – | – | – | – |  | – |
| Furniture and Office Equipment |  |  |  |  |  |  |  | – |  |  |
| Machinery and Equipment |  | – | – | – | – | – | – | – |  | – |
| Machinery and Equipment |  |  |  |  |  |  |  | – |  |  |
| Transport Assets |  | – | – | – | – | – | – | – |  | – |
| Transport Assets |  |  |  |  |  |  |  | – |  |  |
| Land |  | – | – | – | – | – | – | – |  | – |
| Land |  |  |  |  |  |  |  | – |  |  |
|  |  |  |  |  |  |  |  |  | . |  |
| Zoo's, Marine and Non-biological Animals |  | – | – | – | – | – | – | – |  | – |
| Zoo's, Marine and Non-biological Animals |  |  |  |  |  |  |  | – |  |  |
| Total Capital Expenditure on upgrading of existing assets | 1 | – | 2 200 | 2 200 | – | – | 1 100 | 1 100 | 100,0% | 2 200 |

Capital expenditure for December 2019 is R10 003 272

13. Quality Report

# Quality Certificate

I, T Manele, acting Municipal Manager of Metsimaholo Local Municipality, hereby certify that the monthly budget statement for the month of December 2019 has been prepared in accordance with the Municipal Finance Management Act and the regulations made under the Act.

......................................

# T Manele

# Acting Municipal Manager of

# Metsimaholo Local Municipality, FS 204

11/02/2020

(SIGNED COPY IS SENT TO NATIONAL TREASURY)