Department: Financial services

# Metsimaholo Local Municipality

2019/2020 Schedule C

October 2019

1. Table of Contents

| No. | Section Description | Page No. |
| --- | --- | --- |
| 1 | Table of Contents | 2 |
|  | Part 1 In - Year Report |  |
| 2 | Mayor’s Report | 3 |
| 3 | Resolutions | 4 |
| 4 | Executive Summary | 5 |
| 5 | In-Year budget statement tables | 28 |
|  | Supporting Documentation |  |
| 6 | Debtors’ Analysis | 38 |
| 7 | Creditors’ Analysis | 39 |
| 8 | Investment Portfolio analysis | 40 |
| 9 | Allocation and grant receipts and expenditure | 41 |
| 10 | Councillor allowances and employee benefits | 43 |
| 11 | Material variances to the service delivery and budget implementation plan | 44 |
| 12 | Capital programme performance | 57 |
| 13 | Quality Certificate | 67 |

2.	Report of the Executive Mayor

  - Council approved the 2019/2020 MTREF on 29 May 2019.

  - The information provided to the Executive Mayor is in compliance with Section 71 of the Local Government: Municipal Finance Management Act 56 of 2003. (MFMA).

  - This monthly report is referred to as the Section 71 Report or the Schedule C Report for ease of reference.

  - The report format is a standard template issued by National Treasury to all municipalities for completion and all the necessary information required to be reported on in terms of Section 71 is in included in the report.

  - In terms of Section 71, the Accounting Officer must by no later than 10 working days after the end of each month submit to the mayor and the relevant provincial treasury the monthly Section 71 (Schedule C) report.

  - The Executive Mayor also hereby confirms having received the monthly report timeously from the Accounting Officer.

3.	Resolutions

- That the monthly budget statement and supporting documentation for the month of October 2019 be noted.

# 4.	Executive Summary

The in-year reporting is prepared in accordance with the guidelines as set out in the Government Gazette, 17 April 2009 (Schedule C: in-year reports and mid-year budget and performance assessment of Municipalities) and National Treasury Guidelines, Schedule C. Section 71 Reporting Guideline, July 2013 issued by National Treasury.

Key Indicators for the period under review

- Operating 	Revenue: 	represents      30.9% of budgeted revenue.

- Operating 	Expenditure:	represents      27.5% of budgeted expenditure

- Capital 	Expenditure:	 represents       5.2% of budgeted capital expenditure

- Operating Revenue for the period under review

- Revenue for the period is on average 2.4% above budget.

- The property rates on farmland is billed in July 2019 for the full year.

- The budget performance on water consumption is below target.

- Included in the revenue is the equitable share of which 41.66% of the allocation for the year has already been received and accounted for.

- Operating expenditure for the period under review

- Operating expenditure for the period is 5.8% below budget.

- Provision was made for vacancies, including filling of posts of directors, for R18m

- Depreciation will only be allocated after the audit in November 2019.

- A journal will be done for bulk purchase of water and electricity to provide for additional month, as it is paid a month later.

- Capital Expenditure

- Capital spending is 5.2% of the budget.

Capital expenditure for the year (4 months) is as follows:

- Grants spending		   4.4%

- Borrowing			   0%

- Donation			   0%

- Own funding			   1.0%

- The approved budgeted Capital Expenditure for the year is R294.5m

- Capital expenditure is to be funded from the following sources:

Current month

(October 2019)

Spending

- Own funds 		  		R  61.3m   	R592k

- Donations				R  26.2m	R0

- Borrowings				R   56.0m	R0

- Grant funds (see below)		R 151.1m   	R6.6m

- Department of Energy			R 10m		R0

- Municipal Infrastructure Grant		R 49.1m	R4.4m

- Department of Water Sanitation	R 15m	 	R2.2m

- Free State Sports			R 7m		R0

- Regional Bulk Infrastructure		R 70m		R0

Total Capex budget			R 294.5m	R7.2m

- Personnel expenses

- Employee cost for the month totalled R24.99 million

- Employee costs account for: -

  - 19.6% of the current month total expenditure

  - 27.4% of the year to date total expenditure

  - 27.5% of the total personnel budget for the year. Allocation on provision for leave, bonus and other employee benefits still outstanding.

- Remuneration of councillors:

- Councillor Allowances in terms of the upper limits for October 2019 amounts to R1.6 million

- Salaries and overtime (excluding Councillors)

Normal salary				R13 954 213

Overtime 					R 1 958 995

Total						R 15 913 208

Overtime %	of normal salary		14.04% 	(Prev. month 13.16 %)

Overtime incurred is to be monitored on an on-going basis by the Technical and Social Services directorates so as to reduce overtime to 5% of normal salaries.

This has not been achieved and is being reported every month.

The schedule below is an analysis of the overtime for the period July 2019 to October 2019 per department.

| Description | YTD Movement | Political Offices | Municipal Manager | Corporate Services | Social Services | Technical Services | Financial Services | LED |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| BASIC SALARIES | 57 713 383 | 3 574 408 | 3 532 559 | 4 041 008 | 18 865 937 | 13 453 086 | 8 237 900 | 4 150 123 |
| OVERTIME | 7 090 582 | 277 777 | 21 581 | 52 274 | 3 160 838 | 3 250 315 | 316 962 | 10 836 |
| Overtime as % of salaries | 12.29 | 7.77 | 0.61 | 1.29 | 16.75 | 24.16 | 3.85 | 0.26 |

- Distribution losses

The norms are set by National Treasury as per MFMA Circular 71- Uniform Ratios and Norms (January 2014) paragraph B –Distribution losses

- The electricity distribution loss of 15.98% (Ytd.) is above the acceptable threshold.

The acceptable norm is between 7% and 10%

(The loss for the 2018/2019 financial year was 6%)

- The water distribution loss of 10.54% (Ytd.) is within the acceptable norm.

The acceptable norm is between 15% and 30%.

(The loss for the 2018/2019 financial year was 16%)

|  | Purchased | Sold | (Loss)/ Gain | (Loss)/Gain at cost |
| --- | --- | --- | --- | --- |
|  | kl/kWh | kl/kWh | % | Rand value |
| October (Month) |  |  |  |  |
| Water (Kilolitre) | 1 890 168 | 1 436 629 | (23.99) | (R4 241 425.00) |
| Electricity (kWh) | 18 530 325 | 16 614 409 | (10.34) | (R 1 076 936) |
| Year to date |  |  |  |  |
| Water (Kilolitre) | 7 247 311 | 6 483 439 | (10.54) | (R 7 570 318.92) |
| Electricity (kWh) | 76 665 844 | 64 413 818 | (15.98) | (R 10 500 092.00) |

The electricity losses are indicative of electricity theft and bridging of meters that needs to be investigated by the technical department.

Water losses also arise as a result of unmetered water at informal stands, calculated on average at 20kl per household:

- Themba Kubheka is 	50 000kl per month

- Zamdela is 		60 580kl per month.

Taking this 110 580 kl per month of unmetered water into account, the unaccounted for water loss will reduce further.

F: Current Assets - Debtors

- The debtor’s age analysis has decreased to R1.599b (Sept R1.608b)

- The age analysis will continue to grow to the extent of non-payment below 100% and by interest charged every month on the arrears.

- Credit control measures must be applied strictly throughout the municipality, regardless of the customer type, whether it be businesses, schools, hospitals, government departments or private households. This process has been intensified.

- The municipality has in place a detailed Revenue Enhancement Strategy which will be rolled out in this financial year.

  - Presentations have been made to the Senior Management and also to managers and the item also served at MAYCO and is to be discussed at the Strategic Session of the Executive Mayor.

  - A further presentation will be made to the Council in due course.

  - This workshop has been repeatedly postponed and rollout can only be in the 2019/2020 year

Payment Rates

| Average | Excluding prepaid | Including prepaid |
| --- | --- | --- |
| For the month | 76.51% | 198.41% |
| September 2019 levies received in October 2019 |  |  |
| Year to date | 67.38% | 74.62% |
| July to October levies received in September 2019 to October 2019 |  |  |

- Calculation of payment ratio

- The average payment rate is calculated by expressing as a percentage:   Payments received in the month following the month in which levies were raised, and the levies raised for the month

- This calculation does not include prepaid electricity – as the payment rate on this is 100%, by virtue of it being prepaid.

- The average payment rate can exceed 100% which indicates that arrears have also been collected.

Year to Date - Average payment rates:  (excluding prepaid electricity)

|  | LEVIES | PAYMENTS | PAYMENT- |
| --- | --- | --- | --- |
|  | R 000 | R 000 | RATE (%) |
| Sasolburg | 253 172 | 214 822 | 84.9 |
| Zamdela | 61 220 | 6 762 | 11.0 |
| Deneysville | 6 533 | 5 214 | 79.8 |
| Refengkgotso | 12 755 | 124 | 1.0 |
| Oranjeville | 2 543 | 1 815 | 71.4 |
| Metsimaholo | 3 985 | 38 | 1.0 |
| Sundry Debtors | 492 | 785 | 159.6 |
| Metsimaholo | 340 700 | 229 560 | 67.38 |
| Local Municipality |  |  |  |

Monthly payment rate for: September 2019 (excluding prepaid)

|  | LEVIES | PAYMENTS | PAYMENT- |
| --- | --- | --- | --- |
|  | Sep-19 | Oct-19 |  |
|  | R 000 | R 000 | RATE (%) |
| Sasolburg | 80 189 | 77 345 | 96.5 |
| Zamdela | 17 232 | 1 131 | 6.6 |
| Deneysville | 2 330 | 1 364 | 58.5 |
| Refengkgotso | 3 605 | 22 | 0.6 |
| Oranjeville | 569 | 551 | 96.8 |
| Metsimaholo | 1 083 | 12 | 1.1 |
| Sundry Debtors | 174 | 54 | 31.0 |
| Metsimaholo | 105 182 | 80 479 | 76.51 |
| Local Municipality |  |  |  |

- The levies represent all the amounts billed, including indigent accounts, but excluding prepaid electricity sales

- The levied amount is net of the free basic amount.

- The payment amount does not include the indigent subsidy, as the free basic services are deducted from the levies.

- If the free basic services amounts are included in the levies and in the payments, the payment level will be slightly higher

- If prepaid electricity sales are included in the levies and in the payments, the payment level will be slightly higher.

Payment rate per ward – for the month

(Taking into account free basic services to indigents)

| Ward | MOVEMENT(Levies) September 2019 | RECEIPTS October 2019 | PERCENTAGE |
| --- | --- | --- | --- |
| 001 | 1 601 808.12 | -253 022.42 | 15.80 |
| 002 | 1 322 273.57 | -13 822.98 | 1.05 |
| 003 | 1 658 273.02 | -11 654.71 | 0.70 |
| 004 | 1 073 531.30 | -5 544.45 | 0.52 |
| 005 | 2 187 366.23 | -777 138.56 | 35.53 |
| 006 | 2 826 914.09 | -23 045.48 | 0.82 |
| 007 | 1 064 309.82 | -102 243.53 | 9.61 |
| 008 | 2 031 964.27 | -80 438.21 | 3.96 |
| 009 | 594 786.67 | -121 555.64 | 20.44 |
| 010 | 1 975 141.05 | -349 604.16 | 17.70 |
| 011 | 800 740.70 | -155 036.36 | 19.36 |
| 012 | 473 085.82 | -92 516.91 | 19.56 |
| 013 | 2 557 018.09 | -42 621.66 | 1.67 |
| 014 | 8 656 112.95 | -7 535 312.97 | 87.05 |
| 015 | 1 521 349.99 | -1 312 538.97 | 86.27 |
| 016 | 3 150 831.29 | -5 822 422.47 | 184.79 |
| 017 | 28 513 140.84 | -54 356 540.38 | 190.64 |
| 018 | 44 695 627.95 | -6 189 326.93 | 13.85 |
| 019 | 3 023 482.40 | -78 323.92 | 2.59 |
| 020 | 3 164 360.28 | -1 380 184.59 | 43.62 |
| 021 | 1 060 777.84 | -15 437.79 | 1.46 |

*Included industrial areas such as NATREF, SASOL, NALEDI

Payment rate per ward - Year to date

(Taking into account free basic services to indigents)

| Ward | MOVEMENT(Levies) September 2019 | RECEIPTS October 2019 | PERCENTAGE |
| --- | --- | --- | --- |
| 001 | 7 560 778.53 | -2 054 517.62 | 27.17 |
| 002 | 3 908 356.49 | -149 075.46 | 3.81 |
| 003 | 5 178 564.42 | -75 555.46 | 1.46 |
| 004 | 4 620 396.62 | -20 950.22 | 0.45 |
| 005 | 9 599 991.07 | -2 824 931.91 | 29.43 |
| 006 | 6 010 482.44 | -1 736 588.21 | 28.89 |
| 007 | 4 533 481.63 | -340 707.55 | 7.52 |
| 008 | 8 073 143.96 | -568 633.54 | 7.04 |
| 009 | 4 345 010.84 | -553 855.89 | 12.75 |
| 010 | 7 065 983.67 | -1 506 374.19 | 21.32 |
| 011 | 3 567 603.13 | -640 798.82 | 17.96 |
| 012 | 1 771 867.40 | -395 541.78 | 22.32 |
| 013 | 8 154 704.58 | -471 374.27 | 5.78 |
| 014 | 40 681 864.09 | -23 828 244.02 | 58.57 |
| 015 | 5 464 791.96 | -4 889 697.71 | 89.48 |
| 016 | 21 952 737.81 | -19 810 999.97 | 90.24 |
| 017 | 110 922 066.81 | -139 982 423.10 | 126.20 |
| 018 | 62 427 186.84 | -19 592 844.39 | 31.39 |
| 019 | 8 439 061.67 | -214 003.29 | 2.54 |
| 020 | 10 983 109.05 | -5 289 926.46 | 48.16 |
| 021 | 5 117 275.92 | -93 930.86 | 1.84 |

*Included industrial areas such as NATREF, SASOL, NALEDI

- Analysis of Budget, Actual and Collection

(Actual Billing compared to Budgeted Billing) (Including prepaid electricity)   Comparison:   (as per General Ledger)

| Budget vs Levy | Budget per Month (19/20) | Actual Levy (October 2019) | Actual Cash Collection (November 2019) |
| --- | --- | --- | --- |
| Cleansing | R2 357 599 | R2 885 444 |  |
| Electricity | R24 852 098 | R25 132 759 |  |
| Sewer | R2 491 001 | R2 322 146 |  |
| Water | R39 848 771 | R32 618 459 |  |
| Assessment Rates | R17 933 680 | R14 675 857 |  |
| Housing/Hostel Interest | R471 268 R3 022 483 | R442 829 R3 918 268 |  |
| Unallocated |  |  |  |
| Total | R90 976 900 | R81 995 762 |  |

Actual levies are 90.13% of Budgeted levies for the month

| Budget vs Levy | Budget per Month (19/20) | Actual Levy (September 2019) | Actual Cash Collection (October 2019) |
| --- | --- | --- | --- |
| Cleansing | R2 357 599 | R83 246 | R1 515 824 |
| Electricity | R24 852 098 | R6 568 952 | R15 626 142 |
| Sewer | R2 491 001 | R75 962 | R1 416 784 |
| Water | R39 848 771 | R31 120 952 | R8 360 205 |
| Assessment Rates | R17 933 680 | R1 710 272 | R9 678 838 |
| Housing/Hostel Interest | R471 268 R3 022 483 | R35 766 R3 709 500 | R68 271 R246 529 |
| Unallocated |  |  | R49 007 346 |
| Total | R90 976 900 | R43 304 650 | R85 919 939 |

- Actual levied is 	        	   47.60% 	of budgeted levies for the month.

- Actual cash collection is 	   94.44% 	of budgeted levies for the month

- Actual cash collection is 	   198.41% 	of actual levied-previous month

- Councillors’ balances and arrears outstanding as at 31 October 2019

Councillor Arrears

Councillor balances outstanding		R816k 	 (Sept 2019– R803k)

Arrears longer than 3 months 		R709k   	 (Sept 2019 – R686k)

The amount has increased from the previous month for the period 3 months and longer

Municipal Systems Act

A Councillor may not be in arrears to the municipality for rates and service charges for a period longer than 3 months

It is the duty of the chairperson of municipal Councils to take necessary action where the Code of Conduct for Councillors has been breached

| Councillors balances outstanding as 31 October 2019 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Account No | Name | Initials | Debtor Type | Account Type | Current Ageing | 30 Days Ageing | 60 Days Ageing | 90 Days Ageing | 120+ Days Ageing | Total Ageing | Remarks |
| 525381 | DU TOIT | T | CC | Normal | 3 693.22 | 4 386.89 | 18 795.88 | 7 854.30 | 7 437.97 | 42 168.26 | No Arrangement |
| 108921 | DYWILI (MY2436) | NN | CC | Normal | 881.22 | 943.85 | 972.32 | 582.27 | 24 507.63 | 27 887.29 | No Arrangement |
| 536637 | LEOTLELA (MY2403) | PR | CC | Normal | 174.29 | 173.40 | 172.50 | 173.25 | 10 834.90 | 11 528.34 | No Arrangement |
| 592959 | LEOTLELA (MY2403) | PR | CC | Handed over | - | - | - | - | 10 944.67 | 10 944.67 | No Arrangement |
| 108353 | MAHLAELA (MY2428) | MD | CC | Normal | 223.89 | 219.29 | 105.21 | 4 593.80 | 4 211.27 | 9 353.46 | No Arrangement |
| 595729 | MALINDI (MY2417) | MJ | CC | Handed over | - | - | - | - | 5 129.94 | 5 129.94 | No Arrangement |
| 593277 | MATWA (MY2444-R616 PM) | SM | CC | Handed over | - | - | - | - | 11 393.81 | 11 393.81 | No Arrangement |
| 612908 | MATWA (MY2444-R616 PM) | SM | CC | Normal | 154.53 | 158.07 | 161.77 | 164.46 | 24.27 | 663.10 | No Arrangement |
| 872070 | MATWA (MY2444-R616 PM) | SM | CC | Abeyance | - | - | - | - | 6 146.92 | 6 146.92 | No Arrangement |
| 553229 | MOISI T J TAATS (MY2405) | ME` | CC | Normal | 378.64 | 1 709.77 | 473.75 | 1 459.87 | 2 435.72 | 6 457.75 | No Arrangement |
| 109049 | MOKOENA M E Maseko (MY2406) | DE | CC | Normal | 310.06 | 309.16 | 308.26 | 308.16 | 37 839.70 | 39 075.34 | No Arrangement |
| 590648 | MOKOENA M E Maseko (MY2406) | DE | CC | Handed over | - | - | - | - | 10 839.32 | 10 839.32 | No Arrangement |
| 565105 | MOKWENA N Mokoena (MY2439) | MS | CC | Arrangement | - | - | - | 305.60 | 27 792.82 | 28 098.42 | Honoured |
| 594687 | MOKWENA N Mokoena (MY2439) | MS | CC | Handed over | - | - | - | - | 779.19 | 779.19 | No Arrangement |
| 594135 | MOKWENA N Mokoena (MY2439) | RE | CC | Handed over | - | - | - | - | 25 181.67 | 25 181.67 | No Arrangement |
| 12921 | MOLETA S Motlhale (MY2411) | M | CC | Normal | 593.06 | 587.21 | 537.20 | 538.11 | 16 673.40 | 18 928.98 | No Arrangement |
| 553206 | MONYELA P M Mokoena(MY2431) | SD | CC | Normal | 193.96 | 179.83 | 507.27 | 226.65 | 8 891.27 | 9 998.98 | No Arrangement |
| 108066 | MOSOKWENI (MY2437) | FD | CC | Normal | 438.44 | 426.67 | 375.80 | 387.30 | 63 051.48 | 64 679.69 | No Arrangement |
| 537934 | MOTAUNG (MY2410) | TA | CC | Normal | 319.44 | 317.48 | 304.95 | 305.49 | 12 438.70 | 13 686.06 | No Arrangement |
| 106180 | MOTJEANE S M Motjeane(MY2407) | RJ | CC | Normal | 4 124.79 | 11 667.64 | 3 421.27 | 3 299.26 | 78 279.34 | 100 792.30 | No Arrangement |
| 103466 | MTSHALI (MY2420) | BP | CC | Normal | 614.87 | 595.51 | 576.70 | 505.25 | 6 000.00 | 8 292.33 |  |
| 562315 | MTSHALI (MY2420) | BP | CC | Arrangement | - | - | - | - | 33 404.84 | 33 404.84 | Honoured |
| 526816 | MZIZI S S Kobo(MY2426) | TJ | CC | Normal | 261.42 | 213.99 | 486.88 | 431.29 | 30 344.29 | 31 737.87 | No Arrangement |
| 108037 | NKHELOANE M Nkheloane (MY2433) | NE | CC | Normal | 694.36 | 689.64 | 688.75 | 682.65 | 12 564.91 | 15 320.31 |  |
| 575013 | NKHELOANE M Nkheloane (MY2433) | NE | CC | Arrangement | - | - | - | - | 6 721.10 | 6 721.10 | Honoured |
| 592910 | NKHELOANE M Nkheloane (MY2433) | NE | CC | Handed over | - | - | - | - | 31 356.25 | 31 356.25 | No Arrangement |
| 107830 | NYAKU-MAPHEELLE (MY2416) | MM | CC | Normal | 1 325.40 | 1 637.33 | 1 794.60 | 1 593.21 | 2 684.25 | 9 034.79 |  |
| 830645 | NYAKU-MAPHEELLE (MY2416) | MM | CC | Arrangement | - | - | - | - | 7 902.52 | 7 902.52 | Honoured |
| 589204 | POHO(MY2432) | MS | CC | Arrangement | - | - | - | - | 15 140.88 | 15 140.88 | Honoured |
| 590215 | SEMELA T S Mokoena(MY2415) | MF | CC | Normal | 730.35 | 725.84 | 566.40 | 572.22 | 52 722.22 | 55 317.03 | No Arrangement |
| 512521 | TELANE (MY2429) | P | CC | Normal | 2 512.98 | 839.47 | 2 968.14 | 1 301.41 | 77 408.40 | 85 030.40 | No Arrangement |
| 511192 | TSOTETSI (MY2423) | P | CC | Normal | 467.84 | 466.79 | 28 856.31 | 587.80 | 42 144.46 | 72 523.20 | No Arrangement |
|  |  |  |  |  | 18 092.76 | 26 247.83 | 62 073.96 | 25 872.35 | 683 228.11 | 815 515.01 |  |

- Officials balances and arrears as at 31 October 2019

Those officials who have not made arrangements - Deductions of up to 20% are made from their salaries.

Staff arrears (outstanding greater than 90 days)

Staff (officials) balances outstanding greater than 90 days totalled R1.0m (Sept – R1.0m)

Staffs have been reminded of the requirements of the Municipal Systems Act in that they are not to have arrears for a period longer than 3 months.

- Deductions were effected from the staff salaries as from the month of September 2014 in cases where no arrangements have been made.

- Where arrangements are in place this will be reviewed and the arrangements amounts may be increased. Affordability will be taken into consideration.

- All the officials owing may not be on the list as their residential details is not available. Information is not declared by officials.

Those officials who have not made arrangements - Deductions of up to 20% have been made from their salaries from November 2017.

Officials with arrears will be specifically addressed in the Revenue Enhancement Strategy. The workshop has been postponed and roll out can only happen in 2018/2019 year.

| Officials balance outstanding as at 31 October 2019 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Account No | Name | Initials | Debtor Type | Account Type | Current Ageing | 30 Days Ageing | 60 Days Ageing | 90 Days Ageing | 120+ Days Ageing | Total Ageing | Remarks |
| 598702 | MPETJEKANA (A48082) | NS | OF | Handed over | - | 17.25 | 34.50 | 17.25 | 7 635.76 | 7 704.76 | Arrangement M & G |
|  |  |  |  |  | - | 17.25 | 34.50 | 17.25 | 7 635.76 | 7 704.76 |  |
| Account No | Name | Initials | Debtor Type | Account Type | Current Ageing | 30 Days Ageing | 60 Days Ageing | 90 Days Ageing | 120+ Days Ageing | Total Ageing | Remarks |
| 589598 | KHUMALO TD032(R550) | MR | OF | Arrangement | - | - | - | 1 400.00 | 16 144.63 | 17 544.63 | Honoured |
| 580348 | KOK (1119)(R1000) | TJ | OF | Arrangement | - | - | - | - | 14 368.80 | 14 368.80 | Honoured |
| 600517 | LUMA A60264 | MB | OF | Arrangement | - | - | - | - | 564.07 | 564.07 | Honoured |
| 599787 | MABULA(A48085)(R1000.00) | MM | OF | Arrangement | - | - | - | - | 1 266.88 | 1 266.88 | Honoured |
| 578762 | MADLALA(A02557) | BT | OF | Arrangement | - | - | - | - | 9 464.18 | 9 464.18 | Honoured |
| 563823 | MALINDI(A19218) | MA | OF | Arrangement | - | - | - | - | 59.73 | 59.73 | Honoured |
| 830745 | MALOKA( TD055) | MM | OF | Arrangement | - | - | - | - | 11 792.73 | 11 792.73 | Honoured |
| 581425 | MAROSHA 2541 | PA&MA | OF | Arrangement | - | 1 227.45 | 585.62 | - | 3 266.08 | 5 079.15 | Honoured |
| 830780 | MATSEMULA TD035 | MM | OF | Arrangement | - | - | - | - | 4 856.92 | 4 856.92 | Honoured |
| 562772 | MAZIBUKO_(AMPT 00150) | NE | OF | Arrangement | - | - | - | - | 7 289.09 | 7 289.09 | Honoured |
| 830690 | MGXWASHU A19143 | MS | OF | Arrangement | - | - | - | - | 15 952.79 | 15 952.79 | Honoured |
| 830839 | MKHABELA | MG&GN | OF | Arrangement | - | - | - | - | 20 626.89 | 20 626.89 | Honoured |
| 561605 | MNGUNI(A47447) | NB | OF | Arrangement | - | - | - | - | 3 304.79 | 3 304.79 | Honoured |
| 830242 | MOKOENA (A19174)(R600) | MS | OF | Arrangement | - | - | - | - | 6 852.13 | 6 852.13 | Honoured |
| 578911 | MONAHENG A19220 R600 | JC | OF | Arrangement | - | - | 403.18 | 403.48 | 4 935.82 | 5 742.48 | Honoured |
| 568212 | MONGALE(1724) | M | OF | Arrangement | - | - | - | - | 1 525.98 | 1 525.98 | Honoured |
| 576073 | MOTLOUNG_PO3000 | MS | OF | Arrangement | - | - | - | - | 3 449.68 | 3 449.68 | Honoured |
| 830884 | MOTSITSI (1125) | MD&AB | OF | Arrangement | - | 1 797.76 | 1 802.05 | 1 485.70 | 57.79 | 5 143.30 | Honoured |
| 588504 | MOTSITSI A24725 | MJ | OF | Arrangement | - | - | - | - | 13 246.33 | 13 246.33 | Honoured |
| 561146 | NDUMO 0127 | LL | OF | Arrangement | - | - | - | - | 286.91 | 286.91 | Honoured |
| 830680 | SELEPE(R400)A24734 | J | OF | Arrangement | - | - | - | - | 5 069.61 | 5 069.61 | Honoured |
| 830112 | SELIANE (BI4738) | RD&CN | OF | Arrangement | - | - | - | - | 10 366.44 | 10 366.44 | Honoured |
| 589284 | SELIANE(BI4738) | RD | OF | Arrangement | - | - | - | - | 2 049.11 | 2 049.11 | Honoured |
| 830387 | SHEBE (5712) | KA | OF | Arrangement | - | - | - | - | 15 931.95 | 15 931.95 | Honoured |
| 830842 | SHEBE (5712) | KA | OF | Arrangement | - | - | - | - | 18 259.37 | 18 259.37 | Honoured |
| 566565 | SIMELANE A24736(R830) | LA | OF | Arrangement | - | - | - | - | 7 073.57 | 7 073.57 | Honoured |
| 830126 | TSHABALALA(3806) | PP | OF | Arrangement | - | - | - | - | 35 384.30 | 35 384.30 | Honoured |
| 562276 | TSHABALALA_A49339 | NS | OF | Arrangement | - | - | - | - | 8 415.96 | 8 415.96 | Honoured |
| 588456 | TSHABANGU 00126 | SM | OF | Arrangement | - | - | - | - | 4 158.02 | 4 158.02 | Honoured |
| 830421 | VAN DER MERWE 0129 | KJH&EA | OF | Arrangement | - | - | - | - | 16 101.89 | 16 101.89 | Honoured |
| 562477 | ZWANE (A02558) | SE&HB | OF | Arrangement | - | - | - | - | 10 040.17 | 10 040.17 | Honoured |
|  |  |  |  |  | - | 3 025.21 | 2 790.85 | 3 289.18 | 272 162.61 | 281 267.85 |  |
| Account No | Name | Initials | Debtor Type | Account Type | Current Ageing | 30 Days Ageing | 60 Days Ageing | 90 Days Ageing | 120+ Days Ageing | Total Ageing | Remarks |
| 512582 | HLAHANE__(D7212) | J | OF | Normal | 1 189.83 | 535.34 | 482.08 | 1 970.81 | - | 4 178.06 | No Arrangement |
| 558233 | KASA (1022) | LN | OF | Normal | 476.21 | 389.31 | 389.17 | 383.22 | 11 477.80 | 13 115.71 | No Arrangement |
| 588221 | KHOZA | T | OF | Normal | 1 000.68 | 1 356.50 | 1 059.81 | 1 019.66 | 8 776.50 | 13 213.15 | No Arrangement |
| 792036 | LERATA__4905 | DP | OF | Normal | 158.98 | 157.77 | 156.56 | 155.49 | 579.16 | 1 207.96 | No Arrangement |
| 556399 | MACHAEA | PV | OF | Normal | 850.62 | 841.50 | 710.30 | 708.33 | 8 932.08 | 12 042.83 | No Arrangement |
| 319590 | MAKHELEDISA (3806) | SJ | OF | Normal | 589.32 | 591.99 | 589.04 | 588.66 | 17 639.27 | 19 998.28 | No Arrangement |
| 791508 | MAKO (A19364) | MK | OF | Normal | 1 975.97 | 2 118.32 | 1 841.17 | 1 800.70 | 58 007.58 | 65 743.74 | No Arrangement |
| 603246 | MASUKU | TL | OF | Normal | 672.30 | 667.14 | 661.97 | 657.97 | 6 531.47 | 9 190.85 | No Arrangement |
| 550463 | MBABALE (1927- R300PM) | JM | OF | Normal | 640.51 | 573.99 | 429.57 | 439.38 | 37 538.38 | 39 621.83 | No Arrangement |
| 526623 | MOFOKENG__080313 | DE | OF | Normal | 641.20 | 636.50 | 493.01 | 493.71 | 8 996.33 | 11 260.75 | No Arrangement |
| 511919 | MOFOKENG__D8003 | PJ | OF | Normal | 329.35 | 318.13 | 338.55 | 327.49 | 15 890.59 | 17 204.11 | No Arrangement |
| 568955 | MOHOLI(A10319) | ML&NR | OF | Normal | 1 338.29 | 850.64 | 1 526.98 | 1 363.61 | - | 5 079.52 | No Arrangement |
| 107168 | MOKHELE A15891 | SR | OF | Normal | 948.47 | 1 278.68 | 1 244.44 | 2 911.49 | 21 743.82 | 28 126.90 | No Arrangement |
| 604348 | MOKOENA (1101) | SJ&SJ | OF | Normal | 1 099.86 | 1 129.62 | 977.71 | 892.93 | - | 4 100.12 | No Arrangement |
| 1753 | MOKOENA(1101) | SJ | OF | Normal | 754.09 | 810.76 | 770.98 | 720.72 | 672.37 | 3 728.92 | No Arrangement |
| 794364 | MOKOENA(1101) | SJ&SJ | OF | Normal | 1 320.45 | 1 347.45 | 1 304.59 | 1 149.85 | - | 5 122.34 | No Arrangement |
| 871950 | MONAHENG A19220 R600 | JC | OF | Abeyance | - | - | - | - | 12 061.37 | 12 061.37 | No Arrangement |
| 100415 | MOTSEI 1006 | ZA | OF | Normal | 1 129.27 | 515.86 | 513.99 | 513.28 | 9 898.76 | 12 571.16 | No Arrangement |
| 109198 | MOTSIE__00119 | JM | OF | Normal | 307.34 | 617.10 | 319.76 | 646.69 | 8 154.67 | 10 045.56 | No Arrangement |
| 108932 | MOTSOENENG 1171 | MJ | OF | Normal | 1 022.46 | 3 663.23 | 858.71 | 849.88 | 13 461.67 | 19 855.95 | No Arrangement |
| 109232 | NGQUBA(A42517) | T | OF | Normal | 1 900.49 | 1 974.80 | 1 980.00 | 1 898.74 | 40 507.89 | 48 261.92 | No Arrangement |
| 604363 | NKUMANE | SB | OF | Normal | 999.83 | 1 599.57 | 915.29 | 974.12 | 4 375.06 | 8 863.87 | No Arrangement |
| 526564 | QHAMAKOANE(O80308) | DI | OF | Normal | 417.20 | 442.31 | 461.13 | 433.14 | 599.08 | 2 352.86 | No Arrangement |
| 605027 | RADEBE(3840) & MASOMBUKA | PM&NB | OF | Normal | 458.72 | 487.45 | 464.40 | 509.21 | - | 1 919.78 | No Arrangement |
| 794833 | RAMATHE | JS | OF | Normal | 2 561.60 | 1 792.04 | 1 909.96 | 1 747.91 | 85 949.19 | 93 960.70 | No Arrangement |
| 104043 | SEFATSA W07673 | LA | OF | Normal | 1 085.50 | 938.04 | 1 182.64 | 918.80 | 69 448.73 | 73 573.71 | No Arrangement |
| 526983 | SOLANI (080018) | NM | OF | Normal | 847.39 | 687.25 | 1 141.00 | 533.69 | 28 460.74 | 31 670.07 | No Arrangement |
| 795037 | TOM 00140 | NE | OF | Normal | 1 327.53 | 1 654.04 | 2 235.51 | 176.13 | - | 5 393.21 | No Arrangement |
| 599634 | TSOTETSI(00114) | TE | OF | Normal | 1 332.19 | 2 055.53 | 1 863.81 | 216.48 | - | 5 468.01 | No Arrangement |
| 27524 | ZAKWE A024 | OL | OF | Normal | 605.08 | 601.42 | 614.62 | 582.33 | 2 228.13 | 4 631.58 | No Arrangement |
| 592756 | KOK (1119)(R1000) | TJ | OF | Handed over | - | - | - | - | 3 828.31 | 3 828.31 | No Arrangement M & G |
| 597055 | MALINDI(A19218) | MA | OF | Handed over | - | - | - | - | 29 844.65 | 29 844.65 | No Arrangement M & G |
| 582620 | MATSEMULA TD035 | MM | OF | Handed over | - | - | - | - | 43 175.80 | 43 175.80 | No Arrangement M & G |
| 596744 | MBIKOLO(W10010) | MM | OF | Handed over | - | - | - | - | 9 164.85 | 9 164.85 | No Arrangement M & G |
| 590644 | MOKOENA (A19174)(R600) | MS | OF | Handed over | - | - | 353.63 | - | 11 184.69 | 11 538.32 | No Arrangement M & G |
| 593107 | MONAHENG A19220 R600 | JC | OF | Handed over | - | - | - | - | 7 664.79 | 7 664.79 | No Arrangement M & G |
| 598707 | NGQUBA(A42517) | T | OF | Handed over | - | - | 106.95 | - | 36 406.55 | 36 513.50 | No Arrangement M & G |
| 588031 | VILAKAZI (4301) | MC | OF | Handed over | - | - | - | - | 21 872.42 | 21 872.42 | No Arrangement M & G |
| 597748 | ZAKWE A024 | OL | OF | Handed over | - | 40.25 | 40.25 | 40.25 | 3 472.92 | 3 593.67 | No Arrangement M & G |
|  |  |  |  |  | 27 980.73 | 30 672.53 | 27 937.58 | 25 624.67 | 638 545.62 | 750 761.13 |  |
| Account No | Name | Initials | Debtor Type | Account Type | Current Ageing | 30 Days Ageing | 60 Days Ageing | 90 Days Ageing | 120+ Days Ageing | Total Ageing | Remarks |
| 339440 | KOK (1119)(R1000) | TJ | OF | Normal | 2 322.94 | 1 745.89 | 1 151.92 | 1 141.08 | 13 748.67 | 20 110.50 |  |
| 530162 | MADLALA(A02557) | BT | OF | Normal | 1 112.27 | 966.80 | 1 425.47 | 477.31 | - | 3 981.85 |  |
| 105655 | MALINDI(A19218) | MA | OF | Normal | 741.11 | 737.73 | 683.47 | 676.92 | 2 051.97 | 4 891.20 |  |
| 560323 | MKHABELA | MG&GN | OF | Normal | 2 275.49 | 2 477.03 | 2 419.48 | 1 710.92 | - | 8 882.92 |  |
| 581317 | MOKOENA (A19174)(R600) | MS | OF | Normal | 1 336.00 | 879.19 | 1 433.05 | 1 153.10 | 8 273.73 | 13 075.07 |  |
| 604272 | MOTSITSI (1125) | MD&AB | OF | Normal | 1 843.48 | 58.04 | 16.98 | 236.95 | 1 021.06 | 3 176.51 |  |
| 552905 | SIMELANE A24736(R830) | LA | OF | Normal | 7 480.42 | 255.47 | 234.18 | 234.57 | 8 187.79 | 16 392.43 |  |
| 795182 | TSHABALALA(3806) | PP | OF | Normal | 1 645.33 | 2 026.84 | 2 814.43 | 1 693.88 | 7 394.06 | 15 574.54 |  |
| 3931 | TSHABANGU 00126 | SM | OF | Normal | 549.24 | 624.34 | 3 009.94 | 5 423.67 | 19 216.30 | 28 823.49 |  |
|  |  |  |  |  | 19 306.28 | 9 771.33 | 13 188.92 | 12 748.40 | 59 893.58 | 114 908.51 |  |
|  |  |  |  | TOTAL | 47 287.01 | 43 486.32 | 43 951.85 | 41 679.50 | 978 237.57 | 1 154 642.25 |  |

# J Current Liabilities

- The creditor’s age analysis increased from R149.2 to R158.2

- The payment of creditors affects the cash flow situation.

The top 6 creditors balances are as follows: -

| 1. | Government Garage | June 2019 statement | R16 150 000 |
| --- | --- | --- | --- |
| 2. | Department of Water Affairs | August statement | R41 274 970 |
| 3. | Eskom | Current account | R 22 045 080 |
| 4. | Rand Water | Current account | R 18 330 260 |
| 5 | Millennium Pumps | July 2019 statement | R1 045 130 |
| 6. | Aqua Transport | July 2018 Statement | R 985 890 |
|  | Total of top 6 | 63.0%of total creditors | 40444R 99 831 330 |
| 7. | Other creditors |  | R54 455 635 |
|  | Total creditors |  | R158 286 965 |

- Government Garage:

No payments were made in October 2019.  No arrangements were made for the payment of outstanding balance.

- Department of Water Affairs:

No current account was received for payment in October.  An enquiry was made

to the Supplier and payment will be made in November 2019.

A formal agreement for payments of the arrear amount is not yet signed.

# K: Budget Related Charts

# Chart 1:	Revenue by Major source

Revenue from own sources represents 100% of total revenue in October 2019.

The four major sources of own revenue for October 2019 is as follows:

- Water					37.8%

- Electricity	 			32.8%

- Property rates				17.0%

- Interest – outstanding debtors	4.5%

- Waste Management			 3.4%

# Total				           95.5 %

The figures on the chart for October 2019 are cumulative (Year-to-date).

# Chart 2:	Revenue by Minor Source

# The figures on the chart are cumulative (year to date)

- Interest earned on outstanding debtors amounts to R3 918 000 in October 2019.

- Revenue from fines amounts to R54 000 in October 2019.

# Chart 3:	Operating Expenditure by Major Type

# The figures on the chart are cumulative (year to date)

The major expenses for October 2019 are as follows:

- Bulk Purchases-Electricity		31.7 %

- Bulk purchases – Water		23.8%

- Employee related cost			19.6%

- Contracted services			 6.3%

TOTAL				            81.4%

# Chart 4:	Capital Expenditure Monthly Trend

# Chart 5:	Consumer Debtors Consumers per period

# Consumers per category

COMMENTS ON THE DEBTORS BOOK

Performance of the debtors’ book

- The gross debtors book exceeds R1 billion and the latest amount at end of October 2019 is R1 598 745 603 (June 2019 – R1 373 437 700)

- The concentration of the debtors’ book is mainly in the category of household consumers

- The debtors’ book is an accumulation of debt over many years

- The debtors’ book will continue to grow for as long as the payment level is below 100%, in addition interest is charged on the outstanding balances which also contributes to the growth in the debtors’ book

Impairment of the debtors’ book

- The Impairment on the debtors’ book as at 30 June 2019 is R1 039.766b and represents 75.63% of the gross debtor’s book

- Impairment for the four months totalled R50.9m

- Total impairment as at October 2019 is R1 090.66b, and represents 68% of the gross debtor’s book

Budget implications

- The budget is prepared based on an estimated projection of the payment level and not on the balance of the debtors’ book

Credit Control

- Credit control measures are to be applied to all household consumers throughout the municipality

- The municipality does not have sufficient capacity in the debt management department to manage all the household debt.

- The debt management department needs to be further capacitated

- No credit control measures for Deneysville and Oranjeville

5. In -Year	Budget Statement Tables

| FS204 Metsimaholo - Table C1 Monthly Budget Statement Summary - M04 October |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description | 2018/19 | Budget Year 2019/20 |  |  |  |  |  |  |  |
|  | Audited Outcome | Original Budget | Adjusted Budget | Monthly actual | YearTD actual | YearTD budget | YTD variance | YTD variance | Full Year Forecast |
| R thousands |  |  |  |  |  |  |  | % |  |
| Financial Performance |  |  |  |  |  |  |  |  |  |
| Property rates | 143 648 | 215 204 | 215 204 | 14 676 | 80 006 | 71 735 | 8 272 | 12% | 215 204 |
| Service charges | 698 482 | 831 098 | 831 098 | 66 227 | 281 265 | 277 033 | 4 232 | 2% | 831 098 |
| Investment revenue | 3 784 | 1 500 | 1 500 | 468 | 941 | 500 | 441 | 88% | 1 500 |
| Transfers and subsidies | 168 246 | 189 039 | 189 039 | – | 78 802 | 63 013 | 15 789 | 25% | 189 039 |
| Other own revenue | 54 659 | 75 211 | 75 211 | 5 025 | 19 684 | 25 070 | (5 386) | -21% | 75 211 |
| Total Revenue (excluding capital transfers and contributions) | 1 068 819 | 1 312 052 | 1 312 052 | 86 397 | 460 698 | 437 351 | 23 348 | 5% | 1 312 052 |
| Employee costs | 288 618 | 359 390 | 358 069 | 24 991 | 98 506 | 119 408 | (20 902) | -18% | 358 069 |
| Remuneration of Councillors | 17 554 | 19 855 | 19 855 | 1 559 | 6 235 | 6 619 | (383) | -6% | 19 855 |
| Depreciation & asset impairment | 72 118 | 83 085 | 83 085 | – | – | 27 695 | (27 695) | -100% | 83 085 |
| Finance charges | 8 063 | 6 448 | 6 448 | 208 | 306 | 2 149 | (1 844) | -86% | 6 448 |
| Materials and bulk purchases | 414 318 | 511 948 | 512 741 | 73 058 | 172 796 | 170 790 | 2 005 | 1% | 512 741 |
| Transfers and subsidies | 297 | 42 | 42 | – | 14 | 14 | (1) | -4% | 42 |
| Other expenditure | 365 272 | 329 619 | 330 147 | 27 926 | 82 273 | 110 123 | (27 850) | -25% | 330 147 |
| Total Expenditure | 1 166 241 | 1 310 388 | 1 310 388 | 127 742 | 360 129 | 436 798 | (76 669) | -18% | 1 310 388 |
| Surplus/(Deficit) | (97 422) | 1 665 | 1 665 | (41 345) | 100 569 | 552 | 100 017 | 18108% | 1 665 |
| Transfers and subsidies - capital (monetary allocations) (National / Provincial and District) | 60 980 | 81 069 | 81 069 | – | – | 27 023 | (27 023) | -100% | 81 069 |
| Contributions & Contributed assets | 65 141 | 96 200 | 96 200 | – | – | 32 067 | (32 067) | -100% | 96 200 |
| Surplus/(Deficit) after capital transfers & contributions | 28 698 | 178 934 | 178 934 | (41 345) | 100 569 | 59 642 | 40 927 | 69% | 178 934 |
| Share of surplus/ (deficit) of associate | – | – | – | – | – | – | – |  | – |
| Surplus/ (Deficit) for the year | 28 698 | 178 934 | 178 934 | (41 345) | 100 569 | 59 642 | 40 927 | 69% | 178 934 |
| Capital expenditure & funds sources |  |  |  |  |  |  |  |  |  |
| Capital expenditure | 117 339 | 294 517 | 294 517 | 7 224 | 15 378 | 98 173 | (82 794) | -84% | 294 517 |
| Capital transfers recognised | 113 156 | 177 269 | 177 269 | 6 632 | 13 677 | 59 090 | (45 413) | -77% | 177 269 |
| Borrowing | – | 55 972 | 55 972 | – | – | 18 658 | (18 658) | -100% | 55 972 |
| Internally generated funds | 4 183 | 61 275 | 61 275 | 592 | 1 701 | 20 425 | (18 724) | -92% | 61 275 |
| Total sources of capital funds | 117 339 | 294 517 | 294 517 | 7 224 | 15 378 | 98 173 | (82 794) | -84% | 294 517 |
| Financial position |  |  |  |  |  |  |  |  |  |
| Total current assets | 838 444 | 344 423 | 344 423 |  | 1 712 816 |  |  |  | 344 423 |
| Total non current assets | 1 688 390 | 1 625 784 | 1 625 784 |  | 1 703 769 |  |  |  | 1 625 784 |
| Total current liabilities | 984 576 | 285 112 | 285 112 |  | 1 640 742 |  |  |  | 285 112 |
| Total non current liabilities | 3 828 | 59 570 | 59 570 |  | 3 828 |  |  |  | 59 570 |
| Community wealth/Equity | 1 606 741 | 1 625 525 | 1 625 525 |  | 1 772 015 |  |  |  | 1 625 525 |
| Cash flows |  |  |  |  |  |  |  |  |  |
| Net cash from (used) operating | 97 785 | 83 249 | 83 249 | 11 762 | 34 060 | 27 750 | (6 310) | -23% | 83 249 |
| Net cash from (used) investing | (86 656) | (134 237) | (134 237) | 17 453 | (52 223) | (44 746) | 7 477 | -17% | (134 237) |
| Net cash from (used) financing | (3 312) | (5 924) | (5 924) | 138 | 753 | (1 975) | (2 728) | 138% | (5 924) |
| Cash/cash equivalents at the month/year end | 20 444 | (52 216) | (52 216) | – | 18 009 | (18 971) | (36 980) | 195% | (56 912) |
| Debtors & creditors analysis | 0-30 Days | 31-60 Days | 61-90 Days | 91-120 Days | 121-150 Dys | 151-180 Dys | 181 Dys-1 Yr | Over 1Yr | Total |
| Debtors Age Analysis |  |  |  |  |  |  |  |  |  |
| Total By Income Source | 85 907 | 84 071 | 47 066 | 35 905 | 31 278 | 35 260 | 193 038 | 1 086 221 | 1 598 746 |
| Creditors Age Analysis |  |  |  |  |  |  |  |  |  |
| Total Creditors | 53 258 | 1 496 | 3 099 | 2 039 | 1 054 | 35 875 | – | 61 466 | 158 287 |

# VIREMENTS:   October 2019

| Account no | Description | Reference | Date | Original | Additional | Reduced |
| --- | --- | --- | --- | --- | --- | --- |
| 3121228362FPRFLTZZWM | CONTR: MAINTENANCE FLEET | MEMO FROM OFFICE OF THE SPEAKER | 20191002 | 0 | 20 000 | 0 |
| 3121232360FPRFLTZZWM | INVENTORY - MATERIALS & SUPPLIES FLEET | MEMO FROM OFFICE OF THE SPEAKER | 20191002 | 40 000 | 0 | 20 000 |
| 32142265170PRMRCZZHO | OS: PRINTING SERVICES | MEMO FROM MUNICIPAL MANAGER | 20191007 | 0 | 3 500 | 0 |
| 32142320600PRMRCZZWM | INV - CONSUMABLE STORES - STANDARD RATE | MEMO FROM MUNICIPAL MANAGER | 20191007 | 0 | 2 000 | 0 |
| 32142323600PRMRCZZHO | INVENTORY - MATERIALS & SUPPLIES | MEMO FROM MUNICIPAL MANAGER | 20191007 | 10 230 | 0 | 2 000 |
| 32142323600PRMRCZZHO | INVENTORY - MATERIALS & SUPPLIES | MEMO FROM MUNICIPAL MANAGER | 20191007 | 10 230 | 0 | 3 500 |
| 33232301170PRMRCZZHO | OC: COMM - PHONE FAX TELEGRAPH & TELEX | MEMO FROM CORPORATE SERVICES | 20191022 | 1 995 000 | 0 | 85 000 |
| 33232304520PRMRCZZHO | OC: PROFESSIONAL BODIES M/SHIP & SUBS | MEMO FROM CORPORATE SERVICES | 20191022 | 3 108 000 | 85 000 | 0 |
| 34322303330PRMRCZZWM | OC: LIC - VEHICLE LIC & REGISTRATIONS | MEMO FROM SOCIAL SERVICES | 20191024 | 5 100 | 10 000 | 0 |
| 34322323600PRMRCZZHO | INVENTORY - MATERIALS & SUPPLIES | MEMO FROM SOCIAL SERVICES | 20191024 | 25 220 | 0 | 10 000 |
| 36222323600ELMRCZZHO | INVENTORY - MATERIALS & SUPPLIES | MEMO FROM TECHNICAL SERVICES | 20191004 | 30 910 | 60 000 | 0 |
| 36222323600ELQ57ZZHO | INVENTORY - MATERIALS & SUPPLIES | MEMO FROM TECHNICAL SERVICES | 20191007 | 0 | 800 000 | 0 |
| 36222323600ELQ62ZZHO | INVENTORY - MATERIALS & SUPPLIES | MEMO FROM TECHNICAL SERVICES | 20191004 | 2 500 000 | 0 | 60 000 |
| 36222323600ELQ62ZZHO | INVENTORY - MATERIALS & SUPPLIES | MEMO FROM TECHNICAL SERVICES | 20191007 | 2 500 000 | 0 | 800 000 |
| 36362272460WTP78ZZWM | C&PS: I&P ENGINEERING CIVIL | MEMO FROM TECHNICAL SERVICES | 20191022 | 1 500 000 | 0 | 400 000 |
| 36362272460WTP78ZZWM | C&PS: I&P ENGINEERING CIVIL | MEMO FROM TECHNICAL SERVICES | 20191022 | 1 500 000 | 0 | 200 000 |
| 36362326600WTQ42ZZWM | INVENTORY - WATER | MEMO FROM TECHNICAL SERVICES | 20191022 | 0 | 400 000 | 0 |
| 36362326600WTQ43ZZWM | INVENTORY - WATER | MEMO FROM TECHNICAL SERVICES | 20191022 | 0 | 200 000 | 0 |
| 38222283600PRP44ZZHO | CONTR: MAINT OF BUILDINGS & FACILITIES | MEMO FROM LED | 20191009 | 323 510 | 0 | 15 000 |
| 38222323600PRP45ZZHO | INVENTORY - MATERIALS & SUPPLIES | MEMO FROM LED | 20191009 | 5 000 | 15 000 | 0 |
|  |  |  |  |  | 1 595 500 | 1 595 500 |

  - Monthly Budget Statement Financial Performance: Standard Classification

| FS204 Metsimaholo - Table C2 Monthly Budget Statement - Financial Performance (functional classification) - M04 October |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description | Ref | 2018/19 | Budget Year 2019/20 |  |  |  |  |  |  |  |
|  |  | Audited Outcome | Original Budget | Adjusted Budget | Monthly actual | YearTD actual | YearTD budget | YTD variance | YTD variance | Full Year Forecast |
| R thousands | 1 |  |  |  |  |  |  |  | % |  |
| Revenue - Functional |  |  |  |  |  |  |  |  |  |  |
| Governance and administration |  | 141 102 | 141 917 | 141 917 | (2 175) | 71 784 | 47 306 | 24 478 | 52% | 141 917 |
| Executive and council |  | – | – | – | – | – | – | – |  | – |
| Finance and administration |  | 141 102 | 141 917 | 141 917 | (2 175) | 71 784 | 47 306 | 24 478 | 52% | 141 917 |
| Internal audit |  | – | – | – | – | – | – | – |  | – |
| Community and public safety |  | 166 928 | 269 616 | 269 616 | 16 374 | 86 984 | 89 872 | (2 888) | -3% | 269 616 |
| Community and social services |  | 470 | 1 950 | 1 950 | 22 | 136 | 650 | (513) | -79% | 1 950 |
| Sport and recreation |  | 2 170 | 17 795 | 17 795 | 52 | 234 | 5 932 | (5 697) | -96% | 17 795 |
| Public safety |  | 4 761 | 17 010 | 17 010 | 60 | 501 | 5 670 | (5 169) | -91% | 17 010 |
| Housing |  | 159 526 | 232 861 | 232 861 | 16 240 | 86 112 | 77 620 | 8 492 | 11% | 232 861 |
| Economic and environmental services |  | 26 891 | 8 716 | 8 716 | 86 | 287 | 2 905 | (2 619) | -90% | 8 716 |
| Planning and development |  | 3 022 | 3 902 | 3 902 | 86 | 286 | 1 301 | (1 014) | -78% | 3 902 |
| Road transport |  | 23 868 | 4 814 | 4 814 | – | 0 | 1 605 | (1 604) | -100% | 4 814 |
| Environmental protection |  | – | – | – | – | – | – | – |  | – |
| Trading services |  | 860 019 | 1 068 967 | 1 068 967 | 72 112 | 301 645 | 356 322 | (54 678) | -15% | 1 068 967 |
| Energy sources |  | 311 687 | 322 493 | 322 493 | 29 166 | 102 857 | 107 498 | (4 641) | -4% | 322 493 |
| Water management |  | 405 468 | 528 893 | 528 893 | 35 743 | 171 080 | 176 298 | (5 218) | -3% | 528 893 |
| Waste water management |  | 97 014 | 166 325 | 166 325 | 3 038 | 12 110 | 55 442 | (43 331) | -78% | 166 325 |
| Waste management |  | 45 851 | 51 255 | 51 255 | 4 165 | 15 597 | 17 085 | (1 488) | -9% | 51 255 |
| Other | 4 | – | 105 | 105 | – | – | 35 | (35) | -100% | 105 |
| Total Revenue - Functional | 2 | 1 194 939 | 1 489 321 | 1 489 321 | 86 397 | 460 698 | 496 440 | (35 742) | -7% | 1 489 321 |
| Expenditure - Functional |  |  |  |  |  |  |  |  |  |  |
| Governance and administration |  | 257 135 | 314 752 | 314 551 | 23 742 | 76 639 | 104 852 | (28 212) | -27% | 314 551 |
| Executive and council |  | 50 825 | 56 234 | 56 034 | 3 693 | 14 535 | 18 678 | (4 143) | -22% | 56 034 |
| Finance and administration |  | 203 799 | 255 693 | 255 692 | 19 854 | 61 324 | 85 231 | (23 908) | -28% | 255 692 |
| Internal audit |  | 2 511 | 2 826 | 2 826 | 195 | 780 | 942 | (162) | -17% | 2 826 |
| Community and public safety |  | 84 934 | 103 749 | 103 750 | 8 363 | 27 111 | 34 584 | (7 472) | -22% | 103 750 |
| Community and social services |  | 4 743 | 6 950 | 6 951 | 442 | 1 681 | 2 317 | (636) | -27% | 6 951 |
| Sport and recreation |  | 32 826 | 38 615 | 38 610 | 2 729 | 10 227 | 12 871 | (2 643) | -21% | 38 610 |
| Public safety |  | 41 992 | 52 510 | 52 515 | 4 597 | 13 265 | 17 505 | (4 239) | -24% | 52 515 |
| Housing |  | 5 373 | 5 674 | 5 674 | 595 | 1 937 | 1 891 | 46 | 2% | 5 674 |
| Economic and environmental services |  | 58 502 | 95 508 | 95 708 | 4 397 | 13 821 | 31 903 | (18 081) | -57% | 95 708 |
| Planning and development |  | 14 723 | 22 623 | 22 823 | 1 493 | 5 224 | 7 608 | (2 384) | -31% | 22 823 |
| Road transport |  | 43 779 | 72 885 | 72 885 | 2 903 | 8 597 | 24 295 | (15 698) | -65% | 72 885 |
| Trading services |  | 763 660 | 792 604 | 792 604 | 91 053 | 241 805 | 264 202 | (22 397) | -8% | 792 604 |
| Energy sources |  | 294 022 | 358 161 | 358 161 | 44 510 | 119 773 | 119 387 | 386 | 0% | 358 161 |
| Water management |  | 363 085 | 312 802 | 312 802 | 39 279 | 95 823 | 104 267 | (8 445) | -8% | 312 802 |
| Waste water management |  | 46 269 | 60 065 | 60 065 | 3 439 | 11 338 | 20 022 | (8 684) | -43% | 60 065 |
| Waste management |  | 60 284 | 61 577 | 61 577 | 3 826 | 14 872 | 20 526 | (5 654) | -28% | 61 577 |
| Other |  | 2 009 | 3 775 | 3 775 | 188 | 752 | 1 258 | (506) | -40% | 3 775 |
| Total Expenditure - Functional | 3 | 1 166 241 | 1 310 388 | 1 310 388 | 127 742 | 360 129 | 436 798 | (76 669) | -18% | 1 310 388 |
| Surplus/ (Deficit) for the year |  | 28 698 | 178 934 | 178 934 | (41 345) | 100 569 | 59 642 | 40 927 | 69% | 178 934 |

# The statement reflects the operating revenue and expenditure per Directorate for the month as well as the year to date figures for the 2018/2019 financial year

# 5.3 Monthly Budget Statement Financial Performance: Municipal vote

| FS204 Metsimaholo - Table C3 Monthly Budget Statement - Financial Performance (revenue and expenditure by municipal vote) - M04 October |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vote Description | Ref | 2018/19 | Budget Year 2019/20 |  |  |  |  |  |  |  |
|  |  | Audited Outcome | Original Budget | Adjusted Budget | Monthly actual | YearTD actual | YearTD budget | YTD variance | YTD variance | Full Year Forecast |
| R thousands |  |  |  |  |  |  |  |  | % |  |
| Revenue by Vote | 1 |  |  |  |  |  |  |  |  |  |
| Vote 01 - Executive & Council |  | – | – | – | – | – | – | – |  | – |
| Vote 02 - Municipal Manager |  | 2 300 | 3 183 | 3 183 | 19 | 38 | 1 061 | (1 023) | -96.4% | 3 183 |
| Vote 03 - Corporate Services |  | 888 | 1 300 | 1 300 | 355 | 365 | 433 | (69) | -15.9% | 1 300 |
| Vote 04 - Social Services |  | 53 253 | 88 010 | 88 010 | 4 299 | 16 469 | 29 337 | (12 868) | -43.9% | 88 010 |
| Vote 05 - Technical Services |  | 838 036 | 1 022 526 | 1 022 526 | 67 947 | 286 048 | 340 842 | (54 794) | -16.1% | 1 022 526 |
| Vote 06 - Financial Services |  | 293 862 | 362 711 | 362 711 | 13 212 | 155 555 | 120 904 | 34 651 | 28.7% | 362 711 |
| Vote 07 - Local Economic Development And Planning |  | 6 601 | 11 593 | 11 593 | 565 | 2 225 | 3 864 | (1 639) | -42.4% | 11 593 |
| Total Revenue by Vote | 2 | 1 194 939 | 1 489 321 | 1 489 321 | 86 397 | 460 698 | 496 440 | (35 742) | -7.2% | 1 489 321 |
| Expenditure by Vote | 1 |  |  |  |  |  |  |  |  |  |
| Vote 01 - Executive & Council |  | 37 009 | 45 943 | 45 943 | 3 230 | 12 719 | 15 315 | (2 595) | -16.9% | 45 943 |
| Vote 02 - Municipal Manager |  | 62 613 | 74 009 | 74 009 | 5 928 | 15 076 | 24 670 | (9 594) | -38.9% | 74 009 |
| Vote 03 - Corporate Services |  | 35 468 | 50 877 | 50 877 | 4 374 | 11 823 | 16 959 | (5 137) | -30.3% | 50 877 |
| Vote 04 - Social Services |  | 140 289 | 160 871 | 160 871 | 11 614 | 40 076 | 53 624 | (13 549) | -25.3% | 160 871 |
| Vote 05 - Technical Services |  | 760 280 | 821 994 | 821 994 | 91 400 | 239 901 | 273 998 | (34 097) | -12.4% | 821 994 |
| Vote 06 - Financial Services |  | 107 122 | 120 909 | 120 909 | 9 164 | 33 110 | 40 303 | (7 194) | -17.8% | 120 909 |
| Vote 07 - Local Economic Development And Planning |  | 23 460 | 35 784 | 35 784 | 2 032 | 7 424 | 11 928 | (4 504) | -37.8% | 35 784 |
| Total Expenditure by Vote | 2 | 1 166 241 | 1 310 388 | 1 310 388 | 127 742 | 360 129 | 436 798 | (76 669) | -17.6% | 1 310 388 |
| Surplus/ (Deficit) for the year | 2 | 28 698 | 178 934 | 178 934 | (41 345) | 100 569 | 59 642 | 40 927 | 68.6% | 178 934 |

# 5.4 Monthly Budget Statement – Financial Performance (Revenue and expenditure)

| FS204 Metsimaholo - Table C4 Monthly Budget Statement - Financial Performance (revenue and expenditure) - M04 October |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description | Ref | 2018/19 | Budget Year 2019/20 |  |  |  |  |  |  |  |
|  |  | Audited Outcome | Original Budget | Adjusted Budget | Monthly actual | YearTD actual | YearTD budget | YTD variance | YTD variance | Full Year Forecast |
| R thousands |  |  |  |  |  |  |  |  | % |  |
| Revenue By Source |  |  |  |  |  |  |  |  |  |  |
| Property rates |  | 143 648 | 215 204 | 215 204 | 14 676 | 80 006 | 71 735 | 8 272 | 12% | 215 204 |
| Service charges - electricity revenue |  | 272 953 | 293 928 | 293 928 | 28 336 | 100 126 | 97 976 | 2 150 | 2% | 293 928 |
| Service charges - water revenue |  | 365 987 | 478 442 | 478 442 | 32 660 | 159 898 | 159 481 | 417 | 0% | 478 442 |
| Service charges - sanitation revenue |  | 27 518 | 29 892 | 29 892 | 2 322 | 9 857 | 9 964 | (107) | -1% | 29 892 |
| Service charges - refuse revenue |  | 32 024 | 28 836 | 28 836 | 2 909 | 11 384 | 9 612 | 1 772 | 18% | 28 836 |
| Rental of facilities and equipment |  | 5 852 | 6 567 | 6 567 | 447 | 1 859 | 2 189 | (330) | -15% | 6 567 |
| Interest earned - external investments |  | 3 784 | 1 500 | 1 500 | 468 | 941 | 500 | 441 | 88% | 1 500 |
| Interest earned - outstanding debtors |  | 37 327 | 36 270 | 36 270 | 3 918 | 14 974 | 12 090 | 2 884 | 24% | 36 270 |
| Dividends received |  | 115 | – | – | – | – | – | – |  | – |
| Fines, penalties and forfeits |  | 4 055 | 16 920 | 16 920 | 54 | 282 | 5 640 | (5 358) | -95% | 16 920 |
| Licences and permits |  | 106 | 211 | 211 | – | – | 70 | (70) | -100% | 211 |
| Agency services |  |  |  |  |  |  |  | – |  |  |
| Transfers and subsidies |  | 168 246 | 189 039 | 189 039 | – | 78 802 | 63 013 | 15 789 | 25% | 189 039 |
| Other revenue |  | 7 204 | 15 243 | 15 243 | 606 | 2 569 | 5 081 | (2 512) | -49% | 15 243 |
| Gains on disposal of PPE |  | – | – | – | – | – | – | – |  | – |
| Total Revenue (excluding capital transfers and contributions) |  | 1 068 819 | 1 312 052 | 1 312 052 | 86 397 | 460 698 | 437 351 | 23 348 | 5% | 1 312 052 |
| Expenditure By Type |  |  |  |  |  |  |  |  |  |  |
| Employee related costs |  | 288 618 | 359 390 | 358 069 | 24 991 | 98 506 | 119 408 | (20 902) | -18% | 358 069 |
| Remuneration of councillors |  | 17 554 | 19 855 | 19 855 | 1 559 | 6 235 | 6 619 | (383) | -6% | 19 855 |
| Debt impairment |  | 234 586 | 152 751 | 152 751 | 13 729 | 50 917 | 50 917 | (0) | 0% | 152 751 |
| Depreciation & asset impairment |  | 72 118 | 83 085 | 83 085 | – | – | 27 695 | (27 695) | -100% | 83 085 |
| Finance charges |  | 8 063 | 6 448 | 6 448 | 208 | 306 | 2 149 | (1 844) | -86% | 6 448 |
| Bulk purchases |  | 397 280 | 479 007 | 479 007 | 70 887 | 168 146 | 159 669 | 8 477 | 5% | 479 007 |
| Other materials |  | 17 039 | 32 941 | 33 735 | 2 171 | 4 650 | 11 121 | (6 472) | -58% | 33 735 |
| Contracted services |  | 82 250 | 110 421 | 110 936 | 8 076 | 19 258 | 37 074 | (17 817) | -48% | 110 936 |
| Transfers and subsidies |  | 297 | 42 | 42 | – | 14 | 14 | (1) | -4% | 42 |
| Other expenditure |  | 49 950 | 66 448 | 66 459 | 6 121 | 12 098 | 22 132 | (10 033) | -45% | 66 459 |
| Loss on disposal of PPE |  | (1 514) | – | – | – | – | – | – |  | – |
| Total Expenditure |  | 1 166 241 | 1 310 388 | 1 310 388 | 127 742 | 360 129 | 436 798 | (76 669) | -18% | 1 310 388 |
| Surplus/(Deficit) |  | (97 422) | 1 665 | 1 665 | (41 345) | 100 569 | 552 | 100 017 | 0 | 1 665 |
| Transfers and subsidies - capital (monetary allocations) (National / Provincial and District) |  | 60 980 | 81 069 | 81 069 | – | – | 27 023 | (27 023) | (0) | 81 069 |
| Transfers and subsidies - capital (monetary allocations) (National / Provincial Departmental Agencies, Households, Non-profit Institutions, Private Enterprises, Public Corporatons, Higher Educational Institutions) |  | 1 611 | – | – | – | – | – | – |  | – |
| Transfers and subsidies - capital (in-kind - all) |  | 63 529 | 96 200 | 96 200 | – | – | 32 067 | (32 067) | (0) | 96 200 |
| Surplus/(Deficit) after capital transfers & contributions |  | 28 698 | 178 934 | 178 934 | (41 345) | 100 569 | 59 642 |  |  | 178 934 |
| Taxation |  |  |  |  |  |  |  | – |  |  |
| Surplus/(Deficit) after taxation |  | 28 698 | 178 934 | 178 934 | (41 345) | 100 569 | 59 642 |  |  | 178 934 |
| Attributable to minorities |  |  |  |  |  |  |  |  |  |  |
| Surplus/(Deficit) attributable to municipality |  | 28 698 | 178 934 | 178 934 | (41 345) | 100 569 | 59 642 |  |  | 178 934 |
| Share of surplus/ (deficit) of associate |  |  |  |  |  |  |  |  |  |  |
| Surplus/ (Deficit) for the year |  | 28 698 | 178 934 | 178 934 | (41 345) | 100 569 | 59 642 |  |  | 178 934 |

5.5 Monthly Budget Statement - Capital Expenditure: (municipal vote, standard classification and funding)

| FS204 Metsimaholo - Table C5 Monthly Budget Statement - Capital Expenditure (municipal vote, functional classification and funding) - M04 October |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vote Description | Ref | 2018/19 | Budget Year 2019/20 |  |  |  |  |  |  |  |
|  |  | Audited Outcome | Original Budget | Adjusted Budget | Monthly actual | YearTD actual | YearTD budget | YTD variance | YTD variance | Full Year Forecast |
| R thousands | 1 |  |  |  |  |  |  |  | % |  |
| Multi-Year expenditure appropriation | 2 |  |  |  |  |  |  |  |  |  |
| Vote 01 - Executive & Council |  | – | – | – | – | – | – | – |  | – |
| Vote 02 - Municipal Manager |  | 526 | 2 980 | 2 980 | – | – | 993 | (993) | -100% | 2 980 |
| Vote 03 - Corporate Services |  | – | 5 600 | 5 600 | – | – | 1 867 | (1 867) | -100% | 5 600 |
| Vote 04 - Social Services |  | 168 | 1 504 | 1 504 | – | – | 501 | (501) | -100% | 1 504 |
| Vote 05 - Technical Services |  | 79 753 | 167 510 | 170 345 | 4 655 | 9 674 | 56 404 | (46 730) | -83% | 170 345 |
| Vote 06 - Financial Services |  | – | – | – | – | – | – | – |  | – |
| Vote 07 - Local Economic Development And Planning |  | – | 1 000 | 1 000 | – | – | 333 | (333) | -100% | 1 000 |
| Total Capital Multi-year expenditure | 4,7 | 80 447 | 178 594 | 181 429 | 4 655 | 9 674 | 60 098 | (50 424) | -84% | 181 429 |
| Single Year expenditure appropriation | 2 |  |  |  |  |  |  |  |  |  |
| Vote 01 - Executive & Council |  | – | 80 | 80 | – | – | 27 | (27) | -100% | 80 |
| Vote 02 - Municipal Manager |  | 28 | 1 735 | 1 735 | 249 | 249 | 578 | (329) | -57% | 1 735 |
| Vote 03 - Corporate Services |  | 104 | 653 | 653 | – | 8 | 218 | (210) | -96% | 653 |
| Vote 04 - Social Services |  | 7 324 | 34 632 | 34 632 | – | – | 11 544 | (11 544) | -100% | 34 632 |
| Vote 05 - Technical Services |  | 29 219 | 77 777 | 74 942 | 2 320 | 5 435 | 25 359 | (19 924) | -79% | 74 942 |
| Vote 06 - Financial Services |  | 156 | 747 | 747 | – | 13 | 249 | (237) | -95% | 747 |
| Vote 07 - Local Economic Development And Planning |  | 60 | 300 | 300 | – | – | 100 | (100) | -100% | 300 |
| Total Capital single-year expenditure | 4 | 36 892 | 115 923 | 113 088 | 2 569 | 5 704 | 38 074 | (32 370) | -85% | 113 088 |
| Total Capital Expenditure |  | 117 339 | 294 517 | 294 517 | 7 224 | 15 378 | 98 173 | (82 794) | -84% | 294 517 |
| Capital Expenditure - Functional Classification |  |  |  |  |  |  |  |  |  |  |
| Governance and administration |  | 908 | 14 141 | 14 141 | 447 | 468 | 4 714 | (4 246) | -90% | 14 141 |
| Executive and council |  | – | 80 | 80 | – | – | 27 | (27) | -100% | 80 |
| Finance and administration |  | 908 | 14 061 | 14 061 | 447 | 468 | 4 687 | (4 219) | -90% | 14 061 |
| Internal audit |  |  |  |  |  |  |  | – |  |  |
| Community and public safety |  | 2 451 | 30 186 | 30 186 | – | – | 10 062 | (10 062) | -100% | 30 186 |
| Community and social services |  | 6 | 2 281 | 2 281 | – | – | 760 | (760) | -100% | 2 281 |
| Sport and recreation |  | 832 | 20 953 | 20 953 | – | – | 6 984 | (6 984) | -100% | 20 953 |
| Public safety |  | 1 613 | 6 951 | 6 951 | – | – | 2 317 | (2 317) | -100% | 6 951 |
| Housing |  |  |  |  |  |  |  | – |  |  |
| Health |  |  |  |  |  |  |  | – |  |  |
| Economic and environmental services |  | 23 450 | 49 468 | 49 468 | 86 | 1 244 | 16 489 | (15 245) | -92% | 49 468 |
| Planning and development |  | 60 | 1 200 | 1 200 | – | – | 400 | (400) | -100% | 1 200 |
| Road transport |  | 23 390 | 48 268 | 48 268 | 86 | 1 244 | 16 089 | (14 845) | -92% | 48 268 |
| Environmental protection |  |  |  |  |  |  |  | – |  |  |
| Trading services |  | 90 530 | 200 723 | 200 723 | 6 690 | 13 666 | 66 908 | (53 241) | -80% | 200 723 |
| Energy sources |  | 21 218 | 37 269 | 37 269 | 85 | 258 | 12 423 | (12 165) | -98% | 37 269 |
| Water management |  | 8 696 | 23 784 | 23 784 | 2 379 | 4 347 | 7 928 | (3 581) | -45% | 23 784 |
| Waste water management |  | 55 575 | 133 720 | 133 720 | 4 227 | 9 061 | 44 573 | (35 513) | -80% | 133 720 |
| Waste management |  | 5 041 | 5 950 | 5 950 | – | – | 1 983 | (1 983) | -100% | 5 950 |
| Other |  |  |  |  |  |  |  | – |  |  |
| Total Capital Expenditure - Functional Classification | 3 | 117 339 | 294 517 | 294 517 | 7 224 | 15 378 | 98 173 | (82 794) | -84% | 294 517 |
| Funded by: |  |  |  |  |  |  |  |  |  |  |
| National Government |  | 87 466 | 151 069 | 151 069 | 6 632 | 13 677 | 50 356 | (36 680) | -73% | 151 069 |
| Provincial Government |  | – | – | – | – | – | – | – |  | – |
| District Municipality |  |  |  |  |  |  |  | – |  |  |
| Other transfers and grants |  | 25 690 | 26 200 | 26 200 | – | – | 8 733 | (8 733) | -100% | 26 200 |
| Transfers recognised - capital |  | 113 156 | 177 269 | 177 269 | 6 632 | 13 677 | 59 090 | (45 413) | -77% | 177 269 |
| Borrowing | 6 | – | 55 972 | 55 972 | – | – | 18 658 | (18 658) | -100% | 55 972 |
| Internally generated funds |  | 4 183 | 61 275 | 61 275 | 592 | 1 701 | 20 425 | (18 724) | -92% | 61 275 |
| Total Capital Funding |  | 117 339 | 294 517 | 294 517 | 7 224 | 15 378 | 98 173 | (82 794) | -84% | 294 517 |

  - Monthly Budget Statement – Financial Position

| FS204 Metsimaholo - Table C6 Monthly Budget Statement - Financial Position - M04 October |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Description | Ref | 2018/19 | Budget Year 2019/20 |  |  |  |
|  |  | Audited Outcome | Original Budget | Adjusted Budget | YearTD actual | Full Year Forecast |
| R thousands | 1 |  |  |  |  |  |
| ASSETS |  |  |  |  |  |  |
| Current assets |  |  |  |  |  |  |
| Cash |  | 8 851 | 26 465 | 26 465 | 31 970 | 26 465 |
| Call investment deposits |  | 8 667 | 7 715 | 7 715 | 601 755 | 7 715 |
| Consumer debtors |  | 192 945 | 274 599 | 274 599 | 435 549 | 274 599 |
| Other debtors |  | 626 514 | 16 968 | 16 968 | 642 224 | 16 968 |
| Current portion of long-term receivables |  | – | – | – | – | – |
| Inventory |  | 1 467 | 18 676 | 18 676 | 1 319 | 18 676 |
| Total current assets |  | 838 444 | 344 423 | 344 423 | 1 712 816 | 344 423 |
| Non-current assets |  |  |  |  |  |  |
| Long-term receivables |  | – | – | – | – | – |
| Investments |  | – | – | – | – | – |
| Investment property |  | 295 201 | 86 659 | 86 659 | 295 201 | 86 659 |
| Investments in Associate |  |  |  |  |  |  |
| Property, plant and equipment |  | 1 390 096 | 1 533 977 | 1 533 977 | 1 405 225 | 1 533 977 |
| Biological |  |  |  |  |  |  |
| Intangible |  | 2 532 | 4 588 | 4 588 | 2 781 | 4 588 |
| Other non-current assets |  | 561 | 561 | 561 | 561 | 561 |
| Total non-current assets |  | 1 688 390 | 1 625 784 | 1 625 784 | 1 703 769 | 1 625 784 |
| TOTAL ASSETS |  | 2 526 834 | 1 970 207 | 1 970 207 | 3 416 585 | 1 970 207 |
| LIABILITIES |  |  |  |  |  |  |
| Current liabilities |  |  |  |  |  |  |
| Bank overdraft |  | – | – | – | – | – |
| Borrowing |  | 4 983 | 4 364 | 4 364 | 3 880 | 4 364 |
| Consumer deposits |  | 24 101 | 26 294 | 26 294 | 24 854 | 26 294 |
| Trade and other payables |  | 825 591 | 170 246 | 170 246 | 1 482 107 | 170 246 |
| Provisions |  | 129 901 | 84 208 | 84 208 | 129 901 | 84 208 |
| Total current liabilities |  | 984 576 | 285 112 | 285 112 | 1 640 742 | 285 112 |
| Non-current liabilities |  |  |  |  |  |  |
| Borrowing |  | 3 828 | 59 570 | 59 570 | 3 828 | 59 570 |
| Provisions |  | – | – | – | – | – |
| Total non-current liabilities |  | 3 828 | 59 570 | 59 570 | 3 828 | 59 570 |
| TOTAL LIABILITIES |  | 988 404 | 344 682 | 344 682 | 1 644 570 | 344 682 |
| NET ASSETS | 2 | 1 538 431 | 1 625 525 | 1 625 525 | 1 772 015 | 1 625 525 |
| COMMUNITY WEALTH/EQUITY |  |  |  |  |  |  |
| Accumulated Surplus/(Deficit) |  | 1 606 741 | 1 625 525 | 1 625 525 | 1 772 015 | 1 625 525 |
| Reserves |  | – | – | – | – | – |
| TOTAL COMMUNITY WEALTH/EQUITY | 2 | 1 606 741 | 1 625 525 | 1 625 525 | 1 772 015 | 1 625 525 |

# The year to date does not take into account the opening balances, but only reflects the net movement for the month/period.

  - Monthly Budget Statement – Cash Flow

| FS204 Metsimaholo - Table C7 Monthly Budget Statement - Cash Flow - M04 October |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description | Ref | 2018/19 | Budget Year 2019/20 |  |  |  |  |  |  |  |
|  |  | Audited Outcome | Original Budget | Adjusted Budget | Monthly actual | YearTD actual | YearTD budget | YTD variance | YTD variance | Full Year Forecast |
| R thousands | 1 |  |  |  |  |  |  |  | % |  |
| CASH FLOW FROM OPERATING ACTIVITIES |  |  |  |  |  |  |  |  |  |  |
| Receipts |  |  |  |  |  |  |  |  |  |  |
| Property rates |  | 100 875 | 124 373 | 124 373 | 18 990 | 53 915 | 41 458 | 12 458 | 30% | 124 373 |
| Service charges |  | 479 389 | 667 215 | 667 215 | 75 594 | 219 305 | 222 405 | (3 100) | -1% | 667 215 |
| Other revenue |  | 20 637 | 22 181 | 22 181 | 5 522 | 45 657 | 7 394 | 38 264 | 518% | 22 181 |
| Government - operating |  | 150 551 | 186 715 | 186 715 | – | 78 802 | 62 238 | 16 564 | 27% | 186 715 |
| Government - capital |  | 94 002 | – | – | – | 28 493 | – | 28 493 | #DIV/0! | – |
| Interest |  | 36 490 | 28 326 | 28 326 | 715 | 2 207 | 9 442 | (7 235) | -77% | 28 326 |
| Dividends |  | 107 | – | – | – | – | – | – |  | – |
| Payments |  |  |  |  |  |  |  |  |  |  |
| Suppliers and employees |  | (780 232) | (943 431) | (943 431) | (88 851) | (394 014) | (314 477) | 79 537 | -25% | (943 431) |
| Finance charges |  | (4 024) | (2 130) | (2 130) | (208) | (306) | (710) | (404) | 57% | (2 130) |
| Transfers and Grants |  | (9) | – | – | – | – | – | – |  | – |
| NET CASH FROM/(USED) OPERATING ACTIVITIES |  | 97 785 | 83 249 | 83 249 | 11 762 | 34 060 | 27 750 | (6 310) | -23% | 83 249 |
| CASH FLOWS FROM INVESTING ACTIVITIES |  |  |  |  |  |  |  |  |  |  |
| Receipts |  |  |  |  |  |  |  |  |  |  |
| Proceeds on disposal of PPE |  | – | – | – | – | – | – | – |  | – |
| Decrease (Increase) in non-current debtors |  | – | 300 | 300 | 17 453 | (52 223) | 100 | (52 323) | -52323% | 300 |
| Decrease (increase) other non-current receivables |  | – | – | – | – | – | – | – |  | – |
| Decrease (increase) in non-current investments |  |  |  |  |  |  |  | – |  |  |
| Payments |  |  |  |  |  |  |  |  |  |  |
| Capital assets |  | (86 656) | (134 537) | (134 537) | – | – | (44 846) | (44 846) | 100% | (134 537) |
| NET CASH FROM/(USED) INVESTING ACTIVITIES |  | (86 656) | (134 237) | (134 237) | 17 453 | (52 223) | (44 746) | 7 477 | -17% | (134 237) |
| CASH FLOWS FROM FINANCING ACTIVITIES |  |  |  |  |  |  |  |  |  |  |
| Receipts |  |  |  |  |  |  |  |  |  |  |
| Short term loans |  | – | – | – | – | – | – | – |  | – |
| Borrowing long term/refinancing |  | – | – | – | – | – | – | – |  | – |
| Increase (decrease) in consumer deposits |  | – | – | – | 138 | 753 | – | 753 | #DIV/0! | – |
| Payments |  |  |  |  |  |  |  |  |  |  |
| Repayment of borrowing |  | (3 312) | (5 924) | (5 924) | – | – | (1 975) | (1 975) | 100% | (5 924) |
| NET CASH FROM/(USED) FINANCING ACTIVITIES |  | (3 312) | (5 924) | (5 924) | 138 | 753 | (1 975) | (2 728) | 138% | (5 924) |
| NET INCREASE/ (DECREASE) IN CASH HELD |  | 7 817 | (56 912) | (56 912) | 29 353 | (17 410) | (18 971) |  |  | (56 912) |
| Cash/cash equivalents at beginning: |  | 12 628 | 4 696 | 4 696 |  | 35 419 |  |  |  |  |
| Cash/cash equivalents at month/year end: |  | 20 444 | (52 216) | (52 216) |  | 18 009 | (18 971) |  |  | (56 912) |

# Supporting Documentation

- Debtors’ analysis

| FS204 Metsimaholo - Supporting Table SC3 Monthly Budget Statement - aged debtors - M04 October |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description |  | Budget Year 2019/20 |  |  |  |  |  |  |  |  |  |  |  |
| R thousands | NT Code | 0-30 Days | 31-60 Days | 61-90 Days | 91-120 Days | 121-150 Dys | 151-180 Dys | 181 Dys-1 Yr | Over 1Yr | Total | Total over 90 days | Actual Bad Debts Written Off against Debtors | Impairment - Bad Debts i.t.o Council Policy |
| Debtors Age Analysis By Income Source |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Trade and Other Receivables from Exchange Transactions - Water | 1200 | 50 073 | 60 984 | 26 611 | 16 074 | 19 568 | 23 455 | 133 017 | 641 892 | 971 674 | 834 006 | 339 | 27 118 |
| Trade and Other Receivables from Exchange Transactions - Electricity | 1300 | 11 159 | 4 664 | 2 765 | 2 443 | 2 092 | 1 926 | 11 609 | 45 053 | 81 711 | 63 123 | 8 | 5 716 |
| Receivables from Non-exchange Transactions - Property Rates | 1400 | 12 874 | 9 184 | 4 643 | 10 608 | 2 472 | 2 232 | 11 788 | 79 010 | 132 810 | 106 109 | 76 | 13 638 |
| Receivables from Exchange Transactions - Waste Water Management | 1500 | 2 474 | 1 480 | 1 135 | 1 077 | 1 163 | 903 | 4 820 | 35 116 | 48 169 | 43 079 | 31 | 1 414 |
| Receivables from Exchange Transactions - Waste Management | 1600 | 2 904 | 1 757 | 1 459 | 1 394 | 1 288 | 1 257 | 6 776 | 52 507 | 69 341 | 63 221 | 42 | 1 695 |
| Receivables from Exchange Transactions - Property Rental Debtors | 1700 | – | – | – | – | – | – | – | – | – | – | – | – |
| Interest on Arrear Debtor Accounts | 1810 | 3 918 | 3 684 | 3 589 | 3 621 | 3 496 | 3 695 | 18 716 | 149 560 | 190 279 | 179 087 | – | – |
| Recoverable unauthorised, irregular, fruitless and wasteful expenditure | 1820 | – | – | – | – | – | – | – | – | – | – | – | – |
| Other | 1900 | 2 504 | 2 319 | 6 864 | 688 | 1 199 | 1 793 | 6 312 | 83 082 | 104 763 | 93 076 | – | – |
| Total By Income Source | 2000 | 85 907 | 84 071 | 47 066 | 35 905 | 31 278 | 35 260 | 193 038 | 1 086 221 | 1 598 746 | 1 381 701 | 495 | 49 580 |
| 2018/19 - totals only |  |  |  |  |  |  |  |  |  | – | – |  |  |
| Debtors Age Analysis By Customer Group |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Organs of State | 2200 | 3 445 | 3 850 | 1 397 | 726 | 652 | 983 | 7 141 | 18 414 | 36 608 | 27 915 | – | – |
| Commercial | 2300 | 30 673 | 43 349 | 5 282 | 7 447 | 3 442 | 7 671 | 13 802 | 70 452 | 182 119 | 102 815 | – | – |
| Households | 2400 | 51 789 | 36 872 | 40 386 | 27 732 | 27 184 | 26 606 | 172 095 | 997 355 | 1 380 019 | 1 250 971 | 495 | 49 580 |
| Other | 2500 | – | – | – | – | – | – | – | – | – | – | – | – |
| Total By Customer Group | 2600 | 85 907 | 84 071 | 47 066 | 35 905 | 31 278 | 35 260 | 193 038 | 1 086 221 | 1 598 746 | 1 381 701 | 495 | 49 580 |

No Consumer debts were written off in terms of the Credit Control and Debt Collection Policy during October 2019

- Creditors’ analysis

| FS204 Metsimaholo - Supporting Table SC4 Monthly Budget Statement - aged creditors - M04 October |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description | NT Code | Budget Year 2019/20 |  |  |  |  |  |  |  |  |
|  |  | 0 - 30 Days | 31 - 60 Days | 61 - 90 Days | 91 - 120 Days | 121 - 150 Days | 151 - 180 Days | 181 Days - 1 Year | Over 1 Year | Total |
| R thousands |  |  |  |  |  |  |  |  |  |  |
| Creditors Age Analysis By Customer Type |  |  |  |  |  |  |  |  |  |  |
| Bulk Electricity | 0100 | 22 045 | – | – | – | – | – | – | – | 22 045 |
| Bulk Water | 0200 | 19 130 | 800 | 800 | 1 980 | 1 054 | 35 875 | – | – | 59 640 |
| PAYE deductions | 0300 | – | – | – | – | – | – | – | – | – |
| VAT (output less input) | 0400 | – | – | – | – | – | – | – | – | – |
| Pensions / Retirement deductions | 0500 | – | – | – | – | – | – | – | – | – |
| Loan repayments | 0600 | – | – | – | – | – | – | – | – | – |
| Trade Creditors | 0700 | – | – | – | – | – | – | – | – | – |
| Auditor General | 0800 | 2 976 | – | – | – | – | – | – | – | 2 976 |
| Other | 0900 | 9 105 | 696 | 2 299 | 59 | – | – | – | 61 466 | 73 625 |
| Total By Customer Type | 1000 | 53 258 | 1 496 | 3 099 | 2 039 | 1 054 | 35 875 | – | 61 466 | 158 287 |

Trade creditors include outstanding orders, as a commitment is already made.

The amount becomes payable when the work is completed or when the service is delivered.

- Investment portfolio analyses

# FS204 Metsimaholo - Supporting Table SC5 Monthly Budget Statement - investment portfolio - M04 October

| Investments by maturity Name of institution & investment ID |  | Ref | Period of Investment |  | Type of Investment |  | Capital Guarantee (Yes/ No) | Variable or Fixed interest rate | Opening balance | Interest to be realised | Partial / Premature Withdrawal (4) | Investment Top Up | Closing Balance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R thousands |  |  | Yrs/Months |  |  |  |  |  |  |  |  |  |  |
| Municipality |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ABSA BANK |  |  |  |  | Call |  |  | 6.30% | 12 055 | 40 | (9 100) | – | 2 955 |
| NEDBANK |  |  |  |  | Call |  |  | 6.25% | 1 461 | 7 | – | – | 1 461 |
| FNB |  |  |  |  | Call |  |  | 6.10% | 7 185 | 38 | – | 151 | 7 336 |
| STANDARD BANK |  |  |  |  | Call |  |  | 6.30% | 1 093 | 49 | – | 6 998 | 8 091 |
| INVESTEC |  |  |  |  | Call |  |  | 6.35% | 683 | 3 | (20) | – | 663 |
| FIXED |  |  |  |  | 32 days |  |  | 7.20% | 30 061 | 189 | – | – | 30 061 |
| Municipality sub-total |  |  |  |  |  |  |  |  | 52 538 |  | (9 120) | 7 149 | 50 567 |
| TOTAL INVESTMENTS AND INTEREST |  | 2 |  |  |  |  |  |  | 52 538 |  | (9 120) | 7 149 | 50 567 |

- Allocation and grant receipts and expenditure

| FS204 Metsimaholo - Supporting Table SC6 Monthly Budget Statement - transfers and grant receipts - M04 October |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description | Ref | 2018/19 | Budget Year 2019/20 |  |  |  |  |  |  |  |
|  |  | Audited Outcome | Original Budget | Adjusted Budget | Monthly actual | YearTD actual | YearTD budget | YTD variance | YTD variance | Full Year Forecast |
| R thousands |  |  |  |  |  |  |  |  | % |  |
| RECEIPTS: | 1,2 |  |  |  |  |  |  |  |  |  |
| Operating Transfers and Grants |  |  |  |  |  |  |  |  |  |  |
| National Government: |  | 171 101 | 192 431 | 192 431 | – | 81 327 | 64 144 | 17 183 | 26.8% | 192 431 |
| Equitable Share |  | 163 296 | 183 064 | 183 064 | – | 76 277 | 61 021 | 15 256 | 25.0% | 183 064 |
| Expanded Public Works Programme Integrated Grant |  | 2 170 | 2 314 | 2 314 | – | 580 | 771 | (191) | -24.8% | 2 314 |
| Local Government Financial Management Grant |  | 3 540 | 4 470 | 4 470 | – | 4 470 | 1 490 | 2 980 | 200.0% | 4 470 |
| Municipal Infrastructure Grant |  | 2 095 | 2 583 | 2 583 | – | – | 861 | (861) | -100.0% | 2 583 |
| Municipal Systems Improvement Grant |  | – | – | – | – | – | – | – |  | – |
| Operation Clean Audit | 3 | – | – | – | – | – | – | – |  | – |
| Other transfers and grants [insert description] |  |  |  |  |  |  |  | – |  |  |
| Provincial Government: |  | – | – | – | – | – | – | – |  | – |
|  |  |  |  |  |  |  |  | – |  |  |
| Other transfers and grants [insert description] |  |  |  |  |  |  |  | – |  |  |
| District Municipality: |  | – | – | – | – | – | – | – |  | – |
| [insert description] |  |  |  |  |  |  |  | – |  |  |
| Other grant providers: |  | – | – | – | – | – | – | – |  | – |
| Auditor-General |  | – | – | – | – | – | – | – |  | – |
| Government Motor Transport |  | – | – | – | – | – | – | – |  | – |
| Unspecified |  | – | – | – | – | – | – | – |  | – |
| Total Operating Transfers and Grants | 5 | 171 101 | 192 431 | 192 431 | – | 81 327 | 64 144 | 17 183 | 26.8% | 192 431 |
| Capital Transfers and Grants |  |  |  |  |  |  |  |  |  |  |
| National Government: |  | 60 980 | 74 069 | 74 069 | – | – | 24 690 | (24 690) | -100.0% | 74 069 |
| Integrated National Electrification Programme |  | – | – | – | – | – | – | – |  | – |
| Integrated National Electrification Programme Grant |  | 3 289 | 10 000 | 10 000 | – | – | 3 333 | (3 333) | -100.0% | 10 000 |
| Municipal Infrastructure Grant |  | 47 691 | 49 069 | 49 069 | – | – | 16 356 | (16 356) | -100.0% | 49 069 |
| Municipal Water Infrastructure Grant |  | – | – | – | – | – | – | – |  | – |
| Regional Bulk Infrastructure Grant |  | – | – | – | – | – | – | – |  | – |
| Water Services Infrastructure Grant |  | 10 000 | 15 000 | 15 000 | – | – | 5 000 | (5 000) | -100.0% | 15 000 |
| Provincial Government: |  | – | 33 200 | 33 200 | – | – | 11 067 | (11 067) | -100.0% | 33 200 |
| Specify (Add grant description) |  | – | 33 200 | 33 200 | – | – | 11 067 | (11 067) | -100.0% | 33 200 |
| Sports and Recreation |  | – | – | – | – | – | – | – |  | – |
| District Municipality: |  | – | – | – | – | – | – | – |  | – |
| [insert description] |  |  |  |  |  |  |  | – |  |  |
| Other grant providers: |  | 65 141 | 70 000 | 70 000 | – | – | 23 333 | (23 333) | -100.0% | 70 000 |
| [insert description] |  |  |  |  |  |  |  | – |  |  |
| Government Motor Transport |  | 1 611 | – | – | – | – | – | – |  | – |
| Production |  | 39 450 | 70 000 | 70 000 | – | – | 23 333 | (23 333) | -100.0% | 70 000 |
| Unspecified |  | 24 079 | – | – | – | – | – | – |  | – |
| Total Capital Transfers and Grants | 5 | 126 120 | 177 269 | 177 269 | – | – | 59 090 | (59 090) | -100.0% | 177 269 |
| TOTAL RECEIPTS OF TRANSFERS & GRANTS | 5 | 297 221 | 369 700 | 369 700 | – | 81 327 | 123 233 | (41 906) | -34.0% | 369 700 |

| FS204 Metsimaholo - Supporting Table SC7(1) Monthly Budget Statement - transfers and grant expenditure - M04 October |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description | Ref | 2018/19 | Budget Year 2019/20 |  |  |  |  |  |  |  |
|  |  | Audited Outcome | Original Budget | Adjusted Budget | Monthly actual | YearTD actual | YearTD budget | YTD variance | YTD variance | Full Year Forecast |
| R thousands |  |  |  |  |  |  |  |  | % |  |
| EXPENDITURE |  |  |  |  |  |  |  |  |  |  |
| Operating expenditure of Transfers and Grants |  |  |  |  |  |  |  |  |  |  |
| National Government: |  | 20 445 | 28 368 | 25 368 | 6 719 | 26 440 | 26 440 | – |  | 25 368 |
|  |  |  |  |  |  |  |  | – |  |  |
| Department of Environmental Affairs |  | – | – | – | – | – | – | – |  | – |
| Equitable Share |  | 16 907 | 19 156 | 19 156 | 6 355 | 24 690 | 24 690 | – |  | 19 156 |
| Expanded Public Works Programme Integrated Grant |  | – | – | – | 136 | 504 | 504 | – |  | – |
| Local Government Financial Management Grant |  | 1 339 | 6 470 | 3 470 | 48 | 508 | 508 | – |  | 3 470 |
| Municipal Infrastructure Grant |  | 2 199 | 2 741 | 2 741 | 180 | 738 | 738 | – |  | 2 741 |
| Provincial Government: |  | – | – | – | – | – | – | – |  | – |
|  |  |  |  |  |  |  |  | – |  |  |
| District Municipality: |  | – | – | – | – | – | – | – |  | – |
|  |  |  |  |  |  |  |  | – |  |  |
| Other grant providers: |  | 311 | – | – | – | – | – | – |  | – |
| Unspecified |  | 311 | – | – | – | – | – | – |  | – |
| Total operating expenditure of Transfers and Grants: |  | 20 756 | 28 368 | 25 368 | 6 719 | 26 440 | 26 440 | – |  | 25 368 |
| Capital expenditure of Transfers and Grants |  |  |  |  |  |  |  |  |  |  |
| National Government: |  | 87 466 | 151 069 | 151 069 | 7 627 | 15 728 | 15 728 | – |  | 151 069 |
| Integrated National Electrification Programme Grant |  | 2 907 | 10 000 | 10 000 | – | – | – | – |  | 10 000 |
| Municipal Infrastructure Grant |  | 41 107 | 56 069 | 56 069 | 5 058 | 10 948 | 10 948 | – |  | 56 069 |
| Regional Bulk Infrastructure Grant |  | 34 756 | 80 000 | 80 000 | – | – | – | – |  | 80 000 |
| Water Services Infrastructure Grant |  | 8 696 | 5 000 | 5 000 | 2 569 | 4 781 | 4 781 | – |  | 5 000 |
| Provincial Government: |  | – | – | – | – | – | – | – |  | – |
| Housing |  | – | – | – | – | – | – | – |  | – |
| Water Supply Infrastructure |  | – | – | – | – | – | – | – |  | – |
| District Municipality: |  | – | – | – | – | – | – | – |  | – |
|  |  |  |  |  |  |  |  | – |  |  |
| Other grant providers: |  | 25 690 | 26 200 | 26 200 | – | – | 6 550 | (6 550) | -100.0% | 26 200 |
| Buildings and Construction |  | – | – | – | – | – | – | – |  | – |
| Government Motor Transport |  | 1 611 | – | – | – | – | – | – |  | – |
| Households |  | – | – | – | – | – | – | – |  | – |
| Human Settlement Re-development Programme |  | – | 26 200 | 26 200 | – | – | 6 550 | (6 550) | -100.0% | 26 200 |
| South Africa Sport Commission |  | – | – | – | – | – | – | – |  | – |
| Unspecified |  | 24 079 | – | – | – | – | – | – |  | – |
| Total capital expenditure of Transfers and Grants |  | 113 156 | 177 269 | 177 269 | 7 627 | 15 728 | 22 278 | (6 550) | -29.4% | 177 269 |
| TOTAL EXPENDITURE OF TRANSFERS AND GRANTS |  | 133 912 | 205 637 | 202 637 | 14 345 | 42 168 | 48 718 | (6 550) | -13.4% | 202 637 |

10. Councillor allowance and employee benefit

| FS204 Metsimaholo - Supporting Table SC8 Monthly Budget Statement - councillor and staff benefits - M04 October |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Summary of Employee and Councillor remuneration | Ref | 2018/19 | Budget Year 2019/20 |  |  |  |  |  |  |  |
|  |  | Audited Outcome | Original Budget | Adjusted Budget | Monthly actual | YearTD actual | YearTD budget | YTD variance | YTD variance | Full Year Forecast |
| R thousands |  |  |  |  |  |  |  |  | % |  |
|  | 1 | A | B | C |  |  |  |  |  | D |
| Councillors (Political Office Bearers plus Other) |  |  |  |  |  |  |  |  |  |  |
| Basic Salaries and Wages |  | 12 576 | 14 457 | 14 457 | 1 130 | 4 527 | 4 819 | (292) | -6% | 14 457 |
| Pension and UIF Contributions |  | – | – | – | – | – | – | – |  | – |
| Medical Aid Contributions |  |  |  |  |  |  |  | – |  |  |
| Motor Vehicle Allowance |  |  |  |  |  |  |  | – |  |  |
| Cellphone Allowance |  | 1 706 | 2 004 | 2 004 | 143 | 571 | 668 | (97) | -14% | 2 004 |
| Housing Allowances |  | – | – | – | – | – | – | – |  | – |
| Other benefits and allowances |  | 3 271 | 3 394 | 3 394 | 286 | 1 137 | 1 131 | 6 | 1% | 3 394 |
| Sub Total - Councillors |  | 17 554 | 19 855 | 19 855 | 1 559 | 6 235 | 6 619 | (383) | -6% | 19 855 |
| % increase | 4 |  | 13.1% | 13.1% |  |  |  |  |  | 13.1% |
| Senior Managers of the Municipality | 3 |  |  |  |  |  |  |  |  |  |
| Basic Salaries and Wages |  | 1 830 | 8 086 | 8 086 | 124 | 496 | 2 695 | (2 199) | -82% | 8 086 |
| Pension and UIF Contributions |  | 2 | 19 | 19 | 0 | 1 | 6 | (6) | -90% | 19 |
| Medical Aid Contributions |  | – | – | – | – | – | – | – |  | – |
| Overtime |  | – | – | – | – | – | – | – |  | – |
| Performance Bonus |  | – | 815 | 815 | – | – | 272 | (272) | -100% | 815 |
| Motor Vehicle Allowance |  | 244 | 258 | 258 | 20 | 80 | 86 | (6) | -7% | 258 |
| Cellphone Allowance |  | 41 | 167 | 167 | 3 | 12 | 56 | (44) | -78% | 167 |
| Housing Allowances |  | – | – | – | – | – | – | – |  | – |
| Other benefits and allowances |  | 3 444 | 1 829 | 1 829 | 319 | 1 457 | 610 | 847 | 139% | 1 829 |
| Payments in lieu of leave |  | 367 | 108 | 108 | – | – | 36 | (36) | -100% | 108 |
| Long service awards |  | – | – | – | – | – | – | – |  | – |
| Post-retirement benefit obligations | 2 | (2 733) | – | – | – | – | – | – |  | – |
| Sub Total - Senior Managers of Municipality |  | 3 195 | 11 280 | 11 280 | 466 | 2 045 | 3 760 | (1 715) | -46% | 11 280 |
| % increase | 4 |  | 253.0% | 253.0% |  |  |  |  |  | 253.0% |
| Other Municipal Staff |  |  |  |  |  |  |  |  |  |  |
| Basic Salaries and Wages |  | 157 896 | 213 171 | 211 634 | 13 954 | 55 855 | 70 620 | (14 765) | -21% | 211 634 |
| Pension and UIF Contributions |  | 27 360 | 29 921 | 29 921 | 2 484 | 9 612 | 9 974 | (362) | -4% | 29 921 |
| Medical Aid Contributions |  | 17 227 | 19 355 | 19 355 | 1 452 | 5 844 | 6 452 | (608) | -9% | 19 355 |
| Overtime |  | 23 196 | 24 101 | 24 101 | 1 959 | 7 091 | 8 034 | (943) | -12% | 24 101 |
| Performance Bonus |  | 12 932 | 15 149 | 15 149 | 1 165 | 4 100 | 5 050 | (950) | -19% | 15 149 |
| Motor Vehicle Allowance |  | 18 534 | 21 581 | 21 581 | 1 673 | 6 619 | 7 194 | (575) | -8% | 21 581 |
| Cellphone Allowance |  | 1 224 | 1 511 | 1 511 | 109 | 449 | 504 | (55) | -11% | 1 511 |
| Housing Allowances |  | 2 433 | 2 180 | 2 180 | 207 | 842 | 727 | 115 | 16% | 2 180 |
| Other benefits and allowances |  | 10 393 | 10 880 | 11 097 | 1 192 | 4 330 | 3 674 | 656 | 18% | 11 097 |
| Payments in lieu of leave |  | 838 | 1 517 | 1 517 | 105 | 347 | 506 | (159) | -31% | 1 517 |
| Long service awards |  | 1 139 | 744 | 744 | 50 | 668 | 248 | 420 | 169% | 744 |
| Post-retirement benefit obligations | 2 | 12 252 | 7 998 | 7 998 | 174 | 706 | 2 666 | (1 960) | -74% | 7 998 |
| Sub Total - Other Municipal Staff |  | 285 423 | 348 109 | 346 789 | 24 525 | 96 461 | 115 648 | (19 187) | -17% | 346 789 |
| % increase | 4 |  | 22.0% | 21.5% |  |  |  |  |  | 21.5% |
| Total Parent Municipality |  | 306 172 | 379 245 | 377 925 | 26 550 | 104 741 | 126 026 | (21 285) | -17% | 377 925 |
| TOTAL SALARY, ALLOWANCES & BENEFITS |  | 306 172 | 379 245 | 377 925 | 26 550 | 104 741 | 126 026 | (21 285) | -17% | 377 925 |
| % increase | 4 |  | 23.9% | 23.4% |  |  |  |  |  | 23.4% |
| TOTAL MANAGERS AND STAFF |  | 288 618 | 359 390 | 358 069 | 24 991 | 98 506 | 119 408 | (20 902) | -18% | 358 069 |

# 11. Material variances to the Service Delivery and Budget Implementation Plan

# 11.1   Actual revenue must be at least at 33.3% of the budget and expenditure cannot exceed 33.3% of the budget. All the transactions for the year, especially on expenditure have not been processed.

# If there is no budget amount on revenue, it means that revenue was received that was not anticipated.

|  | Revenue less than 33,33% by end of October 2019 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Vote number | Description | Budget | YTD Movement | Unspent Bud | Perc | Reasons for variance |
|  | MUNICIPAL MANAGER |  |  |  |  |  |
| 12001040530000000000 | PENALTIES: TENDER WITHDRAWAL | -600 000.00 | -37 757.25 | -562 242.75 | 6.29 |  |
|  | CORPORATE SERVICES |  |  |  |  |  |
| 13001424500000000000 | PARKING FEES | -50 000.00 | -14 252.18 | -35 747.82 | 28.50 |  |
|  | SOCIAL SERVICES |  |  |  |  |  |
| 14001040080000000000 | FINES: TRAFFIC - COURT FINES | -3 320 100.00 | -244 487.59 | -3 075 612.41 | 7.36 |  |
| 14001178910000000000 | TS_O_M_NG_EPWP GRANT | -1 157 000.00 | -290 000.00 | -867 000.00 | 25.06 |  |
| 14001179100000000000 | TS_O_M_NRF_EQUITABLE SHARE | -19 029 940.00 | -3 051 872.10 | -15 978 067.90 | 16.03 |  |
| 14001322010000000000 | WASTE MANGEMENT: DISPOSAL FACILITIES | -544 430.00 | -71 436.34 | -472 993.66 | 13.12 |  |
| 15001400880000000000 | N-M-R PPE: S/LINE-COMMUNITY ASSETS | -319 400.00 | -6 217.40 | -313 182.60 | 1.94 |  |
| 15001401090000000000 | N-M-R PPE: AD HOC-COMMUNITY ASSETS | 0.00 | -2 000.00 | 2 000.00 | 0.00 |  |
| 15001401100000000000 | N-M-R PPE: AD HOC-OTHER ASSETS | -587 300.00 | -29 635.66 | -557 664.34 | 5.04 |  |
| 15001420610000000000 | CEMETERY & BURIAL | -495 000.00 | -130 228.48 | -364 771.52 | 26.30 |  |
| 15001421210000000000 | ENTRANCE FEES | -1 100 000.00 | -202 725.55 | -897 274.45 | 18.42 |  |
|  | TECHNICAL SERVICES |  |  |  |  |  |
| 16001179100000000000 | TS_O_M_NRF_EQUITABLE SHARE | -34 593 890.00 | -5 848 725.38 | -28 745 164.62 | 16.90 |  |
| 16001321080000000000 | ELEC: METER READING FEES | 0.00 | -11 400.00 | 11 400.00 | 0.00 |  |
| 16001321120000000000 | ELEC SALES: COMMERC CONVEN SINGLE PHASE | -49 952 640.00 | -11 793 665.66 | -38 158 974.34 | 23.60 |  |
| 16001321160000000000 | ELEC SALES: DOMESTI LOW HOME LIGHT 1 60A | -27 345 670.00 | -8 594 104.81 | -18 751 565.19 | 31.42 |  |
| 16001321270000000000 | ELEC SALES: INDUSTR 11 000 VOLTS (HIGH) | -1 611 060.00 | -447 491.13 | -1 163 568.87 | 27.77 |  |
| 16001321310000000000 | ELEC SALES: SPORT/CHURCH/HOLIDAY/OLD-AGE | -8 799 420.00 | -1 485 910.18 | -7 313 509.82 | 16.88 |  |
| 16001321330000000000 | ELEC SALES: WATER PUMPS | -1 848 770.00 | -227 385.39 | -1 621 384.61 | 12.29 |  |
| 16001321380000000000 | ELEC: AVAILABILITY CHARGES | -12 766 790.00 | -3 788 731.66 | -8 978 058.34 | 29.67 |  |
| 16001323020000000000 | WASTE WATER MANG: SANITATION CHARGES | -23 051 080.00 | -7 128 318.76 | -15 922 761.24 | 30.92 |  |
| 16001323060000000000 | WASTE WATER MANG: AVAILABILITY CHARGES | -5 172 950.00 | -1 140 360.64 | -4 032 589.36 | 22.04 |  |
| 16001323070000000000 | WASTE WATER MANG: CONNECTION/RECONNECTIO | 0.00 | -16 367.54 | 16 367.54 | 0.00 |  |
| 16001324010000000000 | WATER: METER READING FEES | 0.00 | -50 570.00 | 50 570.00 | 0.00 |  |
| 16001324060000000000 | WATER: INDUSTRIAL WATER | -287 972 080.00 | -90 723 684.38 | -197 248 395.62 | 31.50 |  |
| 16001424540000000000 | PLAN & DEV: BUILDING PLAN APPROVAL | -5 840.00 | -305.61 | -5 534.39 | 5.23 |  |
| 16001424570000000000 | PLAN & DEV: DRAINAGE FEES | 0.00 | -3 217.52 | 3 217.52 | 0.00 |  |
|  | FINANCIAL SERVICES |  |  |  |  |  |
| 17001021500000000000 | FARM PROPERTIES: AGRICULTURAL PURPOSES | -3 135 770.00 | -540 997.26 | -2 594 772.74 | 17.25 |  |
| 17001025100000000000 | RESIDENTIAL PROPERTIES: DEVELOPED | -89 071 610.00 | -27 453 679.07 | -61 617 930.93 | 30.82 |  |
| 17001025110000000000 | RESIDENTIAL PROPERTIES: VACANT LAND | -9 765 300.00 | -727 105.83 | -9 038 194.17 | 7.44 |  |
| 17001025460000000000 | STATE-OWNED PROPERTIES | -15 688 960.00 | -1 877 490.26 | -13 811 469.74 | 11.96 |  |
| 17001380010000000000 | ADMINISTRATIVE HANDLING FEES | 0.00 | -9 574.73 | 9 574.73 | 0.00 | Incorrect allocation – journal to correct |
| 17001423310000000000 | LEGAL FEES | -5 300 000.00 | -1 056 840.63 | -4 243 159.37 | 19.94 |  |
|  | LED |  |  |  |  |  |
| 18001401100000000000 | N-M-R PPE: AD HOC-OTHER ASSETS | -5 655 210.00 | -1 802 417.94 | -3 852 792.06 | 31.87 |  |
| 18001424550000000000 | PLAN & DEV: BUILDING PLAN CLAUSE LEVY | -300 000.00 | -63 772.28 | -236 227.72 | 21.25 |  |
| 18001425430000000000 | SALE OF: AGRIC PROD - ASSET < CAP THRESH | -5 107 260.00 | -154 987.00 | -4 952 273.00 | 3.03 |  |

|  | Expenditure more than 33,33% by end of October 2019 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Vote number | Description | Budget | YTD Movement | Unspent Bud | Perc | Reasons for variance |
|  | COUNCIL |  |  |  |  |  |
| 11002110220000000000 | MS: ALL - CELLULAR & TELEPHONE | 128 380.00 | 51 121.25 | 77 258.75 | 39.82 |  |
| 11002110380000000000 | MS: OVERTIME - STRUCTURED | 543 460.00 | 277 776.63 | 265 683.37 | 51.11 |  |
| 11002110440000000000 | MS: SRB - ACTING ALLOWANCE | 115 000.00 | 52 721.01 | 62 278.99 | 45.84 |  |
| 11002110500000000000 | MS: SRB - LONG SERVICE AWARD | 89 550.00 | 52 301.65 | 37 248.35 | 58.40 |  |
| 11002110560000000000 | MS: SRB - STANDBY ALLOWANCE | 10 000.00 | 31 546.13 | -21 546.13 | 315.46 |  |
| 11002130300000000000 | MS: SOC CONTR - PENSION | 342 070.00 | 214 340.65 | 127 729.35 | 62.65 |  |
| 11002210310000000000 | WHIP: OFFICE-BEARER ALLOWANCE | 513 680.00 | 216 067.68 | 297 612.32 | 42.06 |  |
| 11002210650000000000 | EXEC MAYOR: TRAVELLING ALLOWANCE | 212 000.00 | 71 622.60 | 140 377.40 | 33.78 |  |
| 11002211250000000000 | EXCO: TRAVELLING ALLOWANCE | 710 200.00 | 257 841.20 | 452 358.80 | 36.30 |  |
| 11002211550000000000 | OTH COUNCIL: TRAVELLING ALLOWANCE | 1 060 000.00 | 361 519.94 | 698 480.06 | 34.10 |  |
| 11002285430000000000 | CONTR: STAGE & SOUND CREW | 119 830.00 | 65 400.00 | 54 430.00 | 54.57 |  |
| 11002362540000000000 | INT PAID: FINANCE LEASES | 37 510.00 | 13 788.68 | 23 721.32 | 36.76 |  |
|  | MUNICIPAL MANAGER |  |  |  |  |  |
| 12002030180000000000 | SM MM: SRB - ACTING & POST RELATED ALLOW | 300 000.00 | 428 450.06 | -128 450.06 | 142.81 |  |
| 12002110260000000000 | MS: HB & INC: HOUSING BENEFITS | 182 420.00 | 65 451.67 | 116 968.33 | 35.87 |  |
| 12002110460000000000 | MS: SRB - ANNUAL BONUS | 882 470.00 | 307 340.17 | 575 129.83 | 34.82 |  |
| 12002110560000000000 | MS: SRB - STANDBY ALLOWANCE | 66 400.00 | 27 760.60 | 38 639.40 | 41.80 |  |
| 12002140080000000000 | MS: PRB - MED: PAST SERVICE COST | 108 830.00 | 36 487.16 | 72 342.84 | 33.52 |  |
| 12002265170000000000 | OS: PRINTING SERVICES | 403 500.00 | 196 777.27 | 206 722.73 | 48.76 |  |
| 12002362540000000000 | INT PAID: FINANCE LEASES | 27 870.00 | 13 857.44 | 14 012.56 | 49.72 |  |
|  | CORPORATE SERVICES |  |  |  |  |  |
| 13002030980000000000 | SM D01: SRB - ACTING & POST RELATE ALLOW | 222 500.00 | 208 790.55 | 13 709.45 | 93.83 |  |
| 13002110220000000000 | MS: ALL - CELLULAR & TELEPHONE | 113 200.00 | 41 927.67 | 71 272.33 | 37.03 |  |
| 13002110340000000000 | MS: ALL - TRAVEL OR MOTOR VEHICLE | 1 759 790.00 | 623 769.17 | 1 136 020.83 | 35.44 |  |
| 13002110440000000000 | MS: SRB - ACTING ALLOWANCE | 139 250.00 | 125 887.51 | 13 362.49 | 90.40 |  |
| 13002110560000000000 | MS: SRB - STANDBY ALLOWANCE | 12 600.00 | 4 482.72 | 8 117.28 | 35.57 |  |
| 13002130010000000000 | MS: SOC CONTR - BARGAINING COUNCIL | 3 870.00 | 1 362.03 | 2 507.97 | 35.19 |  |
| 13002260620000000000 | OS: CLEANING SERVICES | 1 535 000.00 | 969 002.88 | 565 997.12 | 63.12 |  |
| 13002303330000000000 | OC: LIC - VEHICLE LIC & REGISTRATIONS | 2 630.00 | 1 345.00 | 1 285.00 | 51.14 |  |
| 13002304520000000000 | OC: PROFESSIONAL BODIES M/SHIP & SUBS | 3 212 610.00 | 3 178 072.00 | 34 538.00 | 98.92 |  |
|  | SOCIAL SERVICES |  |  |  |  |  |
| 14002031360000000000 | SM D02: SRB - ENTERTAINMENT | 2 000.00 | 1 833.91 | 166.09 | 91.69 |  |
| 14002031380000000000 | SM D02: SRB - ACTING & POST RELATE ALLOW | 215 000.00 | 208 790.55 | 6 209.45 | 97.11 |  |
| 14002110260000000000 | MS: HB & INC: HOUSING BENEFITS | 335 570.00 | 236 500.79 | 99 069.21 | 70.47 |  |
| 14002110320000000000 | MS: ALL - LEAVE PAY | 162 250.00 | 104 005.35 | 58 244.65 | 64.10 |  |
| 14002110400000000000 | MS: PAYMENTS - SHIFT ADD REMUNERATION | 1 401 120.00 | 1 195 093.73 | 206 026.27 | 85.29 |  |
| 14002110440000000000 | MS: SRB - ACTING ALLOWANCE | 225 970.00 | 169 596.99 | 56 373.01 | 75.05 |  |
| 14002110500000000000 | MS: SRB - LONG SERVICE AWARD | 215 000.00 | 169 085.93 | 45 914.07 | 78.64 |  |
| 14002130100000000000 | MS: SOC CONTR - GROUP LIFE INSURANCE | 52 100.00 | 17 824.98 | 34 275.02 | 34.21 |  |
| 14002303330000000000 | OC: LIC - VEHICLE LIC & REGISTRATIONS | 324 710.00 | 129 558.00 | 195 152.00 | 39.89 |  |
| 1400232061F000000000 | INV - CONSUMABL STORES -ZERO RATED FLEET | 1 692 360.00 | 723 721.58 | 968 638.42 | 42.76 |  |
| 1400232360F000000000 | INVENTORY - MATERIALS & SUPPLIES FLEET | 1 307 500.00 | 687 531.76 | 619 968.24 | 52.58 |  |
| 14002599400000000000 | HH SSP SOC ASS: SOCIAL RELIEF | 31 000.00 | 13 500.00 | 17 500.00 | 43.54 |  |
| 15002110380000000000 | MS: OVERTIME - STRUCTURED | 1 940 880.00 | 707 085.36 | 1 233 794.64 | 36.43 |  |
| 15002110440000000000 | MS: SRB - ACTING ALLOWANCE | 256 290.00 | 138 009.36 | 118 280.64 | 53.84 |  |
| 15002110460000000000 | MS: SRB - ANNUAL BONUS | 1 551 630.00 | 564 282.05 | 987 347.95 | 36.36 |  |
| 15002110500000000000 | MS: SRB - LONG SERVICE AWARD | 21 500.00 | 137 039.71 | -115 539.71 | 637.39 |  |
| 15002110560000000000 | MS: SRB - STANDBY ALLOWANCE | 67 500.00 | 27 907.47 | 39 592.53 | 41.34 |  |
| 15002130010000000000 | MS: SOC CONTR - BARGAINING COUNCIL | 14 640.00 | 4 882.65 | 9 757.35 | 33.35 |  |
| 15002130300000000000 | MS: SOC CONTR - PENSION | 3 304 360.00 | 1 108 720.40 | 2 195 639.60 | 33.55 |  |
| 15002140080000000000 | MS: PRB - MED: PAST SERVICE COST | 103 470.00 | 50 321.98 | 53 148.02 | 48.63 |  |
| 15002303330000000000 | OC: LIC - VEHICLE LIC & REGISTRATIONS | 23 020.00 | 19 199.50 | 3 820.50 | 83.40 |  |
|  | TECHNICAL SERVICES |  |  |  |  |  |
| 16002031780000000000 | SM D03: SRB - ACTING & POST RELATE ALLOW | 322 500.00 | 203 538.54 | 118 961.46 | 63.11 |  |
| 16002110220000000000 | MS: ALL - CELLULAR & TELEPHONE | 307 850.00 | 105 657.04 | 202 192.96 | 34.32 |  |
| 16002110380000000000 | MS: OVERTIME - STRUCTURED | 7 992 470.00 | 3 250 315.12 | 4 742 154.88 | 40.66 |  |
| 16002110440000000000 | MS: SRB - ACTING ALLOWANCE | 874 140.00 | 438 760.61 | 435 379.39 | 50.19 |  |
| 16002110560000000000 | MS: SRB - STANDBY ALLOWANCE | 1 926 830.00 | 1 190 835.29 | 735 994.71 | 61.80 |  |
| 16002303330000000000 | OC: LIC - VEHICLE LIC & REGISTRATIONS | 172 160.00 | 68 310.00 | 103 850.00 | 39.67 |  |
| 16002305760000000000 | OC: T&S DOM - ACCOMMODATION | 50 980.00 | 27 049.14 | 23 930.86 | 53.05 |  |
| 1600232061F000000000 | INV - CONSUMABL STORES -ZERO RATED FLEET | 2 007 340.00 | 805 194.84 | 1 202 145.16 | 40.11 |  |
| 16002349900000000000 | SUB TOTAL : BULK PURCHASES | 479 006 620.00 | 168 145 940.22 | 310 860 679.78 | 35.10 |  |
|  | FINANCIAL SERVICES |  |  |  |  |  |
| 17002030580000000000 | SM CFO: SRB - ACTING & POST RELATE ALLOW | 430 000.00 | 201 342.28 | 228 657.72 | 46.82 | Acting for CFO- foreseen that CFO be appointed during financial year |
| 17002110260000000000 | MS: HB & INC: HOUSING BENEFITS | 256 720.00 | 87 699.30 | 169 020.70 | 34.16 |  |
| 17002110440000000000 | MS: SRB - ACTING ALLOWANCE | 320 000.00 | 114 436.70 | 205 563.30 | 35.76 |  |
| 17002110460000000000 | MS: SRB - ANNUAL BONUS | 2 005 460.00 | 876 553.76 | 1 128 906.24 | 43.70 |  |
| 17002110500000000000 | MS: SRB - LONG SERVICE AWARD | 161 250.00 | 244 829.77 | -83 579.77 | 151.83 | To be adjusted with adjustment budget |
| 17002130010000000000 | MS: SOC CONTR - BARGAINING COUNCIL | 10 170.00 | 3 539.83 | 6 630.17 | 34.80 |  |
| 17002130100000000000 | MS: SOC CONTR - GROUP LIFE INSURANCE | 63 630.00 | 21 574.39 | 42 055.61 | 33.90 |  |
| 17002265110000000000 | OS: CONNECT/DIS-CONNECTION: ELECTICITY | 150 000.00 | 94 782.89 | 55 217.11 | 63.18 |  |
| 17002300400000000000 | OC: BC/FAC/C FEES - BANK ACCOUNTS | 700 000.00 | 237 455.62 | 462 544.38 | 33.92 |  |
| 17002303330000000000 | OC: LIC - VEHICLE LIC & REGISTRATIONS | 2 500.00 | 2 820.80 | -320.80 | 112.83 |  |
|  | LED |  |  |  |  |  |
| 18002032580000000000 | SM D05: SRB - ACTING & POST RELATE ALLOW | 322 500.00 | 203 825.04 | 118 674.96 | 63.20 |  |
| 18002110260000000000 | MS: HB & INC: HOUSING BENEFITS | 83 450.00 | 29 325.33 | 54 124.67 | 35.14 |  |
| 18002110320000000000 | MS: ALL - LEAVE PAY | 43 000.00 | 92 252.04 | -49 252.04 | 214.53 |  |
| 18002110440000000000 | MS: SRB - ACTING ALLOWANCE | 117 100.00 | 52 667.96 | 64 432.04 | 44.97 |  |
| 18002110460000000000 | MS: SRB - ANNUAL BONUS | 1 156 430.00 | 476 917.22 | 679 512.78 | 41.24 |  |
| 18002110500000000000 | MS: SRB - LONG SERVICE AWARD | 10 750.00 | 47 068.33 | -36 318.33 | 437.84 |  |
| 18002130100000000000 | MS: SOC CONTR - GROUP LIFE INSURANCE | 4 830.00 | 3 623.89 | 1 206.11 | 75.02 |  |
| 18002140080000000000 | MS: PRB - MED: PAST SERVICE COST | 54 400.00 | 39 750.60 | 14 649.40 | 73.07 |  |
| 18002303330000000000 | OC: LIC - VEHICLE LIC & REGISTRATIONS | 1 200.00 | 654.00 | 546.00 | 54.50 |  |
| 1800230572F000000000 | OC: TOLL GATE FEES FLEET | 3 000.00 | 1 312.00 | 1 688.00 | 43.73 |  |
| 18002305760000000000 | OC: T&S DOM - ACCOMMODATION | 70 000.00 | 39 159.84 | 30 840.16 | 55.94 |  |
| 18002305810000000000 | OC: T&S DOM TRP - W/OUT OPR OWN TRANSPRT | 22 000.00 | 14 224.50 | 7 775.50 | 64.65 |  |
| 1800232061F000000000 | INV - CONSUMABL STORES -ZERO RATED FLEET | 15 000.00 | 9 604.15 | 5 395.85 | 64.02 |  |

Variance to monthly target of Cash flow for October 2019 as per SDBIP

| Detail | Actual July | Actual Aug | Actual Sept | Month 4 Oct | Actual Oct | Var | Var % | Month 5 Nov | Month 6 Dec | Month 7 Jan | Month 8 Feb | Month 9 Mar | Month 10 Apr | Month 11 May | Month 12 June |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cash Receipts by Source |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Property rates | 10 453 021 | 14 024 | 10 447 978 | 20 000 000 | 18 990 234 | 1 009 766 | 5 | 15 542 000 | 13 542 000 | 10 542 000 | 14 542 000 | 14 542 000 | 14 542 000 | 14 542 000 | 174 290 240 |
| Service charges - electricity revenue | 29 097 420 | 37 588 | 16 391 349 | 20 097 420 | 29 506 235 | -9 408 815 | -47 | 18 097 420 | 19 097 420 | 18 097 420 | 17 097 420 | 24 097 420 | 25 097 420 | 26 097 420 | 276 779 470 |
| Service charges - water revenue | 21 177 190 | 29 027 | 15 987 182 | 33 427 830 | 39 234 833 | -5 807 003 | -17 | 34 427 830 | 35 427 830 | 35 427 830 | 36 427 830 | 34 427 830 | 32 427 830 | 32 427 830 | 397 078 610 |
| Service charges - sanitation revenue | 1 804 240 | 2 015 | 1 509 830 | 2 137 000 | 2 887 005 | -750 005 | -35 | 2 137 000 | 1 999 000 | 1 800 000 | 2 137 000 | 2 137 000 | 2 237 000 | 2 137 000 | 25 650 560 |
| Service charges - refuse | 2 361 608 | 2 601 | 1 969 898 | 1 500 000 | 3 966 191 | -2 466 191 | -164 | 2 379 000 | 1 400 000 | 1 979 000 | 1 979 000 | 2 479 000 | 1 979 000 | 1 979 000 | 23 752 330 |
| Rental of facilities and equipment | 452 806 | 910 | 49 899 | 547 250 | 446 505 | 100 745 | 18 | 547 250 | 547 250 | 547 250 | 547 250 | 547 250 | 547 250 | 547 250 | 6 566 910 |
| Interest earned - external investments | 0 | 439 | 33 596 | 50 000 | 468 407 | -418 407 | -837 | 50 000 | 250 000 | 150 000 | 75 000 | 200 000 | 150 000 | 90 000 | 1 500 000 |
| Interest earned - outstanding debtors | 279 640 | 405 | 334 701 | 2 508 000 | 246 529 | 2 261 471 | 90 | 2 808 000 | 2 508 000 | 2 508 000 | 2 608 000 | 2 558 000 | 2 570 000 | 2 508 000 | 30 104 100 |
| Dividends received | 0 | – | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Fines, penalties and forfeits | 18 908 | 83 | 126 285 | 276 000 | 54 382 | 221 618 | 80 | 276 000 | 276 000 | 276 000 | 276 000 | 276 000 | 276 000 | 276 000 | 3 320 100 |
| Licences and permits | 0 | – | 0 | 17 580 | 0 | 17 580 | 100 | 17 580 | 17 580 | 17 580 | 17 580 | 17 580 | 17 580 | 17 580 | 210 930 |
| Agency services |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  |  |
| Transfer receipts - operating | 76 277 000 | 2 525 | 0 | 196 020 | 0 | 196 020 | 100 | 196 020 | 54 919 200 | 196 020 | 196 020 | 36 612 800 | 196 020 | 196 020 | 189 039 000 |
| Other revenue | 697 828 | 13 486 | 6 493 089 | 1 020 250 | 5 020 945 | -4 000 695 | -392 | 1 020 250 | 1 020 250 | 1 020 250 | 1 020 250 | 1 020 250 | 1 020 250 | 1 020 250 | 12 163 450 |
| Cash Receipts by Source | 142 619 661 | 103 101 552 | 53 343 807 | 81 777 350 | 100 821 266 |  |  | 77 498 350 | 131 004 530 | 72 561 350 | 76 923 350 | 118 915 130 | 81 060 350 | 81 838 350 | 1 140 455 700 |
| Other Cash Flows by Source |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Transfer receipts - capital | 25 813 370 | 2 680 | 0 | 3 500 000 |  | 3 500 000 | 100 | 26 356 466 |  |  | 35 000 000 | 19 700 000 | 0 | 0 | 177 269 000 |
| Contributions & Contributed assets |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  |  |
| Proceeds on disposal of PPE | 0 | – | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Short term loans | 0 | – | 0 |  |  |  |  | 0 | 15 692 000 | 0 | 0 | 0 | 0 | 0 | 21 692 450 |
| Borrowing long term/refinancing | 0 | – | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 16 000 000 | 0 | 0 | 37 709 000 |
| Increase in consumer deposits | 172 797 | 240 | 202 103 | -33 000 | 137 844 | -170 844 | 518 | -35 000 | -33 000 | -30 000 | -30 000 | -33 000 | -33 000 | -33 000 | -400 000 |
| Receipt of non-current debtors | 0 | – | 0 | 4 000 000 |  | 4 000 000 | 100 | 200 000 | 200 000 | 250 000 | 200 000 | 500 000 | 200 000 | 300 000 | 8 050 000 |
| Receipt of non-current receivables | 0 | – | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Change in non-current investments |  |  |  |  |  | 0 |  |  |  |  |  |  |  |  |  |
| Total Cash Receipts by Source | 168 605 828 | 106 021 580 | 53 545 910 | 89 244 350 | 100 959 110 |  |  | 104 019 816 | 146 863 530 | 72 781 350 | 112 093 350 | 155 082 130 | 81 227 350 | 82 105 350 | 1 384 776 150 |
| Cash Payments by Type |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Employee related costs | 24 119 406 | 23 984 | 25 411 384 | 26 992 000 | 24 991 016 | 2 000 984 | 7 | 32 992 000 | 28 992 000 | 28 992 000 | 30 992 000 | 30 992 000 | 30 992 000 | 31 992 000 | 350 931 390 |
| Remuneration of councillors | 1 558 839 | 1 559 | 1 558 839 | 1 591 920 | 1 558 839 | 33 081 | 2 | 1 591 920 | 1 591 920 | 1 591 920 | 1 591 920 | 1 591 920 | 1 591 920 | 1 591 920 | 19 855 440 |
| Interest paid | 0 | 41 | 57 238 | 177 500 | 207 846 | -30 346 | -17 | 178 000 | 1 500 000 | 200 000 | 200 000 | 20 000 | 200 000 | 200 000 | 6 448 030 |
| Bulk purchases - Electricity | 30 792 980 | 40 165 | 34 608 720 | 21 004 330 | 21 525 160 | -520 830 | -2 | 19 004 330 | 19 000 000 | 19 000 000 | 20 004 330 | 20 004 330 | 20 004 330 | 20 004 330 | 287 044 840 |
| Bulk purchases - Water & Sewer | 16 288 950 | 17 739 | 17 698 278 | 15 289 000 | 16 275 760 | -986 760 | -6 | 16 289 000 | 20 289 000 | 17 289 000 | 16 589 000 | 15 889 000 | 15 789 000 | 14 999 000 | 191 961 780 |
| Other materials | 223 087 | 1 042 | 1 213 379 | 2 348 500 | 2 171 180 | 177 320 | 8 | 2 348 500 | 2 348 500 | 2 348 500 | 2 348 500 | 2 348 500 | 2 348 500 | 2 348 500 | 32 941 245 |
| Contracted services | 1 971 769 | 6 059 | 3 150 560 | 9 558 420 | 8 076 127 | 1 482 293 | 16 | 9 558 420 | 9 558 420 | 9 558 420 | 9 558 420 | 9 558 420 | 9 558 420 | 9 558 420 | 110 421 000 |
| Grants and subsidies paid - other municipalities | 0 | – | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Grants and subsidies paid - other | 0 | – | 0 | 0 | 0 | 0 |  | 0 | 10 000 | 0 | 0 | 10 000 | 0 | 0 | 42 020 |
| General expenses | 13 512 339 | 17 243 | 25 261 980 | 4 537 000 | 14 253 002 | -9 716 002 | -214 | 4 037 000 | 5 537 000 | 5 537 000 | 6 037 000 | 6 537 000 | 7 237 000 | 7 007 000 | 66 447 520 |
| Cash Payments by Type | 88 467 370 | 107 832 630 | 108 960 378 | 81 498 670 | 89 058 930 |  |  | 85 999 170 | 88 826 840 | 84 516 840 | 87 321 170 | 86 951 170 | 87 721 170 | 87 701 170 | 1 066 093 265 |
| Other Cash Flows/Payments by Type |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Capital assets | 0 |  | 0 | 30 000 000 | 0 | 30 000 000 | 100 | 15 000 000 | 30 600 000 | 24 000 000 | 24 000 000 | 40 000 000 | 27 000 000 | 29 500 000 | 294 517 100 |
| Repayment of borrowing | 0 |  | 0 | 541 898 | 0 | 541 898 | 100 | 541 898 | 942 000 | 541 898 | 541 898 | 541 898 | 541 898 | 541 898 | 8 642 396 |
| Other Cash Flows/Payments | 64 793 571 | 3 478 | 1 404 611 | 2 000 000 | -17 452 894 | 19 452 894 | 973 | 0 | 0 | 3 000 000 | 0 | 0 | 0 | 0 | 16 762 000 |
| Total Cash Payments by Type | 153 260 941 | 111 310 453 | 110 364 989 | 114 040 568 | 71 606 036 | 42 434 532 | 37 | 101 541 068 | 120 368 840 | 112 058 738 | 111 863 068 | 127 493 068 | 115 263 068 | 117 743 068 | 1 386 014 761 |
| NET INCREASE/(DECREASE) IN CASH HELD | 15 344 887 | -5 288 873 | -56 819 079 | -24 796 218 | 29 353 074 | -54 149 292 | 218 | 2 478 748 | 26 494 690 | -39 277 388 | 230 282 | 27 589 062 | -34 035 718 | -35 637 718 | -1 238 611 |
| Cash/cash equivalents at the month/year beginning: | 35 419 000 | 50 763 887 | 45 475 014 | 146 513 770 | -11 344 065 | 157 857 835 | 108 | 121 717 552 | 124 196 300 | 150 690 990 | 111 413 602 | 111 643 884 | 139 232 946 | 105 197 228 | 35 419 000 |
| Cash/cash equivalents at the month/year end: | 50 763 887 | 45 475 014 | -11 344 065 | 121 717 552 | 18 009 009 | 103 708 543 | 85 | 124 196 300 | 150 690 990 | 111 413 602 | 111 643 884 | 139 232 946 | 105 197 228 | 69 559 510 | 34 180 389 |

12. Capital programme performance

| FS204 Metsimaholo - Supporting Table SC13a Monthly Budget Statement - capital expenditure on new assets by asset class - M04 October |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description | Ref | 2018/19 | Budget Year 2019/20 |  |  |  |  |  |  |  |
|  |  | Audited Outcome | Original Budget | Adjusted Budget | Monthly actual | YearTD actual | YearTD budget | YTD variance | YTD variance | Full Year Forecast |
| R thousands | 1 |  |  |  |  |  |  |  | % |  |
| Capital expenditure on new assets by Asset Class/Sub-class |  |  |  |  |  |  |  |  |  |  |
| Infrastructure |  | 97 638 | 181 686 | 181 686 | 6 632 | 14 720 | 60 562 | 45 842 | 75.7% | 181 686 |
| Roads Infrastructure |  | 20 101 | 9 501 | 9 501 | 171 | 1 503 | 3 167 | 1 664 | 52.5% | 9 501 |
| Roads |  | 20 101 | 4 808 | 4 808 | 86 | 1 244 | 1 603 | 358 | 22.4% | 4 808 |
| Road Structures |  | – | – | – | – | – | – | – |  | – |
| Road Furniture |  | – | 4 693 | 4 693 | 85 | 258 | 1 564 | 1 306 | 83.5% | 4 693 |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Storm water Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Drainage Collection |  |  |  |  |  |  |  | – |  |  |
| Storm water Conveyance |  |  |  |  |  |  |  | – |  |  |
| Attenuation |  |  |  |  |  |  |  | – |  |  |
| Electrical Infrastructure |  | 13 692 | 18 216 | 18 216 | – | – | 6 072 | 6 072 | 100.0% | 18 216 |
| Power Plants |  |  |  |  |  |  |  | – |  |  |
| HV Substations |  | – | – | – | – | – | – | – |  | – |
| HV Switching Station |  |  |  |  |  |  |  | – |  |  |
| HV Transmission Conductors |  |  |  |  |  |  |  | – |  |  |
| MV Substations |  | – | 150 | 150 | – | – | 50 | 50 | 100.0% | 150 |
| MV Switching Stations |  | – | – | – | – | – | – | – |  | – |
| MV Networks |  | 10 759 | 1 650 | 1 650 | – | – | 550 | 550 | 100.0% | 1 650 |
| LV Networks |  | 2 907 | 15 916 | 15 916 | – | – | 5 305 | 5 305 | 100.0% | 15 916 |
| Capital Spares |  | 26 | 500 | 500 | – | – | 167 | 167 | 100.0% | 500 |
| Water Supply Infrastructure |  | 8 696 | 9 593 | 9 593 | 2 234 | 4 157 | 3 198 | (959) | -30.0% | 9 593 |
| Dams and Weirs |  |  |  |  |  |  |  | – |  |  |
| Boreholes |  |  |  |  |  |  |  | – |  |  |
| Reservoirs |  |  |  |  |  |  |  | – |  |  |
| Pump Stations |  |  |  |  |  |  |  | – |  |  |
| Water Treatment Works |  | 8 696 | 9 593 | 9 593 | 2 234 | 4 157 | 3 198 | (959) | -30.0% | 9 593 |
| Bulk Mains |  |  |  |  |  |  |  | – |  |  |
| Distribution |  | – | – | – | – | – | – | – |  | – |
| Distribution Points |  |  |  |  |  |  |  | – |  |  |
| PRV Stations |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Sanitation Infrastructure |  | 55 149 | 144 126 | 144 126 | 4 227 | 9 061 | 48 042 | 38 981 | 81.1% | 144 126 |
| Pump Station |  |  |  |  |  |  |  | – |  |  |
| Reticulation |  | 11 057 | 31 876 | 31 876 | 1 690 | 3 591 | 10 625 | 7 034 | 66.2% | 31 876 |
| Waste Water Treatment Works |  | 34 756 | 80 000 | 80 000 | – | – | 26 667 | 26 667 | 100.0% | 80 000 |
| Outfall Sewers |  |  |  |  |  |  |  | – |  |  |
| Toilet Facilities |  | 9 336 | 32 250 | 32 250 | 2 537 | 5 470 | 10 750 | 5 280 | 49.1% | 32 250 |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Solid Waste Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Landfill Sites |  | – | – | – | – | – | – | – |  | – |
| Waste Transfer Stations |  |  |  |  |  |  |  | – |  |  |
| Waste Processing Facilities |  |  |  |  |  |  |  | – |  |  |
| Waste Drop-off Points |  |  |  |  |  |  |  | – |  |  |
| Waste Separation Facilities |  | – | – | – | – | – | – | – |  | – |
| Electricity Generation Facilities |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Rail Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Rail Lines |  |  |  |  |  |  |  | – |  |  |
| Rail Structures |  |  |  |  |  |  |  | – |  |  |
| Rail Furniture |  |  |  |  |  |  |  | – |  |  |
| Drainage Collection |  |  |  |  |  |  |  | – |  |  |
| Storm water Conveyance |  |  |  |  |  |  |  | – |  |  |
| Attenuation |  |  |  |  |  |  |  | – |  |  |
| MV Substations |  |  |  |  |  |  |  | – |  |  |
| LV Networks |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Coastal Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Sand Pumps |  |  |  |  |  |  |  | – |  |  |
| Piers |  |  |  |  |  |  |  | – |  |  |
| Revetments |  |  |  |  |  |  |  | – |  |  |
| Promenades |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Information and Communication Infrastructure |  | – | 250 | 250 | – | – | 83 | 83 | 100.0% | 250 |
| Data Centres |  |  |  |  |  |  |  | – |  |  |
| Core Layers |  |  |  |  |  |  |  | – |  |  |
| Distribution Layers |  | – | 250 | 250 | – | – | 83 | 83 | 100.0% | 250 |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Community Assets |  | 625 | 17 049 | 17 049 | – | – | 5 683 | 5 683 | 100.0% | 17 049 |
| Community Facilities |  | 621 | 17 005 | 17 005 | – | – | 5 668 | 5 668 | 100.0% | 17 005 |
| Halls |  | – | – | – | – | – | – | – |  | – |
| Centres |  |  |  |  |  |  |  | – |  |  |
| Crèches |  |  |  |  |  |  |  | – |  |  |
| Clinics/Care Centres |  |  |  |  |  |  |  | – |  |  |
| Fire/Ambulance Stations |  | – | – | – | – | – | – | – |  | – |
| Testing Stations |  |  |  |  |  |  |  | – |  |  |
| Museums |  |  |  |  |  |  |  | – |  |  |
| Galleries |  |  |  |  |  |  |  | – |  |  |
| Theatres |  |  |  |  |  |  |  | – |  |  |
| Libraries |  |  |  |  |  |  |  | – |  |  |
| Cemeteries/Crematoria |  | – | 470 | 470 | – | – | 157 | 157 | 100.0% | 470 |
| Police |  |  |  |  |  |  |  | – |  |  |
| Purls |  | – | – | – | – | – | – | – |  | – |
| Public Open Space |  | 621 | 16 535 | 16 535 | – | – | 5 512 | 5 512 | 100.0% | 16 535 |
| Nature Reserves |  |  |  |  |  |  |  | – |  |  |
| Public Ablution Facilities |  |  |  |  |  |  |  | – |  |  |
| Markets |  |  |  |  |  |  |  | – |  |  |
| Stalls |  | – | – | – | – | – | – | – |  | – |
| Abattoirs |  |  |  |  |  |  |  | – |  |  |
| Airports |  |  |  |  |  |  |  | – |  |  |
| Taxi Ranks/Bus Terminals |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Sport and Recreation Facilities |  | 4 | 44 | 44 | – | – | 15 | 15 | 100.0% | 44 |
| Indoor Facilities |  |  |  |  |  |  |  | – |  |  |
| Outdoor Facilities |  | 4 | 44 | 44 | – | – | 15 | 15 | 100.0% | 44 |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Heritage assets |  | – | – | – | – | – | – | – |  | – |
| Monuments |  |  |  |  |  |  |  | – |  |  |
| Historic Buildings |  |  |  |  |  |  |  | – |  |  |
| Works of Art |  |  |  |  |  |  |  | – |  |  |
| Conservation Areas |  |  |  |  |  |  |  | – |  |  |
| Other Heritage |  |  |  |  |  |  |  | – |  |  |
| Investment properties |  | – | – | – | – | – | – | – |  | – |
| Revenue Generating |  | – | – | – | – | – | – | – |  | – |
| Improved Property |  |  |  |  |  |  |  | – |  |  |
| Unimproved Property |  |  |  |  |  |  |  | – |  |  |
| Non-revenue Generating |  | – | – | – | – | – | – | – |  | – |
| Improved Property |  |  |  |  |  |  |  | – |  |  |
| Unimproved Property |  |  |  |  |  |  |  | – |  |  |
| Other assets |  | – | 3 800 | 3 800 | – | – | 1 267 | 1 267 | 100.0% | 3 800 |
| Operational Buildings |  | – | 3 800 | 3 800 | – | – | 1 267 | 1 267 | 100.0% | 3 800 |
| Municipal Offices |  | – | 300 | 300 | – | – | 100 | 100 | 100.0% | 300 |
| Pay/Enquiry Points |  |  |  |  |  |  |  | – |  |  |
| Building Plan Offices |  |  |  |  |  |  |  | – |  |  |
| Workshops |  |  |  |  |  |  |  | – |  |  |
| Yards |  |  |  |  |  |  |  | – |  |  |
| Stores |  |  |  |  |  |  |  | – |  |  |
| Laboratories |  |  |  |  |  |  |  | – |  |  |
| Training Centres |  |  |  |  |  |  |  | – |  |  |
| Manufacturing Plant |  |  |  |  |  |  |  | – |  |  |
| Depots |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  | – | 3 500 | 3 500 | – | – | 1 167 | 1 167 | 100.0% | 3 500 |
| Housing |  | – | – | – | – | – | – | – |  | – |
| Staff Housing |  |  |  |  |  |  |  | – |  |  |
| Social Housing |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Biological or Cultivated Assets |  | – | – | – | – | – | – | – |  | – |
| Biological or Cultivated Assets |  |  |  |  |  |  |  | – |  |  |
| Intangible Assets |  | – | 1 400 | 1 400 | – | – | 467 | 467 | 100.0% | 1 400 |
| Servitudes |  |  |  |  |  |  |  | – |  |  |
| Licences and Rights |  | – | 1 400 | 1 400 | – | – | 467 | 467 | 100.0% | 1 400 |
| Water Rights |  |  |  |  |  |  |  | – |  |  |
| Effluent Licenses |  |  |  |  |  |  |  | – |  |  |
| Solid Waste Licenses |  |  |  |  |  |  |  | – |  |  |
| Computer Software and Applications |  | – | 1 400 | 1 400 | – | – | 467 | 467 | 100.0% | 1 400 |
| Load Settlement Software Applications |  |  |  |  |  |  |  | – |  |  |
| Unspecified |  |  |  |  |  |  |  | – |  |  |
| Computer Equipment |  | 310 | 1 330 | 1 330 | – | – | 443 | 443 | 100.0% | 1 330 |
| Computer Equipment |  | 310 | 1 330 | 1 330 | – | – | 443 | 443 | 100.0% | 1 330 |
| Furniture and Office Equipment |  | 164 | 2 636 | 2 636 | – | 8 | 879 | 871 | 99.1% | 2 636 |
| Furniture and Office Equipment |  | 164 | 2 636 | 2 636 | – | 8 | 879 | 871 | 99.1% | 2 636 |
| Machinery and Equipment |  | 2 449 | 1 479 | 1 479 | 198 | 211 | 493 | 283 | 57.3% | 1 479 |
| Machinery and Equipment |  | 2 449 | 1 479 | 1 479 | 198 | 211 | 493 | 283 | 57.3% | 1 479 |
| Transport Assets |  | 8 606 | 17 548 | 17 548 | – | – | 5 849 | 5 849 | 100.0% | 17 548 |
| Transport Assets |  | 8 606 | 17 548 | 17 548 | – | – | 5 849 | 5 849 | 100.0% | 17 548 |
| Land |  | – | – | – | – | – | – | – |  | – |
| Land |  |  |  |  |  |  |  | – |  |  |
| Zoo's, Marine and Non-biological Animals |  | – | – | – | – | – | – | – |  | – |
| Zoo's, Marine and Non-biological Animals |  |  |  |  |  |  |  | – |  |  |
| Total Capital Expenditure on new assets | 1 | 109 792 | 226 928 | 226 928 | 6 830 | 14 939 | 75 643 | 60 704 | 80.3% | 226 928 |

| FS204 Metsimaholo - Supporting Table SC13b Monthly Budget Statement - capital expenditure on renewal of existing assets by asset class - M04 October |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description | Ref | 2018/19 | Budget Year 2019/20 |  |  |  |  |  |  |  |
|  |  | Audited Outcome | Original Budget | Adjusted Budget | Monthly actual | YearTD actual | YearTD budget | YTD variance | YTD variance | Full Year Forecast |
| R thousands | 1 |  |  |  |  |  |  |  | % |  |
| Capital expenditure on renewal of existing assets by Asset Class/Sub-class |  |  |  |  |  |  |  |  |  |  |
| Infrastructure |  | 7 461 | 58 604 | 58 604 | 145 | 190 | 19 535 | 19 344 | 99.0% | 58 604 |
| Roads Infrastructure |  | – | 42 000 | 42 000 | – | – | 14 000 | 14 000 | 100.0% | 42 000 |
| Roads |  | – | 42 000 | 42 000 | – | – | 14 000 | 14 000 | 100.0% | 42 000 |
| Road Structures |  |  |  |  |  |  |  | – |  |  |
| Road Furniture |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Storm water Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Drainage Collection |  |  |  |  |  |  |  | – |  |  |
| Storm water Conveyance |  |  |  |  |  |  |  | – |  |  |
| Attenuation |  |  |  |  |  |  |  | – |  |  |
| Electrical Infrastructure |  | 7 461 | 13 600 | 13 600 | – | – | 4 533 | 4 533 | 100.0% | 13 600 |
| Power Plants |  |  |  |  |  |  |  | – |  |  |
| HV Substations |  |  |  |  |  |  |  | – |  |  |
| HV Switching Station |  |  |  |  |  |  |  | – |  |  |
| HV Transmission Conductors |  |  |  |  |  |  |  | – |  |  |
| MV Substations |  |  |  |  |  |  |  | – |  |  |
| MV Switching Stations |  |  |  |  |  |  |  | – |  |  |
| MV Networks |  | 7 461 | – | – | – | – | – | – |  | – |
| LV Networks |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  | – | 13 600 | 13 600 | – | – | 4 533 | 4 533 | 100.0% | 13 600 |
| Water Supply Infrastructure |  | – | 3 000 | 3 000 | 145 | 190 | 1 000 | 810 | 81.0% | 3 000 |
| Dams and Weirs |  |  |  |  |  |  |  | – |  |  |
| Boreholes |  |  |  |  |  |  |  | – |  |  |
| Reservoirs |  | – | – | – | – | – | – | – |  | – |
| Pump Stations |  |  |  |  |  |  |  | – |  |  |
| Water Treatment Works |  | – | 1 300 | 1 300 | 49 | 49 | 433 | 384 | 88.6% | 1 300 |
| Bulk Mains |  |  |  |  |  |  |  | – |  |  |
| Distribution |  |  |  |  |  |  |  | – |  |  |
| Distribution Points |  |  |  |  |  |  |  | – |  |  |
| PRV Stations |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  | – | 1 700 | 1 700 | 96 | 141 | 567 | 425 | 75.1% | 1 700 |
| Sanitation Infrastructure |  | – | 4 | 4 | – | – | 1 | 1 | 100.0% | 4 |
| Pump Station |  | – | 4 | 4 | – | – | 1 | 1 | 100.0% | 4 |
| Reticulation |  |  |  |  |  |  |  | – |  |  |
| Waste Water Treatment Works |  | – | – | – | – | – | – | – |  | – |
| Outfall Sewers |  |  |  |  |  |  |  | – |  |  |
| Toilet Facilities |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  | – | – | – | – | – | – | – |  | – |
| Solid Waste Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Landfill Sites |  |  |  |  |  |  |  | – |  |  |
| Waste Transfer Stations |  |  |  |  |  |  |  | – |  |  |
| Waste Processing Facilities |  |  |  |  |  |  |  | – |  |  |
| Waste Drop-off Points |  |  |  |  |  |  |  | – |  |  |
| Waste Separation Facilities |  |  |  |  |  |  |  | – |  |  |
| Electricity Generation Facilities |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Rail Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Rail Lines |  |  |  |  |  |  |  | – |  |  |
| Rail Structures |  |  |  |  |  |  |  | – |  |  |
| Rail Furniture |  |  |  |  |  |  |  | – |  |  |
| Drainage Collection |  |  |  |  |  |  |  | – |  |  |
| Storm water Conveyance |  |  |  |  |  |  |  | – |  |  |
| Attenuation |  |  |  |  |  |  |  | – |  |  |
| MV Substations |  |  |  |  |  |  |  | – |  |  |
| LV Networks |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Coastal Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Sand Pumps |  |  |  |  |  |  |  | – |  |  |
| Piers |  |  |  |  |  |  |  | – |  |  |
| Revetments |  |  |  |  |  |  |  | – |  |  |
| Promenades |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Information and Communication Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Data Centres |  |  |  |  |  |  |  | – |  |  |
| Core Layers |  |  |  |  |  |  |  | – |  |  |
| Distribution Layers |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Community Assets |  | – | 2 983 | 2 983 | – | – | 994 | 994 | 100.0% | 2 983 |
| Community Facilities |  | – | 2 983 | 2 983 | – | – | 994 | 994 | 100.0% | 2 983 |
| Halls |  |  |  |  |  |  |  | – |  |  |
| Centres |  |  |  |  |  |  |  | – |  |  |
| Crèches |  |  |  |  |  |  |  | – |  |  |
| Clinics/Care Centres |  |  |  |  |  |  |  | – |  |  |
| Fire/Ambulance Stations |  | – | – | – | – | – | – | – |  | – |
| Testing Stations |  |  |  |  |  |  |  | – |  |  |
| Museums |  |  |  |  |  |  |  | – |  |  |
| Galleries |  |  |  |  |  |  |  | – |  |  |
| Theatres |  |  |  |  |  |  |  | – |  |  |
| Libraries |  |  |  |  |  |  |  | – |  |  |
| Cemeteries/Crematoria |  | – | 1 233 | 1 233 | – | – | 411 | 411 | 100.0% | 1 233 |
| Police |  |  |  |  |  |  |  | – |  |  |
| Purls |  |  |  |  |  |  |  | – |  |  |
| Public Open Space |  | – | 1 750 | 1 750 | – | – | 583 | 583 | 100.0% | 1 750 |
| Nature Reserves |  |  |  |  |  |  |  | – |  |  |
| Public Ablution Facilities |  | – | – | – | – | – | – | – |  | – |
| Markets |  |  |  |  |  |  |  | – |  |  |
| Stalls |  |  |  |  |  |  |  | – |  |  |
| Abattoirs |  |  |  |  |  |  |  | – |  |  |
| Airports |  |  |  |  |  |  |  | – |  |  |
| Taxi Ranks/Bus Terminals |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Sport and Recreation Facilities |  | – | – | – | – | – | – | – |  | – |
| Indoor Facilities |  |  |  |  |  |  |  | – |  |  |
| Outdoor Facilities |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Heritage assets |  | – | – | – | – | – | – | – |  | – |
| Monuments |  |  |  |  |  |  |  | – |  |  |
| Historic Buildings |  |  |  |  |  |  |  | – |  |  |
| Works of Art |  |  |  |  |  |  |  | – |  |  |
| Conservation Areas |  |  |  |  |  |  |  | – |  |  |
| Other Heritage |  |  |  |  |  |  |  | – |  |  |
| Investment properties |  | – | – | – | – | – | – | – |  | – |
| Revenue Generating |  | – | – | – | – | – | – | – |  | – |
| Improved Property |  |  |  |  |  |  |  | – |  |  |
| Unimproved Property |  |  |  |  |  |  |  | – |  |  |
| Non-revenue Generating |  | – | – | – | – | – | – | – |  | – |
| Improved Property |  |  |  |  |  |  |  | – |  |  |
| Unimproved Property |  |  |  |  |  |  |  | – |  |  |
| Other assets |  | – | 200 | 100 | – | – | 33 | 33 | 100.0% | 100 |
| Operational Buildings |  | – | 200 | 100 | – | – | 33 | 33 | 100.0% | 100 |
| Municipal Offices |  | – | 200 | 100 | – | – | 33 | 33 | 100.0% | 100 |
| Pay/Enquiry Points |  |  |  |  |  |  |  | – |  |  |
| Building Plan Offices |  |  |  |  |  |  |  | – |  |  |
| Workshops |  |  |  |  |  |  |  | – |  |  |
| Yards |  |  |  |  |  |  |  | – |  |  |
| Stores |  |  |  |  |  |  |  | – |  |  |
| Laboratories |  |  |  |  |  |  |  | – |  |  |
| Training Centres |  |  |  |  |  |  |  | – |  |  |
| Manufacturing Plant |  |  |  |  |  |  |  | – |  |  |
| Depots |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Housing |  | – | – | – | – | – | – | – |  | – |
| Staff Housing |  |  |  |  |  |  |  | – |  |  |
| Social Housing |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Biological or Cultivated Assets |  | – | – | – | – | – | – | – |  | – |
| Biological or Cultivated Assets |  |  |  |  |  |  |  | – |  |  |
| Intangible Assets |  | – | 1 200 | 1 200 | 249 | 249 | 400 | 151 | 37.7% | 1 200 |
| Servitudes |  |  |  |  |  |  |  | – |  |  |
| Licences and Rights |  | – | 1 200 | 1 200 | 249 | 249 | 400 | 151 | 37.7% | 1 200 |
| Water Rights |  |  |  |  |  |  |  | – |  |  |
| Effluent Licenses |  |  |  |  |  |  |  | – |  |  |
| Solid Waste Licenses |  |  |  |  |  |  |  | – |  |  |
| Computer Software and Applications |  | – | 1 200 | 1 200 | 249 | 249 | 400 | 151 | 37.7% | 1 200 |
| Load Settlement Software Applications |  |  |  |  |  |  |  | – |  |  |
| Unspecified |  |  |  |  |  |  |  | – |  |  |
| Computer Equipment |  | 85 | 200 | 200 | – | – | 67 | 67 | 100.0% | 200 |
| Computer Equipment |  | 85 | 200 | 200 | – | – | 67 | 67 | 100.0% | 200 |
| Furniture and Office Equipment |  | – | 966 | 966 | – | – | 322 | 322 | 100.0% | 966 |
| Furniture and Office Equipment |  | – | 966 | 966 | – | – | 322 | 322 | 100.0% | 966 |
| Machinery and Equipment |  | – | 521 | 621 | – | – | 207 | 207 | 100.0% | 621 |
| Machinery and Equipment |  | – | 521 | 621 | – | – | 207 | 207 | 100.0% | 621 |
| Transport Assets |  | – | 715 | 715 | – | – | 238 | 238 | 100.0% | 715 |
| Transport Assets |  | – | 715 | 715 | – | – | 238 | 238 | 100.0% | 715 |
| Land |  | – | – | – | – | – | – | – |  | – |
| Land |  |  |  |  |  |  |  | – |  |  |
| Zoo's, Marine and Non-biological Animals |  | – | – | – | – | – | – | – |  | – |
| Zoo's, Marine and Non-biological Animals |  |  |  |  |  |  |  | – |  |  |
| Total Capital Expenditure on renewal of existing assets | 1 | 7 546 | 65 389 | 65 389 | 394 | 440 | 21 797 | 21 357 | 98.0% | 65 389 |

| FS204 Metsimaholo - Supporting Table SC13e Monthly Budget Statement - capital expenditure on upgrading of existing assets by asset class - M04 October |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Description | Ref | 2018/19 | Budget Year 2019/20 |  |  |  |  |  |  |  |
|  |  | Audited Outcome | Original Budget | Adjusted Budget | Monthly actual | YearTD actual | YearTD budget | YTD variance | YTD variance | Full Year Forecast |
| R thousands | 1 |  |  |  |  |  |  |  | % |  |
| Capital expenditure on upgrading of existing assets by Asset Class/Sub-class |  |  |  |  |  |  |  |  |  |  |
| Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Roads Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Roads |  |  |  |  |  |  |  | – |  |  |
| Road Structures |  |  |  |  |  |  |  | – |  |  |
| Road Furniture |  | – | – | – | – | – | – | – |  | – |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Storm water Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Drainage Collection |  |  |  |  |  |  |  | – |  |  |
| Storm water Conveyance |  |  |  |  |  |  |  | – |  |  |
| Attenuation |  |  |  |  |  |  |  | – |  |  |
| Electrical Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Power Plants |  |  |  |  |  |  |  | – |  |  |
| HV Substations |  | – | – | – | – | – | – | – |  | – |
| HV Switching Station |  |  |  |  |  |  |  | – |  |  |
| HV Transmission Conductors |  |  |  |  |  |  |  | – |  |  |
| MV Substations |  |  |  |  |  |  |  | – |  |  |
| MV Switching Stations |  |  |  |  |  |  |  | – |  |  |
| MV Networks |  |  |  |  |  |  |  | – |  |  |
| LV Networks |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Water Supply Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Dams and Weirs |  |  |  |  |  |  |  | – |  |  |
| Boreholes |  |  |  |  |  |  |  | – |  |  |
| Reservoirs |  |  |  |  |  |  |  | – |  |  |
| Pump Stations |  |  |  |  |  |  |  | – |  |  |
| Water Treatment Works |  |  |  |  |  |  |  | – |  |  |
| Bulk Mains |  |  |  |  |  |  |  | – |  |  |
| Distribution |  |  |  |  |  |  |  | – |  |  |
| Distribution Points |  |  |  |  |  |  |  | – |  |  |
| PRV Stations |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Sanitation Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Pump Station |  |  |  |  |  |  |  | – |  |  |
| Reticulation |  |  |  |  |  |  |  | – |  |  |
| Waste Water Treatment Works |  |  |  |  |  |  |  | – |  |  |
| Outfall Sewers |  |  |  |  |  |  |  | – |  |  |
| Toilet Facilities |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Solid Waste Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Landfill Sites |  |  |  |  |  |  |  | – |  |  |
| Waste Transfer Stations |  |  |  |  |  |  |  | – |  |  |
| Waste Processing Facilities |  |  |  |  |  |  |  | – |  |  |
| Waste Drop-off Points |  |  |  |  |  |  |  | – |  |  |
| Waste Separation Facilities |  |  |  |  |  |  |  | – |  |  |
| Electricity Generation Facilities |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Rail Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Rail Lines |  |  |  |  |  |  |  | – |  |  |
| Rail Structures |  |  |  |  |  |  |  | – |  |  |
| Rail Furniture |  |  |  |  |  |  |  | – |  |  |
| Drainage Collection |  |  |  |  |  |  |  | – |  |  |
| Storm water Conveyance |  |  |  |  |  |  |  | – |  |  |
| Attenuation |  |  |  |  |  |  |  | – |  |  |
| MV Substations |  |  |  |  |  |  |  | – |  |  |
| LV Networks |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Coastal Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Sand Pumps |  |  |  |  |  |  |  | – |  |  |
| Piers |  |  |  |  |  |  |  | – |  |  |
| Revetments |  |  |  |  |  |  |  | – |  |  |
| Promenades |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Information and Communication Infrastructure |  | – | – | – | – | – | – | – |  | – |
| Data Centres |  |  |  |  |  |  |  | – |  |  |
| Core Layers |  |  |  |  |  |  |  | – |  |  |
| Distribution Layers |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Community Assets |  | – | 2 200 | 2 200 | – | – | 733 | 733 | 100.0% | 2 200 |
| Community Facilities |  | – | 2 200 | 2 200 | – | – | 733 | 733 | 100.0% | 2 200 |
| Halls |  | – | 200 | 200 | – | – | 67 | 67 | 100.0% | 200 |
| Centres |  |  |  |  |  |  |  | – |  |  |
| Crèches |  |  |  |  |  |  |  | – |  |  |
| Clinics/Care Centres |  |  |  |  |  |  |  | – |  |  |
| Fire/Ambulance Stations |  |  |  |  |  |  |  | – |  |  |
| Testing Stations |  |  |  |  |  |  |  | – |  |  |
| Museums |  |  |  |  |  |  |  | – |  |  |
| Galleries |  |  |  |  |  |  |  | – |  |  |
| Theatres |  |  |  |  |  |  |  | – |  |  |
| Libraries |  |  |  |  |  |  |  | – |  |  |
| Cemeteries/Crematoria |  |  |  |  |  |  |  | – |  |  |
| Police |  |  |  |  |  |  |  | – |  |  |
| Purls |  |  |  |  |  |  |  | – |  |  |
| Public Open Space |  | – | – | – | – | – | – | – |  | – |
| Nature Reserves |  | – | 2 000 | 2 000 | – | – | 667 | 667 | 100.0% | 2 000 |
| Public Ablution Facilities |  |  |  |  |  |  |  | – |  |  |
| Markets |  |  |  |  |  |  |  | – |  |  |
| Stalls |  |  |  |  |  |  |  | – |  |  |
| Abattoirs |  |  |  |  |  |  |  | – |  |  |
| Airports |  |  |  |  |  |  |  | – |  |  |
| Taxi Ranks/Bus Terminals |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Sport and Recreation Facilities |  | – | – | – | – | – | – | – |  | – |
| Indoor Facilities |  |  |  |  |  |  |  | – |  |  |
| Outdoor Facilities |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Heritage assets |  | – | – | – | – | – | – | – |  | – |
| Monuments |  |  |  |  |  |  |  | – |  |  |
| Historic Buildings |  |  |  |  |  |  |  | – |  |  |
| Works of Art |  |  |  |  |  |  |  | – |  |  |
| Conservation Areas |  |  |  |  |  |  |  | – |  |  |
| Other Heritage |  |  |  |  |  |  |  | – |  |  |
|  |  |  |  |  |  |  |  | – |  |  |
| Investment properties |  | – | – | – | – | – | – | – |  | – |
| Revenue Generating |  | – | – | – | – | – | – | – |  | – |
| Improved Property |  |  |  |  |  |  |  | – |  |  |
| Unimproved Property |  |  |  |  |  |  |  | – |  |  |
| Non-revenue Generating |  | – | – | – | – | – | – | – |  | – |
| Improved Property |  |  |  |  |  |  |  | – |  |  |
| Unimproved Property |  |  |  |  |  |  |  | – |  |  |
| Other assets |  | – | – | – | – | – | – | – |  | – |
| Operational Buildings |  | – | – | – | – | – | – | – |  | – |
| Municipal Offices |  |  |  |  |  |  |  | – |  |  |
| Pay/Enquiry Points |  |  |  |  |  |  |  | – |  |  |
| Building Plan Offices |  |  |  |  |  |  |  | – |  |  |
| Workshops |  |  |  |  |  |  |  | – |  |  |
| Yards |  |  |  |  |  |  |  | – |  |  |
| Stores |  |  |  |  |  |  |  | – |  |  |
| Laboratories |  |  |  |  |  |  |  | – |  |  |
| Training Centres |  |  |  |  |  |  |  | – |  |  |
| Manufacturing Plant |  |  |  |  |  |  |  | – |  |  |
| Depots |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Housing |  | – | – | – | – | – | – | – |  | – |
| Staff Housing |  |  |  |  |  |  |  | – |  |  |
| Social Housing |  |  |  |  |  |  |  | – |  |  |
| Capital Spares |  |  |  |  |  |  |  | – |  |  |
| Biological or Cultivated Assets |  | – | – | – | – | – | – | – |  | – |
| Biological or Cultivated Assets |  |  |  |  |  |  |  | – |  |  |
| Intangible Assets |  | – | – | – | – | – | – | – |  | – |
| Servitudes |  |  |  |  |  |  |  | – |  |  |
| Licences and Rights |  | – | – | – | – | – | – | – |  | – |
| Water Rights |  |  |  |  |  |  |  | – |  |  |
| Effluent Licenses |  |  |  |  |  |  |  | – |  |  |
| Solid Waste Licenses |  |  |  |  |  |  |  | – |  |  |
| Computer Software and Applications |  | – | – | – | – | – | – | – |  | – |
| Load Settlement Software Applications |  |  |  |  |  |  |  | – |  |  |
| Unspecified |  |  |  |  |  |  |  | – |  |  |
| Computer Equipment |  | – | – | – | – | – | – | – |  | – |
| Computer Equipment |  |  |  |  |  |  |  | – |  |  |
| Furniture and Office Equipment |  | – | – | – | – | – | – | – |  | – |
| Furniture and Office Equipment |  |  |  |  |  |  |  | – |  |  |
| Machinery and Equipment |  | – | – | – | – | – | – | – |  | – |
| Machinery and Equipment |  |  |  |  |  |  |  | – |  |  |
| Transport Assets |  | – | – | – | – | – | – | – |  | – |
| Transport Assets |  |  |  |  |  |  |  | – |  |  |
| Land |  | – | – | – | – | – | – | – |  | – |
| Land |  |  |  |  |  |  |  | – |  |  |
|  |  |  |  |  |  |  |  |  | . |  |
| Zoo's, Marine and Non-biological Animals |  | – | – | – | – | – | – | – |  | – |
| Zoo's, Marine and Non-biological Animals |  |  |  |  |  |  |  | – |  |  |
| Total Capital Expenditure on upgrading of existing assets | 1 | – | 2 200 | 2 200 | – | – | 733 | 733 | 100.0% | 2 200 |

# Capital expenditure for September 2019 is R7 223 962.06

13. Quality Report

# Quality Certificate

I, SJ Mokoena, acting Municipal Manager of Metsimaholo Local Municipality, hereby certify that the monthly budget statement for the month of October 2019 has been prepared in accordance with the Municipal Finance Management Act and the regulations made under the Act.

......................................

# SJ Mokoena

# Acting Municipal Manager of

# Metsimaholo Local Municipality, FS 204

2019/11/26

(SIGNED COPY IS SENT TO NATIONAL TREASURY)